## 표지 (hidden)
하나/외환은행 전자금융 통합 프로젝트
Milestone&WBS
REV.0.8
|  | Category |  | Name | Sign | Date
|  | 자사명 Approval | Author |  |  | 2014-11-07
PL
PM
Client Approval
COPYRIGHT © 웹케시(주). ALL RIGHTS RESERVED
웹케시(주)의 사전 승인 없이 본 내용의 전부 또는 일부에 대한 복사, 전재, 배포, 사용을 금합니다.

## 문서이력관리 (hidden)
하나/외환은행 전자금융 통합 프로젝트
Document History Management
No. | Date | Author | Sheet | Comment / Change | REV
1 | 2014-11-07 |  |  | The first Draft | 0
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
23
24
25
26
27
28
29
30
31
32
33
34
35
36
37
38
39
40

## WBS
하나/외환은행 전자금융 통합 프로젝트 WBS (Work Breakdown Structure)
| Start Date ▶ |  | 2015-02-02 | 6th
| Today ▶ |  | 2015-04-21 | 17th
| End Date ▶ |  | 2015-11-30 | 49th
| PROJECT | [6 empty] | 계획 일정 |  |  |  | 실제 일정 |  |  |  | 진척표시
| ID | TASK |  |  |  |  | 진행상태
|  | Level | Code of Account | Title | Doc | R&R |  | 시작 | 완료 | 가중치 | 기간 | 시작 | 완료 | 가중치 | 기간 | 계획 총기간 | 계획 진척율 | 실제 진척율
[9 empty] | 월-일 |  | Day |  | 월-일 |  | Day
| 1 | 1 | 1 | 프로젝트 관리 |  |  | 0 | 2015-02-09 | 2015-11-30 | 5 | 211 |  |  | 5 | 0 | 0 | 33.65% | 1.157%
| 2 | 2 | 1.1 | 착수/계획 | 착수계 | 수행PM | -1 | 2015-02-09 | 2015-02-27 | 0.8 | 15 |  |  | 0.8 | 0 | 0 | 100% | 5%
| 3 | 3 | 1.1.1 | 프로젝트 착수 |  | 수행PM | -1 | 2015-02-09 | 2015-02-13 | 0.09 | 5 |  |  | 0.09 | 0 | 0 | 100% | 20%
| 4 | 4 | 1.1.1.1 | 사무실환경구성 |  | 사업관리 | -1 | 2015-02-09 | 2015-02-13 | 0.045 | 5 |  |  | 0.045 | 0 | 0 | 100% | 20%
| 5 | 4 | 1.1.1.2 | 조직구성 |  | 사업관리 | -1 | 2015-02-09 | 2015-02-13 | 0.045 | 5 |  |  | 0.045 | 0 | 0 | 100% | 20%
| 6 | 3 | 1.1.2 | 사업수행계획수립 |  | 수행PM | -1 | 2015-02-09 | 2015-02-18 | 0.09 | 8 |  |  | 0.09 | 0 | 0 | 100% | 10%
| 7 | 4 | 1.1.2.1 | 사업수행 계획서 작성 | 사업수행계획서 | 사업관리 | -1 | 2015-02-09 | 2015-02-13 | 0.045 | 5 |  |  | 0.045 | 0 | 0 | 100% | 20%
| 8 | 4 | 1.1.2.2 | 사업수행 계획서 검토/고객승인 |  | 사업관리 | -1 | 2015-02-16 | 2015-02-18 | 0.045 | 3 |  |  | 0.045 | 0 | 0 | 100% | 0%
| 9 | 3 | 1.1.3 | 프로젝트 계획 수립 |  | 수행PM | -1 | 2015-02-09 | 2015-02-18 | 0.09 | 8 |  |  | 0.09 | 0 | 0 | 100% | 10%
| 10 | 4 | 1.1.3.1 | WBS 계획서 작성 | WBS | 사업관리 | -1 | 2015-02-09 | 2015-02-13 | 0.045 | 5 |  |  | 0.045 | 0 | 0 | 100% | 20%
| 11 | 4 | 1.1.3.2 | WBS 계획서 검토/승인 |  | 사업관리 | -1 | 2015-02-16 | 2015-02-18 | 0.045 | 3 |  |  | 0.045 | 0 | 0 | 100% | 0%
| 12 | 3 | 1.1.4 | 품질보증활동 계획 수립 |  | 품질관리 | -1 | 2015-02-09 | 2015-02-18 | 0.09 | 8 |  |  | 0.09 | 0 | 0 | 100% | 5%
| 13 | 4 | 1.1.4.1 | 품질보증활동 계획서 작성 | 품질보증활동계획서 | 품질관리 | -1 | 2015-02-09 | 2015-02-13 | 0.045 | 5 |  |  | 0.045 | 0 | 0 | 100% | 10%
| 14 | 4 | 1.1.4.2 | 품질보증활동 계획 검토/고객승인 |  | 품질관리 | -1 | 2015-02-16 | 2015-02-18 | 0.045 | 3 |  |  | 0.045 | 0 | 0 | 100% | 0%
| 15 | 3 | 1.1.5 | 인력관리 계획 수립 |  | 수행PM | -1 | 2015-02-12 | 2015-02-23 | 0.08 | 8 |  |  | 0.08 | 0 | 0 | 100% | 0%
| 16 | 4 | 1.1.5.1 | 인력관리 계획서 작성 | 인력관리계획서 | 사업관리 | -1 | 2015-02-12 | 2015-02-16 | 0.04 | 3 |  |  | 0.04 | 0 | 0 | 100% | 0%
| 17 | 4 | 1.1.5.2 | 인력관리 계획 검토/승인 |  | 사업관리 | -1 | 2015-02-17 | 2015-02-23 | 0.04 | 5 |  |  | 0.04 | 0 | 0 | 100% | 0%
| 18 | 3 | 1.1.6 | 이슈/리스크 관리 계획 수립 |  | 수행PM | -1 | 2015-02-16 | 2015-02-24 | 0.09 | 7 |  |  | 0.09 | 0 | 0 | 100% | 0%
| 19 | 4 | 1.1.6.1 | 이슈/리스크 관리 계획서 작성 | 이슈/리스크 계획서 | 사업관리 | -1 | 2015-02-16 | 2015-02-17 | 0.045 | 2 |  |  | 0.045 | 0 | 0 | 100% | 0%
| 20 | 4 | 1.1.6.2 | 이슈/리스크 관리 계획 검토/고객승인 |  | 사업관리 | -1 | 2015-02-23 | 2015-02-24 | 0.045 | 2 |  |  | 0.045 | 0 | 0 | 100% | 0%
| 21 | 3 | 1.1.7 | 변경관리 계획 수립 |  | 수행PM | -1 | 2015-02-23 | 2015-02-27 | 0.09 | 5 |  |  | 0.09 | 0 | 0 | 100% | 0%
| 22 | 4 | 1.1.7.1 | 변경관리 계획서 작성 | 변경관리계획서 | 사업관리 | -1 | 2015-02-23 | 2015-02-25 | 0.045 | 3 |  |  | 0.045 | 0 | 0 | 100% | 0%
| 23 | 4 | 1.1.7.2 | 변경관리 계획 검토/고객승인 |  | 사업관리 | -1 | 2015-02-26 | 2015-02-27 | 0.045 | 2 |  |  | 0.045 | 0 | 0 | 100% | 0%
| 24 | 3 | 1.1.8 | 보안관리 계획 수립 |  | 수행PM | -1 | 2015-02-16 | 2015-02-24 | 0.09 | 7 |  |  | 0.09 | 0 | 0 | 100% | 0%
| 25 | 4 | 1.1.8.1 | 보안관리 계획 | 보안관리계획서 | 사업관리 | -1 | 2015-02-16 | 2015-02-17 | 0.045 | 2 |  |  | 0.045 | 0 | 0 | 100% | 0%
| 26 | 4 | 1.1.8.2 | 보안관리 계획 검토/고객승인 |  | 사업관리 | -1 | 2015-02-23 | 2015-02-24 | 0.045 | 2 |  |  | 0.045 | 0 | 0 | 100% | 0%
| 27 | 3 | 1.1.9 | 프로젝트 표준 수립 |  | 품질관리 | -1 | 2015-02-09 | 2015-02-25 | 0.09 | 13 |  |  | 0.09 | 0 | 0 | 100% | 0%
| 28 | 4 | 1.1.9.1 | 문서관리지침 작성 | 문서관리지침서 | 품질관리 | -1 | 2015-02-09 | 2015-02-13 | 0.023 | 5 |  |  | 0.023 | 0 | 0 | 100% | 0%
| 29 | 4 | 1.1.9.2 | 문서관리지침 검토/PM승인 |  | 품질관리 | -1 | 2015-02-16 | 2015-02-17 | 0.02 | 2 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 30 | 4 | 1.1.9.3 | 산출물 표준 양식/템플릿 작성 | 단계별 산출물 템플릿 | 품질관리 | -1 | 2015-02-17 | 2015-02-23 | 0.023 | 5 |  |  | 0.023 | 0 | 0 | 100% | 0%
| 31 | 4 | 1.1.9.4 | 산출물 표준 양식/템플릿 배포 |  | 품질관리 | -1 | 2015-02-24 | 2015-02-25 | 0.024 | 2 |  |  | 0.024 | 0 | 0 | 100% | 0%
| 32 | 2 | 1.2 | 품질보증활동 수행 |  | 품질관리 | 0 | 2015-02-17 | 2015-11-05 | 0.9 | 188 |  |  | 0.9 | 0 | 0 | 33.51% | 0%
| 33 | 3 | 1.2.1 | 품질보증활동 교육 및 검토 |  | 품질관리 | 0 | 2015-02-17 | 2015-11-05 | 0.9 | 188 |  |  | 0.9 | 0 | 0 | 33.51% | 0%
| 34 | 4 | 1.2.1.1 | 품질보증활동 교육 실시(1차) |  | 품질관리 | -1 | 2015-02-17 | 2015-02-23 | 0.0375 | 5 |  |  | 0.0375 | 0 | 0 | 100% | 0%
| 35 | 4 | 1.2.1.2 | 품질보증활동 교육훈련 결과 보고 | 품질보증활동교육훈련결과서 | 품질관리 | -1 | 2015-02-24 | 2015-02-25 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 100% | 0%
| 36 | 4 | 1.2.1.3 | 품질보증활동 교육 실시(2차) |  | 품질관리 | -1 | 2015-03-02 | 2015-03-03 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 100% | 0%
| 37 | 4 | 1.2.1.4 | 품질보증활동 교육훈련 결과 보고 | 품질보증활동교육훈련결과서 | 품질관리 | -1 | 2015-03-04 | 2015-03-05 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 100% | 0%
| 38 | 4 | 1.2.1.5 | 분석단계 품보증활동 내부 검토 | 결함관리대장 | 품질관리 | -1 | 2015-03-02 | 2015-03-03 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 100% | 0%
| 39 | 4 | 1.2.1.6 | 분석단계 품보증활동 내부 검토 조치 결과 | 결함관리대장 | 품질관리 | -1 | 2015-03-04 | 2015-03-05 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 100% | 0%
| 40 | 4 | 1.2.1.7 | 분석단계 품보증활동 QA 검토 | 결함관리대장 | 품질관리 | -1 | 2015-03-06 | 2015-03-09 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 100% | 0%
| 41 | 4 | 1.2.1.8 | 분석단계 품보증활동 QA 검토 조치 결과 | 품질보증활동결과서 | 품질관리 | -1 | 2015-03-10 | 2015-03-12 | 0.0375 | 3 |  |  | 0.0375 | 0 | 0 | 100% | 0%
| 42 | 4 | 1.2.1.9 | 설계단계 품보증활동 내부 검토 | 결함관리대장 | 품질관리 | -1 | 2015-04-20 | 2015-04-21 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 100% | 0%
| 43 | 4 | 1.2.1.10 | 설계단계 품보증활동 내부 검토 조치 결과 | 결함관리대장 | 품질관리 | 0 | 2015-04-22 | 2015-04-23 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 44 | 4 | 1.2.1.11 | 설계단계 품보증활동 QA 검토 | 결함관리대장 | 품질관리 | 0 | 2015-04-24 | 2015-04-27 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 45 | 4 | 1.2.1.12 | 설계단계 품보증활동 QA 검토 조치 결과 | 품질보증활동결과서 | 품질관리 | 0 | 2015-04-28 | 2015-04-30 | 0.0375 | 3 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 46 | 4 | 1.2.1.13 | 구현단계 품보증활동 내부 검토 | 결함관리대장 | 품질관리 | 0 | 2015-06-22 | 2015-06-23 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 47 | 4 | 1.2.1.14 | 구현단계 품보증활동 내부 검토 조치 결과 | 결함관리대장 | 품질관리 | 0 | 2015-06-24 | 2015-06-25 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 48 | 4 | 1.2.1.15 | 구현단계 품보증활동 QA 검토 | 결함관리대장 | 품질관리 | 0 | 2015-06-26 | 2015-06-29 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 49 | 4 | 1.2.1.16 | 구현단계 품보증활동 QA 검토 조치 결과 | 품질보증활동결과서 | 품질관리 | 0 | 2015-06-30 | 2015-07-02 | 0.0375 | 3 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 50 | 4 | 1.2.1.17 | 테스트단계 품보증활동 내부 검토 | 결함관리대장 | 품질관리 | 0 | 2015-10-12 | 2015-10-13 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 51 | 4 | 1.2.1.18 | 테스트단계 품보증활동 내부 검토 조치 결과 | 결함관리대장 | 품질관리 | 0 | 2015-10-14 | 2015-10-15 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 52 | 4 | 1.2.1.19 | 테스트단계 품보증활동 QA 검토 | 결함관리대장 | 품질관리 | 0 | 2015-10-16 | 2015-10-19 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 53 | 4 | 1.2.1.20 | 테스트단계 품보증활동 QA 검토 조치 결과 | 품질보증활동결과서 | 품질관리 | 0 | 2015-10-20 | 2015-10-23 | 0.0375 | 4 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 54 | 4 | 1.2.1.21 | 이행단계 품보증활동 내부 검토 | 결함관리대장 | 품질관리 | 0 | 2015-10-26 | 2015-10-27 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 55 | 4 | 1.2.1.22 | 이행단계 품보증활동 내부 검토 조치 결과 | 결함관리대장 | 품질관리 | 0 | 2015-10-28 | 2015-10-28 | 0.0375 | 1 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 56 | 4 | 1.2.1.23 | 이행단계 품보증활동 QA 검토 | 결함관리대장 | 품질관리 | 0 | 2015-10-30 | 2015-11-02 | 0.0375 | 2 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 57 | 4 | 1.2.1.24 | 이행단계 품보증활동 QA 검토 조치 결과 | 품질보증활동결과서 | 품질관리 | 0 | 2015-11-03 | 2015-11-05 | 0.0375 | 3 |  |  | 0.0375 | 0 | 0 | 0% | 0%
| 58 | 2 | 1.3 | 중간보고회 |  | PM | 0 | 2015-06-15 | 2015-06-23 | 0.8 | 7 |  |  | 0.8 | 0 | 0 | 0% | 0%
| 59 | 3 | 1.3.1 | 중간보고 준비 |  | PM | 0 | 2015-06-15 | 2015-06-23 | 0.8 | 7 |  |  | 0.8 | 0 | 0 | 0% | 0%
| 60 | 4 | 1.3.1.1 | 중간보고서 작성 | 중간보고서 | 사업관리 | 0 | 2015-06-15 | 2015-06-19 | 0.4 | 5 |  |  | 0.4 | 0 | 0 | 0% | 0%
| 61 | 4 | 1.3.1.2 | 중간보고 발표 및 고객승인 |  | 사업관리 | 0 | 2015-06-22 | 2015-06-23 | 0.4 | 2 |  |  | 0.4 | 0 | 0 | 0% | 0%
| 62 | 2 | 1.4 | 정기보고 |  | PM | 0 | 2015-02-13 | 2015-10-30 | 0.9 | 186 |  |  | 0.9 | 0 | 0 | 36.02% | 0%
| 63 | 3 | 1.4.1 | 주간업무 |  | PM | 0 | 2015-02-13 | 2015-10-30 | 0.45 | 186 |  |  | 0.45 | 0 | 0 | 36.02% | 0%
| 64 | 4 | 1.4.1.2 | 주간업무 1주차 | 주간업무보고서 | 사업관리 | -1 | 2015-02-13 | 2015-02-13 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 65 | 4 | 1.4.1.3 | 주간업무 2주차 | 주간업무보고서 | 사업관리 | -1 | 2015-02-23 | 2015-02-23 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 66 | 4 | 1.4.1.4 | 주간업무 3주차 | 주간업무보고서 | 사업관리 | -1 | 2015-02-27 | 2015-02-27 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 67 | 4 | 1.4.1.5 | 주간업무 4주차 | 주간업무보고서 | 사업관리 | -1 | 2015-03-06 | 2015-03-06 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 68 | 4 | 1.4.1.6 | 주간업무 5주차 | 주간업무보고서 | 사업관리 | -1 | 2015-03-13 | 2015-03-13 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 69 | 4 | 1.4.1.7 | 주간업무 6주차 | 주간업무보고서 | 사업관리 | -1 | 2015-03-20 | 2015-03-20 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 70 | 4 | 1.4.1.8 | 주간업무 7주차 | 주간업무보고서 | 사업관리 | -1 | 2015-03-27 | 2015-03-27 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 71 | 4 | 1.4.1.9 | 주간업무 8주차 | 주간업무보고서 | 사업관리 | -1 | 2015-04-03 | 2015-04-03 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 72 | 4 | 1.4.1.10 | 주간업무 9주차 | 주간업무보고서 | 사업관리 | -1 | 2015-04-10 | 2015-04-10 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 73 | 4 | 1.4.1.11 | 주간업무 10주차 | 주간업무보고서 | 사업관리 | -1 | 2015-04-17 | 2015-04-17 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 100% | 0%
| 74 | 4 | 1.4.1.12 | 주간업무 11주차 | 주간업무보고서 | 사업관리 | 0 | 2015-04-24 | 2015-04-24 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 75 | 4 | 1.4.1.13 | 주간업무 12주차 | 주간업무보고서 | 사업관리 | 0 | 2015-05-01 | 2015-05-01 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 76 | 4 | 1.4.1.14 | 주간업무 13주차 | 주간업무보고서 | 사업관리 | 0 | 2015-05-08 | 2015-05-08 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 77 | 4 | 1.4.1.15 | 주간업무 14주차 | 주간업무보고서 | 사업관리 | 0 | 2015-05-15 | 2015-05-15 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 78 | 4 | 1.4.1.16 | 주간업무 15주차 | 주간업무보고서 | 사업관리 | 0 | 2015-05-22 | 2015-05-22 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 79 | 4 | 1.4.1.17 | 주간업무 16주차 | 주간업무보고서 | 사업관리 | 0 | 2015-05-29 | 2015-05-29 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 80 | 4 | 1.4.1.18 | 주간업무 17주차 | 주간업무보고서 | 사업관리 | 0 | 2015-06-05 | 2015-06-05 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 81 | 4 | 1.4.1.19 | 주간업무 18주차 | 주간업무보고서 | 사업관리 | 0 | 2015-06-12 | 2015-06-12 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 82 | 4 | 1.4.1.20 | 주간업무 19주차 | 주간업무보고서 | 사업관리 | 0 | 2015-06-19 | 2015-06-19 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 83 | 4 | 1.4.1.21 | 주간업무 20주차 | 주간업무보고서 | 사업관리 | 0 | 2015-06-26 | 2015-06-26 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 84 | 4 | 1.4.1.22 | 주간업무 21주차 | 주간업무보고서 | 사업관리 | 0 | 2015-07-03 | 2015-07-03 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 85 | 4 | 1.4.1.23 | 주간업무 22주차 | 주간업무보고서 | 사업관리 | 0 | 2015-07-10 | 2015-07-10 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 86 | 4 | 1.4.1.24 | 주간업무 23주차 | 주간업무보고서 | 사업관리 | 0 | 2015-07-17 | 2015-07-17 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 87 | 4 | 1.4.1.25 | 주간업무 24주차 | 주간업무보고서 | 사업관리 | 0 | 2015-07-24 | 2015-07-24 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 88 | 4 | 1.4.1.26 | 주간업무 25주차 | 주간업무보고서 | 사업관리 | 0 | 2015-07-31 | 2015-07-31 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 89 | 4 | 1.4.1.27 | 주간업무 26주차 | 주간업무보고서 | 사업관리 | 0 | 2015-08-07 | 2015-08-07 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 90 | 4 | 1.4.1.28 | 주간업무 27주차 | 주간업무보고서 | 사업관리 | 0 | 2015-08-14 | 2015-08-14 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 91 | 4 | 1.4.1.29 | 주간업무 28주차 | 주간업무보고서 | 사업관리 | 0 | 2015-08-21 | 2015-08-21 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 92 | 4 | 1.4.1.30 | 주간업무 29주차 | 주간업무보고서 | 사업관리 | 0 | 2015-08-28 | 2015-08-28 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 93 | 4 | 1.4.1.31 | 주간업무 30주차 | 주간업무보고서 | 사업관리 | 0 | 2015-09-04 | 2015-09-04 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 94 | 4 | 1.4.1.32 | 주간업무 31주차 | 주간업무보고서 | 사업관리 | 0 | 2015-09-11 | 2015-09-11 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 95 | 4 | 1.4.1.33 | 주간업무 32주차 | 주간업무보고서 | 사업관리 | 0 | 2015-09-18 | 2015-09-18 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 96 | 4 | 1.4.1.34 | 주간업무 33주차 | 주간업무보고서 | 사업관리 | 0 | 2015-09-25 | 2015-09-25 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 97 | 4 | 1.4.1.35 | 주간업무 34주차 | 주간업무보고서 | 사업관리 | 0 | 2015-10-02 | 2015-10-02 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 98 | 4 | 1.4.1.36 | 주간업무 35주차 | 주간업무보고서 | 사업관리 | 0 | 2015-10-08 | 2015-10-08 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 99 | 4 | 1.4.1.37 | 주간업무 36주차 | 주간업무보고서 | 사업관리 | 0 | 2015-10-16 | 2015-10-16 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 100 | 4 | 1.4.1.38 | 주간업무 37주차 | 주간업무보고서 | 사업관리 | 0 | 2015-10-23 | 2015-10-23 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 101 | 4 | 1.4.1.39 | 주간업무 38주차 | 주간업무보고서 | 사업관리 | 0 | 2015-10-30 | 2015-10-30 | 0.011538 | 1 |  |  | 0.011538 | 0 | 0 | 0% | 0%
| 102 | 3 | 1.4.2 | 월간업무 |  | PM | 0 | 2015-02-27 | 2015-10-30 | 0.45 | 176 |  |  | 0.45 | 0 | 0 | 30.11% | 0%
| 103 | 4 | 1.4.2.1 | 월간업무 2월 | 월간업무보고서 | 사업관리 | -1 | 2015-02-27 | 2015-02-27 | 0.05 | 1 |  |  | 0.05 | 0 | 0 | 100% | 0%
| 104 | 4 | 1.4.2.2 | 월간업무 3월 | 월간업무보고서 | 사업관리 | -1 | 2015-03-27 | 2015-03-27 | 0.05 | 1 |  |  | 0.05 | 0 | 0 | 100% | 0%
| 105 | 4 | 1.4.2.3 | 월간업무 4월 | 월간업무보고서 | 사업관리 | 0 | 2015-05-01 | 2015-05-01 | 0.05 | 1 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 106 | 4 | 1.4.2.4 | 월간업무 5월 | 월간업무보고서 | 사업관리 | 0 | 2015-05-29 | 2015-05-29 | 0.05 | 1 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 107 | 4 | 1.4.2.5 | 월간업무 6월 | 월간업무보고서 | 사업관리 | 0 | 2015-07-03 | 2015-07-03 | 0.05 | 1 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 108 | 4 | 1.4.2.6 | 월간업무 7월 | 월간업무보고서 | 사업관리 | 0 | 2015-07-31 | 2015-07-31 | 0.05 | 1 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 109 | 4 | 1.4.2.7 | 월간업무 8월 | 월간업무보고서 | 사업관리 | 0 | 2015-08-28 | 2015-08-28 | 0.05 | 1 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 110 | 4 | 1.4.2.8 | 월간업무 9월 | 월간업무보고서 | 사업관리 | 0 | 2015-10-02 | 2015-10-02 | 0.05 | 1 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 111 | 4 | 1.4.2.9 | 월간업무 10월 | 월간업무보고서 | 사업관리 | 0 | 2015-10-30 | 2015-10-30 | 0.05 | 1 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 112 | 2 | 1.5 | 고객 검토 및 승인 |  | PM | 0 | 2015-03-13 | 2015-11-10 | 0.8 | 173 |  |  | 0.8 | 0 | 0 | 22.54% | 0%
| 113 | 3 | 1.5.1 | 단계별 산출물 |  | PM | 0 | 2015-03-13 | 2015-11-10 | 0.8 | 173 |  |  | 0.8 | 0 | 0 | 22.54% | 0%
| 114 | 4 | 1.5.1.1 | 분석단계 산출물 고객 검토 및 승인 | 분석단계산출물 | 사업관리 | -1 | 2015-03-13 | 2015-03-17 | 0.16 | 3 |  |  | 0.16 | 0 | 0 | 100% | 0%
| 115 | 4 | 1.5.1.2 | 설계단계 산출물 고객 검토 및 승인 | 설계단계산출물 | 사업관리 | 0 | 2015-05-01 | 2015-05-06 | 0.16 | 4 |  |  | 0.16 | 0 | 0 | 0% | 0%
| 116 | 4 | 1.5.1.3 | 구현단계 산출물 고객 검토 및 승인 | 구현단계산출물 | 사업관리 | 0 | 2015-07-03 | 2015-07-07 | 0.16 | 3 |  |  | 0.16 | 0 | 0 | 0% | 0%
| 117 | 4 | 1.5.1.4 | 테스트단계 산출물 고객 검토 및 승인 | 테스트단계산출물 | 사업관리 | 0 | 2015-10-26 | 2015-10-28 | 0.16 | 3 |  |  | 0.16 | 0 | 0 | 0% | 0%
| 118 | 4 | 1.5.1.5 | 이행단계 산출물 고객 검토 및 승인 | 이행단계산출물 | 사업관리 | 0 | 2015-11-06 | 2015-11-10 | 0.16 | 3 |  |  | 0.16 | 0 | 0 | 0% | 0%
| 119 | 2 | 1.6 | 완료보고회 |  | PM | 0 | 2015-11-23 | 2015-11-30 | 0.8 | 6 |  |  | 0.8 | 0 | 0 | 0% | 0%
| 120 | 3 | 1.6.1 | 완료보고서 준비 |  | PM | 0 | 2015-11-23 | 2015-11-30 | 0.8 | 6 |  |  | 0.8 | 0 | 0 | 0% | 0%
| 121 | 4 | 1.6.1.1 | 완료보고서 작성 | 완료보고서 | 사업관리 | 0 | 2015-11-23 | 2015-11-27 | 0.4 | 5 |  |  | 0.4 | 0 | 0 | 0% | 0%
| 122 | 4 | 1.6.1.2 | 완료보고 발표 및 고객승인 |  | 사업관리 | 0 | 2015-11-30 | 2015-11-30 | 0.4 | 1 |  |  | 0.4 | 0 | 0 | 0% | 0%
| 123 | 1 | 2 | 개인인터넷 뱅킹 |  |  | 0 | 2015-02-09 | 2015-08-14 | 3.995 | 135 |  |  | 3.995 | 0 | 0 |  | 0%
| 124 | 2 | 2.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-03-20 | 1.3 | 30 |  |  | 1.3 | 0 | 0 |  | 0%
| 125 | 3 | 2.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.04 | 15 |  |  | 0.04 | 0 | 0 |  | 0%
| 126 | 4 | 2.1.1.1 | 양행시스템분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.04 | 15 |  |  | 0.04 | 0 | 0 |  | 0%
| 127 | 3 | 2.1.2 | GAP 분석 |  |  | -1 | 2015-02-09 | 2015-03-13 | 1.08 | 25 |  |  | 1.08 | 0 | 0 |  | 0%
| 128 | 4 | 2.1.2.1 | 메뉴 GAP분석 |  |  | -1 | 2015-02-09 | 2015-03-06 | 0.54 | 20 |  |  | 0.54 | 0 | 0 |  | 0%
| 129 | 5 | 2.1.2.1.1 | 마이하나 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-09 | 2015-02-17 | 0.03 | 7 |  |  | 0.03 | 0 | 0 |  | 0%
| 130 | 5 | 2.1.2.1.2 | 부가서비스 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-16 | 2015-02-27 | 0.03 | 10 |  |  | 0.03 | 0 | 0 |  | 0%
| 131 | 5 | 2.1.2.1.3 | 보험공제 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-23 | 2015-02-27 | 0.03 | 5 |  |  | 0.03 | 0 | 0 |  | 0%
| 132 | 5 | 2.1.2.1.4 | 예금신탁 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-09 | 2015-02-17 | 0.03 | 7 |  |  | 0.03 | 0 | 0 |  | 0%
| 133 | 5 | 2.1.2.1.5 | 대출 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-16 | 2015-02-27 | 0.03 | 10 |  |  | 0.03 | 0 | 0 |  | 0%
| 134 | 5 | 2.1.2.1.6 | 펀드 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-23 | 2015-02-27 | 0.03 | 5 |  |  | 0.03 | 0 | 0 |  | 0%
| 135 | 5 | 2.1.2.1.7 | 조회 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-09 | 2015-02-17 | 0.03 | 7 |  |  | 0.03 | 0 | 0 |  | 0%
| 136 | 5 | 2.1.2.1.8 | 이체 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-16 | 2015-03-06 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 137 | 5 | 2.1.2.1.9 | 카드 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-23 | 2015-03-06 | 0.03 | 10 |  |  | 0.03 | 0 | 0 |  | 0%
| 138 | 5 | 2.1.2.1.10 | 공과금 | 현행 시스템 분석서 | 분석/설계자4 | -1 | 2015-02-09 | 2015-02-27 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 139 | 5 | 2.1.2.1.11 | 기업결제 | 현행 시스템 분석서 | 분석/설계자4 | -1 | 2015-02-09 | 2015-03-06 | 0.06 | 20 |  |  | 0.06 | 0 | 0 |  | 0%
| 140 | 5 | 2.1.2.1.12 | 외환 | 현행 시스템 분석서 | 분석/설계자5 | -1 | 2015-02-09 | 2015-02-27 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 141 | 5 | 2.1.2.1.13 | 공인인증센터 | 현행 시스템 분석서 | 분석/설계자6 | -1 | 2015-02-16 | 2015-03-06 | 0.04 | 15 |  |  | 0.04 | 0 | 0 |  | 0%
| 142 | 5 | 2.1.2.1.14 | 보안매체 | 현행 시스템 분석서 | 분석/설계자6 | -1 | 2015-02-16 | 2015-03-06 | 0.04 | 15 |  |  | 0.04 | 0 | 0 |  | 0%
| 143 | 5 | 2.1.2.1.15 | 메인 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-23 | 2015-03-06 | 0.03 | 10 |  |  | 0.03 | 0 | 0 |  | 0%
| 144 | 4 | 2.1.2.2 | 전문 GAP분석 |  |  | -1 | 2015-02-09 | 2015-03-13 | 0.48 | 25 |  |  | 0.48 | 0 | 0 |  | 0%
| 145 | 5 | 2.1.2.2.1 | 마이하나 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-09 | 2015-02-27 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 146 | 5 | 2.1.2.2.2 | 부가서비스 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-16 | 2015-03-06 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 147 | 5 | 2.1.2.2.3 | 보험공제 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-23 | 2015-02-27 | 0.03 | 5 |  |  | 0.03 | 0 | 0 |  | 0%
| 148 | 5 | 2.1.2.2.4 | 예금신탁 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-09 | 2015-02-27 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 149 | 5 | 2.1.2.2.5 | 대출 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-16 | 2015-03-06 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 150 | 5 | 2.1.2.2.6 | 펀드 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-23 | 2015-03-06 | 0.03 | 10 |  |  | 0.03 | 0 | 0 |  | 0%
| 151 | 5 | 2.1.2.2.7 | 조회 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-09 | 2015-02-27 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 152 | 5 | 2.1.2.2.8 | 이체 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-16 | 2015-03-13 | 0.03 | 20 |  |  | 0.03 | 0 | 0 |  | 0%
| 153 | 5 | 2.1.2.2.9 | 카드 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-23 | 2015-03-13 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 154 | 5 | 2.1.2.2.10 | 공과금 | 현행 시스템 분석서 | 분석/설계자4 | -1 | 2015-02-09 | 2015-03-06 | 0.03 | 20 |  |  | 0.03 | 0 | 0 |  | 0%
| 155 | 5 | 2.1.2.2.11 | 기업결제 | 현행 시스템 분석서 | 분석/설계자4 | -1 | 2015-02-23 | 2015-03-13 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 156 | 5 | 2.1.2.2.12 | 외환 | 현행 시스템 분석서 | 분석/설계자5 | -1 | 2015-02-09 | 2015-03-13 | 0.06 | 25 |  |  | 0.06 | 0 | 0 |  | 0%
| 157 | 5 | 2.1.2.2.13 | 공인인증센터 | 현행 시스템 분석서 | 분석/설계자6 | -1 | 2015-02-09 | 2015-03-06 | 0.03 | 20 |  |  | 0.03 | 0 | 0 |  | 0%
| 158 | 5 | 2.1.2.2.14 | 보안매체 | 현행 시스템 분석서 | 분석/설계자6 | -1 | 2015-02-16 | 2015-03-13 | 0.03 | 20 |  |  | 0.03 | 0 | 0 |  | 0%
| 159 | 5 | 2.1.2.2.15 | 메인 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-23 | 2015-03-13 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 160 | 4 | 2.1.2.3 | 테이블/속성 GAP분석 |  |  | -1 | 2015-02-23 | 2015-03-06 | 0.06 | 10 |  |  | 0.06 | 0 | 0 |  | 0%
| 161 | 5 | 2.1.2.3 | 테이블/속성 GAP분석 | 현행 시스템 분석서 | 분석/설계자 | -1 | 2015-02-23 | 2015-03-06 | 0.06 | 10 |  |  | 0.06 | 0 | 0 |  | 0%
| 162 | 3 | 2.1.3 | 통합업무확정 |  |  | -1 | 2015-02-16 | 2015-02-27 | 0 | 10 |  |  | 0 | 0 | 0 |  | 0%
| 163 | 4 | 2.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 | 기획자 | -1 | 2015-02-16 | 2015-02-27 | 0 | 10 |  |  | 0 | 0 | 0 |  | 0%
| 164 | 3 | 2.1.4 | 통합요건정의 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.12 | 10 |  |  | 0.12 | 0 | 0 |  | 0%
| 165 | 4 | 2.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 업무총괄 | -1 | 2015-03-02 | 2015-03-13 | 0.12 | 10 |  |  | 0.12 | 0 | 0 |  | 0%
| 166 | 3 | 2.1.5 | 논리모델구축 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 167 | 4 | 2.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 | BT분석/설계자 | -1 | 2015-03-16 | 2015-03-20 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 168 | 2 | 2.2 | 설계 |  |  | 0 | 2015-03-02 | 2015-05-01 | 1.3 | 45 |  |  | 1.3 | 0 | 0 |  | 0%
| 169 | 3 | 2.2.1 | 통합온라인 프로세스 설계 |  |  | 0 | 2015-03-02 | 2015-05-01 | 1.05 | 45 |  |  | 1.05 | 0 | 0 |  | 0%
| 170 | 4 | 2.2.1.1 | 화면설계 |  |  | -1 | 2015-03-02 | 2015-04-17 | 0 | 35 |  |  | 0 | 0 | 0 |  | 0%
| 171 | 4 | 2.2.1.2 | 프로그램 설계 |  |  | 0 | 2015-03-02 | 2015-05-01 | 1.05 | 45 |  |  | 1.05 | 0 | 0 |  | 0%
| 172 | 5 | 2.2.1.2.1 | MyHana | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-02 | 2015-04-03 | 0.08 | 25 |  |  | 0.08 | 0 | 0 |  | 0%
| 173 | 5 | 2.2.1.2.2 | 부가서비스 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-04-03 | 0.06 | 15 |  |  | 0.06 | 0 | 0 |  | 0%
| 174 | 5 | 2.2.1.2.3 | 보험/공제 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-04-06 | 2015-04-17 | 0.04 | 10 |  |  | 0.04 | 0 | 0 |  | 0%
| 175 | 5 | 2.2.1.2.4 | 예금신탁(신규외) | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-02 | 2015-03-13 | 0.04 | 10 |  |  | 0.04 | 0 | 0 |  | 0%
| 176 | 5 | 2.2.1.2.4 | 예금신탁(신규) | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-04-17 | 0.08 | 25 |  |  | 0.08 | 0 | 0 |  | 0%
| 177 | 5 | 2.2.1.2.5 | 대출 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.07 | 20 |  |  | 0.07 | 0 | 0 |  | 0%
| 178 | 5 | 2.2.1.2.6 | 펀드 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-23 | 2015-04-17 | 0.07 | 20 |  |  | 0.07 | 0 | 0 |  | 0%
| 179 | 5 | 2.2.1.2.7 | 이체 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-04-03 | 0.06 | 15 |  |  | 0.06 | 0 | 0 |  | 0%
| 180 | 5 | 2.2.1.2.8 | 조회 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.07 | 20 |  |  | 0.07 | 0 | 0 |  | 0%
| 181 | 5 | 2.2.1.2.9 | 카드 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-23 | 2015-04-17 | 0.07 | 20 |  |  | 0.07 | 0 | 0 |  | 0%
| 182 | 5 | 2.2.1.2.10 | 공과금 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-09 | 2015-04-10 | 0.08 | 25 |  |  | 0.08 | 0 | 0 |  | 0%
| 183 | 5 | 2.2.1.2.11 | 기업결제 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-30 | 2015-04-17 | 0.06 | 15 |  |  | 0.06 | 0 | 0 |  | 0%
| 184 | 5 | 2.2.1.2.12 | 외환 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-04-17 | 0.12 | 25 |  |  | 0.12 | 0 | 0 |  | 0%
| 185 | 5 | 2.2.1.2.13 | 공인인증센터 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-04-17 | 0.08 | 25 |  |  | 0.08 | 0 | 0 |  | 0%
| 186 | 5 | 2.2.1.2.14 | 메인 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-30 | 2015-04-17 | 0.04 | 15 |  |  | 0.04 | 0 | 0 |  | 0%
| 187 | 5 | 2.2.1.2.15 | 추가 변경/신규요건 설계 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | 0 | 2015-04-20 | 2015-05-01 | 0.03 | 10 |  |  | 0.03 | 0 | 0 |  | 0%
| 188 | 3 | 2.2.2 | 통합전문설계 |  |  | -1 | 2015-03-23 | 2015-04-17 | 0.25 | 20 |  |  | 0.25 | 0 | 0 |  | 0%
| 189 | 4 | 2.2.2.1 | 전문매핑 |  |  | -1 | 2015-03-23 | 2015-04-17 | 0.25 | 20 |  |  | 0.25 | 0 | 0 |  | 0%
| 190 | 5 | 2.2.2.1.1 | 전문목록작성 | 전문목록 | BT분석/설계자 | -1 | 2015-03-23 | 2015-03-27 | 0.1 | 5 |  |  | 0.1 | 0 | 0 |  | 0%
| 191 | 5 | 2.2.2.1.3 | 전문매핑정의서작성 | 전문매핑정의서 | BT분석/설계자 | -1 | 2015-03-30 | 2015-04-17 | 0.15 | 15 |  |  | 0.15 | 0 | 0 |  | 0%
| 192 | 2 | 2.3 | 구현 |  |  | 0 | 2015-03-16 | 2015-08-14 | 1.395 | 110 |  |  | 1.395 | 0 | 0 |  | 0%
| 193 | 3 | 2.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-08-14 | 0.56 | 110 |  |  | 0.56 | 0 | 0 |  | 0%
| 194 | 4 | 2.3.1.1 | 온라인 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-08-14 | 0.56 | 110 |  |  | 0.56 | 0 | 0 |  | 0%
| 195 | 5 | 2.3.1.1.1 | 보안취약성점검 및 보완 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-04-03 | 0 | 15 |  |  | 0 | 0 | 0 |  | 0%
| 196 | 5 | 2.3.1.1.2 | MyHana |  |  | 0 | 2015-03-16 | 2015-05-29 | 0.055 | 55 |  |  | 0.055 | 0 | 0 |  | 0%
| 197 | 6 | 2.3.1.1.2.1 | 메인_분실신고 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-03-20 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 198 | 6 | 2.3.1.1.2.2 | 개인정보관리 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-03-27 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 199 | 6 | 2.3.1.1.2.3 | 뱅킹정보관리 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-10 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 200 | 6 | 2.3.1.1.2.4 | 통지서비스 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 201 | 6 | 2.3.1.1.2.5 | 자산관리_소득_개인신용정보 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 202 | 6 | 2.3.1.1.2.6 | 보안서비스 신청/관리 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-01 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 203 | 6 | 2.3.1.1.2.7 | 보안서비스_추천 e-Banking | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 204 | 6 | 2.3.1.1.2.8 | 보안서비스_전자금융보안 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 205 | 6 | 2.3.1.1.2.9 | 보안서비스_마이금융정보 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-29 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 206 | 5 | 2.3.1.1.3 | 부가서비스 |  |  | 0 | 2015-05-04 | 2015-06-05 | 0.01 | 25 |  |  | 0.01 | 0 | 0 |  | 0%
| 207 | 6 | 2.3.1.1.3.1 | 금융IC카드 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-29 | 0.005 | 20 |  |  | 0.005 | 0 | 0 |  | 0%
| 208 | 6 | 2.3.1.1.3.2 | 국민주택채권_전자공무원_학생증 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-01 | 2015-06-05 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 209 | 5 | 2.3.1.1.4 | 보험/공제 |  |  | 0 | 2015-06-01 | 2015-06-12 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 210 | 6 | 2.3.1.1.4.1 | 가입내역조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-01 | 2015-06-12 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 211 | 5 | 2.3.1.1.5 | 예금신탁 |  |  | 0 | 2015-03-16 | 2015-05-22 | 0.03 | 50 |  |  | 0.03 | 0 | 0 |  | 0%
| 212 | 6 | 2.3.1.1.5.1 | 신규가입 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-04-10 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 213 | 6 | 2.3.1.1.5.2 | 예금가입/해지_연금저축신탁가입/해지 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-13 | 2015-04-24 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 214 | 6 | 2.3.1.1.5.3 | 특정금전신탁_IRP_금리변경통지 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-22 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 215 | 5 | 2.3.1.1.6 | 대출 |  |  | 0 | 2015-05-04 | 2015-06-19 | 0.025 | 35 |  |  | 0.025 | 0 | 0 |  | 0%
| 216 | 6 | 2.3.1.1.6.1 | 대출조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 217 | 6 | 2.3.1.1.6.2 | 대출상환/이자납입_예담대 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 218 | 6 | 2.3.1.1.6.3 | 대출신청 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-06-12 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 219 | 6 | 2.3.1.1.6.4 | 원클릭_보금자리_디딤돌_신용대출 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-15 | 2015-06-19 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 220 | 5 | 2.3.1.1.7 | 펀드 |  |  | 0 | 2015-05-04 | 2015-06-15 | 0.03 | 31 |  |  | 0.03 | 0 | 0 |  | 0%
| 221 | 6 | 2.3.1.1.7.1 | 신규가입 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-15 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 222 | 6 | 2.3.1.1.7.2 | 투자의 달인_판드환매 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-22 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 223 | 6 | 2.3.1.1.7.3 | 펀드조회/추가입금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-26 | 2015-06-01 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 224 | 6 | 2.3.1.1.7.4 | 펀드서비스 신청/해제_마이펀드 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-02 | 2015-06-15 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 225 | 5 | 2.3.1.1.8 | 이체 |  |  | 0 | 2015-03-16 | 2015-05-15 | 0.05 | 45 |  |  | 0.05 | 0 | 0 |  | 0%
| 226 | 6 | 2.3.1.1.8.1 | KEB 시소 펀드적금이체 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-03-27 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 227 | 6 | 2.3.1.1.8.2 | 자금_예약_자동이체 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-10 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 228 | 6 | 2.3.1.1.8.3 | 중도금_파일_퇴직연금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 229 | 6 | 2.3.1.1.8.4 | 이체내역조회_수수료_인터넷청약_경매 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 230 | 6 | 2.3.1.1.8.5 | 기부 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-15 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 231 | 5 | 2.3.1.1.9 | 조회 |  |  | 0 | 2015-05-11 | 2015-06-09 | 0.02 | 22 |  |  | 0.02 | 0 | 0 |  | 0%
| 232 | 6 | 2.3.1.1.9.1 | 계좌조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 233 | 6 | 2.3.1.1.9.2 | 예금/신탁기타조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-22 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 234 | 6 | 2.3.1.1.9.3 | 펀드조회_대출_보험_수표조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-27 | 2015-06-02 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 235 | 6 | 2.3.1.1.9.4 | 모임통장_해외지점계좌조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-03 | 2015-06-09 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 236 | 5 | 2.3.1.1.10 | 카드 |  |  | 0 | 2015-06-01 | 2015-06-19 | 0.015 | 15 |  |  | 0.015 | 0 | 0 |  | 0%
| 237 | 6 | 2.3.1.1.10.1 | my카드_조회_결제_현금서비스 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-01 | 2015-06-05 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 238 | 6 | 2.3.1.1.10.2 | 카드론_포인트/마일리지 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-08 | 2015-06-12 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 239 | 6 | 2.3.1.1.10.3 | 이용한도_M/S카드_현금카드결제 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-15 | 2015-06-19 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 240 | 5 | 2.3.1.1.11 | 공과금 |  |  | 0 | 2015-03-16 | 2015-05-22 | 0.05 | 50 |  |  | 0.05 | 0 | 0 |  | 0%
| 241 | 6 | 2.3.1.1.11.1 | MY공과금_지로_지방세 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-03-27 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 242 | 6 | 2.3.1.1.11.2 | 국세 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-10 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 243 | 6 | 2.3.1.1.11.3 | 관세_기타세입금_생활요금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 244 | 6 | 2.3.1.1.11.4 | 아파트관리비 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 245 | 6 | 2.3.1.1.11.5 | 범칙금/벌과금_연금/보험금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 246 | 6 | 2.3.1.1.11.6 | 법원공과금_기금_대학등록금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-22 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 247 | 5 | 2.3.1.1.12 | 기업결제 |  |  | 0 | 2015-04-13 | 2015-05-29 | 0.025 | 35 |  |  | 0.025 | 0 | 0 |  | 0%
| 248 | 6 | 2.3.1.1.12.1 | 판매기업 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-13 | 2015-04-24 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 249 | 6 | 2.3.1.1.12.2 | 구매기업 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-01 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 250 | 6 | 2.3.1.1.12.3 | 질권설정 메뉴(4개) | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-29 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 251 | 5 | 2.3.1.1.13 | 외환 |  |  | 0 | 2015-03-16 | 2015-06-19 | 0.19 | 70 |  |  | 0.19 | 0 | 0 |  | 0%
| 252 | 6 | 3.3.1.1.13.1 | 글로벌페이 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-03-20 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 253 | 6 | 3.3.1.1.13.2 | 조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-03-27 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 254 | 6 | 3.3.1.1.13.3 | 고시환율 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-03 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 255 | 6 | 3.3.1.1.13.4 | 외환시장환율_인터넷환율수신 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-06 | 2015-04-10 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 256 | 6 | 3.3.1.1.13.5 | 맟춤환율통지 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 257 | 6 | 3.3.1.1.13.6 | 환율Ticker | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 258 | 6 | 3.3.1.1.13.7 | 이메일환율수신_무료환율표_외환시장동향 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 259 | 6 | 3.3.1.1.13.8 | 사이버환전 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-29 | 0.01 | 15 |  |  | 0.01 | 0 | 0 |  | 0%
| 260 | 6 | 3.3.1.1.13.9 | 외화기프트서비스 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-25 | 2015-06-12 | 0.01 | 15 |  |  | 0.01 | 0 | 0 |  | 0%
| 261 | 6 | 3.3.1.1.13.10 | 환전클럽_환전정보 나눔광장 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-08 | 2015-06-19 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 262 | 6 | 3.3.1.1.13.11 | 외환매입매도 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-03-27 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 263 | 6 | 3.3.1.1.13.12 | 해외송금_국내즉시송금_외화송금내역 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-10 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 264 | 6 | 3.3.1.1.13.13 | 송금트래킹_송금정보_거래은행지정_수표추심 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 265 | 6 | 3.3.1.1.13.14 | 송금클럽 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-05-15 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 266 | 6 | 3.3.1.1.13.15 | 우대금리외화예금신규 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-12 | 2015-05-18 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 267 | 6 | 3.3.1.1.13.16 | 외화예금상품 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-06-12 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 268 | 6 | 3.3.1.1.13.17 | 외화예금조회_인출_예금해지 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-13 | 2015-04-24 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 269 | 6 | 3.3.1.1.13.18 | 당타행외화계좌이체 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 270 | 6 | 3.3.1.1.13.19 | 글로벌계좌이체 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-22 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 271 | 6 | 3.3.1.1.13.20 | 우대서비스 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-06 | 2015-05-01 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 272 | 6 | 3.3.1.1.13.21 | 글로벌뱅킹 조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 273 | 6 | 3.3.1.1.13.22 | 글로벌뱅킹 즉시_예약 자동이체 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-29 | 0.01 | 15 |  |  | 0.01 | 0 | 0 |  | 0%
| 274 | 6 | 3.3.1.1.13.23 | 글로벌뱅킹 통합_자주입금하는계좌_사전등록거래 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-27 | 2015-06-02 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 275 | 6 | 3.3.1.1.13.24 | 글로벌뱅킹 송금_정보조회_개설결과조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-03 | 2015-06-16 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 276 | 5 | 2.3.1.1.14 | 공인인증센터 |  |  | 0 | 2015-04-06 | 2015-05-15 | 0.03 | 30 |  |  | 0.03 | 0 | 0 |  | 0%
| 277 | 6 | 2.3.1.1.14.1 | 메인_발급_타기관 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | -1 | 2015-04-06 | 2015-04-17 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 278 | 6 | 2.3.1.1.14.2 | 인증서 복사 및 관리 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 279 | 6 | 2.3.1.1.14.3 | 인증서 갱신_폐기_조회_수수료 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-05-04 | 2015-05-15 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 280 | 5 | 2.3.1.1.15 | 메인 |  |  | 0 | 2015-05-25 | 2015-06-19 | 0.02 | 20 |  |  | 0.02 | 0 | 0 |  | 0%
| 281 | 6 | 2.3.1.1.15.1 | 로그인 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-05-25 | 2015-06-12 | 0.01 | 15 |  |  | 0.01 | 0 | 0 |  | 0%
| 282 | 6 | 2.3.1.1.15.2 | 빠른서비스 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-06-08 | 2015-06-19 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 283 | 5 | 2.3.1.1.16 | 상품처리 대응개발 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-22 | 2015-08-14 | 0 | 40 |  |  | 0 | 0 | 0 |  | 0%
| 284 | 3 | 2.3.2 | 단위테스트 수행 |  |  | 0 | 2015-03-23 | 2015-06-26 | 0.835 | 70 |  |  | 0.835 | 0 | 0 |  | 0%
| 285 | 4 | 2.3.2.1 | 단위테스트 수행 |  |  | 0 | 2015-03-23 | 2015-06-26 | 0.835 | 70 |  |  | 0.835 | 0 | 0 |  | 0%
| 286 | 5 | 2.3.2.1.1 | MyHana |  |  | 0 | 2015-03-23 | 2015-06-12 | 0.09 | 60 |  |  | 0.09 | 0 | 0 |  | 0%
| 287 | 6 | 2.3.2.1.1.1 | 메인_분실신고 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-03-27 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 288 | 6 | 2.3.2.1.1.2 | 개인정보관리 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-03 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 289 | 6 | 2.3.2.1.1.3 | 뱅킹정보관리 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-06 | 2015-04-17 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 290 | 6 | 2.3.2.1.1.4 | 통지서비스 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 291 | 6 | 2.3.2.1.1.5 | 자산관리_소득_개인신용정보 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-01 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 292 | 6 | 2.3.2.1.1.6 | 보안서비스 신청/관리 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 293 | 6 | 2.3.2.1.1.7 | 보안서비스_추천 e-Banking | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 294 | 6 | 2.3.2.1.1.8 | 보안서비스_전자금융보안 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-19 | 2015-05-25 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 295 | 6 | 2.3.2.1.1.9 | 보안서비스_마이금융정보 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-26 | 2015-06-12 | 0.01 | 14 |  |  | 0.01 | 0 | 0 |  | 0%
| 296 | 5 | 2.3.2.1.2 | 부가서비스 |  |  | 0 | 2015-05-11 | 2015-06-15 | 0.015 | 26 |  |  | 0.015 | 0 | 0 |  | 0%
| 297 | 6 | 2.3.2.1.2.1 | 금융IC카드 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-06-05 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 298 | 6 | 2.3.2.1.2.2 | 국민주택채권_전자공무원_학생증 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-09 | 2015-06-15 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 299 | 5 | 2.3.2.1.3 | 보험/공제 |  |  | 0 | 2015-06-08 | 2015-06-19 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 300 | 6 | 2.3.2.1.3.1 | 가입내역조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-08 | 2015-06-19 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 301 | 5 | 2.3.2.1.4 | 예금신탁 |  |  | 0 | 2015-03-23 | 2015-05-29 | 0.05 | 50 |  |  | 0.05 | 0 | 0 |  | 0%
| 302 | 6 | 2.3.2.1.4.1 | 신규가입 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-04-17 | 0.02 | 20 |  |  | 0.02 | 0 | 0 |  | 0%
| 303 | 6 | 2.3.2.1.4.2 | 예금가입/해지_연금저축신탁가입/해지 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 304 | 6 | 2.3.2.1.4.3 | 특정금전신탁_IRP_금리변경통지 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-29 | 0.02 | 20 |  |  | 0.02 | 0 | 0 |  | 0%
| 305 | 5 | 2.3.2.1.5 | 대출 |  |  | 0 | 2015-05-11 | 2015-06-26 | 0.05 | 35 |  |  | 0.05 | 0 | 0 |  | 0%
| 306 | 6 | 2.3.2.1.5.1 | 대출조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 307 | 6 | 2.3.2.1.5.2 | 대출상환/이자납입_예담대 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-22 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 308 | 6 | 2.3.2.1.5.3 | 대출신청 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-26 | 2015-06-22 | 0.02 | 20 |  |  | 0.02 | 0 | 0 |  | 0%
| 309 | 6 | 2.3.2.1.5.4 | 원클릭_보금자리_디딤돌_신용대출 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-22 | 2015-06-26 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 310 | 5 | 2.3.2.1.6 | 펀드 |  |  | 0 | 2015-05-11 | 2015-06-22 | 0.06 | 31 |  |  | 0.06 | 0 | 0 |  | 0%
| 311 | 6 | 2.3.2.1.6.1 | 신규가입 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-22 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 312 | 6 | 2.3.2.1.6.2 | 투자의 달인_판드환매 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-25 | 2015-05-29 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 313 | 6 | 2.3.2.1.6.3 | 펀드조회/추가입금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-02 | 2015-06-08 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 314 | 6 | 2.3.2.1.6.4 | 펀드서비스 신청/해제_마이펀드 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-09 | 2015-06-22 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 315 | 5 | 2.3.2.1.7 | 이체 |  |  | 0 | 2015-03-23 | 2015-05-15 | 0.08 | 40 |  |  | 0.08 | 0 | 0 |  | 0%
| 316 | 6 | 2.3.2.1.7.1 | KEB 시소 펀드적금이체 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-04-03 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 317 | 6 | 2.3.2.1.7.2 | 자금_예약_자동이체 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-06 | 2015-04-17 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 318 | 6 | 2.3.2.1.7.3 | 중도금_파일_퇴직연금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 319 | 6 | 2.3.2.1.7.4 | 이체내역조회_수수료_인터넷청약_경매 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 320 | 6 | 2.3.2.1.7.5 | 기부 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 321 | 5 | 2.3.2.1.8 | 조회 |  |  | 0 | 2015-05-19 | 2015-06-16 | 0.04 | 21 |  |  | 0.04 | 0 | 0 |  | 0%
| 322 | 6 | 2.3.2.1.8.1 | 계좌조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-19 | 2015-05-25 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 323 | 6 | 2.3.2.1.8.2 | 예금/신탁기타조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-26 | 2015-06-05 | 0.01 | 9 |  |  | 0.01 | 0 | 0 |  | 0%
| 324 | 6 | 2.3.2.1.8.3 | 펀드조회_대출_보험_수표조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-03 | 2015-06-09 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 325 | 6 | 2.3.2.1.8.4 | 모임통장_해외지점계좌조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-10 | 2015-06-16 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 326 | 5 | 2.3.2.1.9 | 카드 |  |  | 0 | 2015-06-08 | 2015-06-26 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 327 | 6 | 2.3.2.1.9.1 | my카드_조회_결제_현금서비스 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-08 | 2015-06-12 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 328 | 6 | 2.3.2.1.9.2 | 카드론_포인트/마일리지 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-15 | 2015-06-19 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 329 | 6 | 2.3.2.1.9.3 | 이용한도_M/S카드_현금카드결제 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-22 | 2015-06-26 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 330 | 5 | 2.3.2.1.10 | 공과금 |  |  | 0 | 2015-03-23 | 2015-05-29 | 0.1 | 50 |  |  | 0.1 | 0 | 0 |  | 0%
| 331 | 6 | 2.3.2.1.10.1 | MY공과금_지로_지방세 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-04-03 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 332 | 6 | 2.3.2.1.10.2 | 국세 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-06 | 2015-04-17 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 333 | 6 | 2.3.2.1.10.3 | 관세_기타세입금_생활요금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 334 | 6 | 2.3.2.1.10.4 | 아파트관리비 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 335 | 6 | 2.3.2.1.10.5 | 범칙금/벌과금_연금/보험금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 336 | 6 | 2.3.2.1.10.6 | 법원공과금_기금_대학등록금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-29 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 337 | 5 | 2.3.2.1.11 | 기업결제 |  |  | 0 | 2015-04-20 | 2015-06-05 | 0.03 | 35 |  |  | 0.03 | 0 | 0 |  | 0%
| 338 | 6 | 2.3.2.1.11.1 | 판매기업 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 339 | 6 | 2.3.2.1.11.2 | 구매기업 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 340 | 6 | 2.3.2.1.11.3 | 질권설정 메뉴(4개) | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-06-05 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 341 | 5 | 2.3.2.1.12 | 외환 |  |  | 0 | 2015-03-23 | 2015-06-26 | 0.2 | 70 |  |  | 0.2 | 0 | 0 |  | 0%
| 342 | 6 | 3.3.2.1.12.1 | 글로벌페이 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-03-27 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 343 | 6 | 3.3.2.1.12.2 | 조회 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-03 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 344 | 6 | 3.3.2.1.12.3 | 고시환율 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-06 | 2015-04-10 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 345 | 6 | 3.3.2.1.12.4 | 외환시장환율_인터넷환율수신 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 346 | 6 | 3.3.2.1.12.5 | 맟춤환율통지 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 347 | 6 | 3.3.2.1.12.6 | 환율Ticker | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-01 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 348 | 6 | 3.3.2.1.12.7 | 이메일환율수신_무료환율표_외환시장동향 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-15 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 349 | 6 | 3.3.2.1.12.8 | 사이버환전 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-06-05 | 0.01 | 15 |  |  | 0.01 | 0 | 0 |  | 0%
| 350 | 6 | 3.3.2.1.12.9 | 외화기프트서비스 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-03 | 2015-06-16 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 351 | 6 | 3.3.2.1.12.10 | 환전클럽_환전정보 나눔광장 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-15 | 2015-06-26 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 352 | 6 | 3.3.2.1.12.11 | 회환매입매도 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-04-03 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 353 | 6 | 3.3.2.1.12.12 | 해외송금_국내즉시송금_외화송금내역 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-06 | 2015-04-17 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 354 | 6 | 3.3.2.1.12.13 | 송금트래킹_송금정보_거래은행지정_수표추심 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 355 | 6 | 3.3.2.1.12.14 | 송금클럽 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-15 | 0.01 | 15 |  |  | 0.01 | 0 | 0 |  | 0%
| 356 | 6 | 3.3.2.1.12.15 | 우대금리외화예금신규 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-19 | 2015-05-25 | 0.005 | 5 |  |  | 0.005 | 0 | 0 |  | 0%
| 357 | 6 | 3.3.2.1.12.16 | 외화예금상품 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-26 | 2015-06-19 | 0.01 | 19 |  |  | 0.01 | 0 | 0 |  | 0%
| 358 | 6 | 3.3.2.1.12.17 | 외화예금조회_인출_예금해지 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 359 | 6 | 3.3.2.1.12.18 | 당타행외화계좌이체 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-15 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 360 | 6 | 3.3.2.1.12.19 | 글로벌계좌이체 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-06-05 | 0.01 | 15 |  |  | 0.01 | 0 | 0 |  | 0%
| 361 | 6 | 3.3.2.1.12.20 | 우대서비스 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-13 | 2015-05-08 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 362 | 6 | 3.3.2.1.12.21 | 글로벌뱅킹 조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-22 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 363 | 6 | 3.3.2.1.12.22 | 글로벌뱅킹 즉시_예약 자동이체 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-06-05 | 0.01 | 15 |  |  | 0.01 | 0 | 0 |  | 0%
| 364 | 6 | 3.3.2.1.12.23 | 글로벌뱅킹 통합_자주입금하는계좌_사전등록거래 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-01 | 2015-06-12 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 365 | 6 | 3.3.2.1.12.24 | 글로벌뱅킹 송금_정보조회_개설결과조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-15 | 2015-06-26 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 366 | 5 | 2.3.2.1.13 | 공인인증센터 |  |  | 0 | 2015-04-13 | 2015-05-22 | 0.06 | 30 |  |  | 0.06 | 0 | 0 |  | 0%
| 367 | 6 | 2.3.2.1.13.1 | 메인_발급_타기관 | 단위테스트 결과서 | 업무공통,BT개발자 | 0 | 2015-04-13 | 2015-04-24 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 368 | 6 | 2.3.2.1.13.2 | 인증서 복사 및 관리 | 단위테스트 결과서 | 업무공통,BT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 369 | 6 | 2.3.2.1.13.3 | 인증서 갱신_폐기_조회_수수료 | 단위테스트 결과서 | 업무공통,BT개발자 | 0 | 2015-05-11 | 2015-05-22 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 370 | 5 | 2.3.1.1.14 | 메인 |  |  | 0 | 2015-06-08 | 2015-06-26 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 371 | 6 | 2.3.1.1.14.1 | 로그인 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-06-08 | 2015-06-26 | 0.01 | 15 |  |  | 0.01 | 0 | 0 |  | 0%
| 372 | 6 | 2.3.1.1.14.2 | 빠른서비스 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-06-15 | 2015-06-26 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 373 | 1 | 3 | 오픈뱅킹 |  |  | 0 | 2015-02-09 | 2015-08-14 | 8 | 135 |  |  | 8 | 0 | 0 |  | 0%
| 374 | 2 | 3.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-03-20 | 1.3 | 30 |  |  | 1.3 | 0 | 0 |  | 0%
| 375 | 3 | 3.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.04 | 15 |  |  | 0.04 | 0 | 0 |  | 0%
| 376 | 4 | 3.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 | 분석/설계자 | -1 | 2015-02-09 | 2015-02-27 | 0.04 | 15 |  |  | 0.04 | 0 | 0 |  | 0%
| 377 | 3 | 3.1.2 | GAP 분석 |  |  | -1 | 2015-02-09 | 2015-03-13 | 1.12 | 25 |  |  | 1.12 | 0 | 0 |  | 0%
| 378 | 4 | 3.1.2.1 | 메뉴 GAP분석 |  |  | -1 | 2015-02-09 | 2015-03-06 | 0.47 | 20 |  |  | 0.47 | 0 | 0 |  | 0%
| 379 | 5 | 3.1.2.1.1 | 마이하나 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-09 | 2015-02-17 | 0.02 | 7 |  |  | 0.02 | 0 | 0 |  | 0%
| 380 | 5 | 3.1.2.1.2 | 부가서비스 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-16 | 2015-02-27 | 0.04 | 10 |  |  | 0.04 | 0 | 0 |  | 0%
| 381 | 5 | 3.1.2.1.3 | 보험공제 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02 | 0 | 0 |  | 0%
| 382 | 5 | 3.1.2.1.4 | 예금신탁 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-09 | 2015-02-17 | 0.02 | 7 |  |  | 0.02 | 0 | 0 |  | 0%
| 383 | 5 | 3.1.2.1.5 | 대출 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-16 | 2015-02-27 | 0.04 | 10 |  |  | 0.04 | 0 | 0 |  | 0%
| 384 | 5 | 3.1.2.1.6 | 펀드 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02 | 0 | 0 |  | 0%
| 385 | 5 | 3.1.2.1.7 | 조회 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-09 | 2015-02-17 | 0.02 | 7 |  |  | 0.02 | 0 | 0 |  | 0%
| 386 | 5 | 3.1.2.1.8 | 이체 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-16 | 2015-03-06 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 387 | 5 | 3.1.2.1.9 | 카드 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-23 | 2015-03-06 | 0.04 | 10 |  |  | 0.04 | 0 | 0 |  | 0%
| 388 | 5 | 3.1.2.1.10 | 공과금 | 현행 시스템 분석서 | 분석/설계자4 | -1 | 2015-02-09 | 2015-02-27 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 389 | 5 | 3.1.2.1.11 | 외환 | 현행 시스템 분석서 | 분석/설계자5 | -1 | 2015-02-09 | 2015-02-27 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 390 | 5 | 3.1.2.1.12 | 공인인증센터 | 현행 시스템 분석서 | 분석/설계자6 | -1 | 2015-02-16 | 2015-03-06 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 391 | 5 | 3.1.2.1.13 | 보안매체 | 현행 시스템 분석서 | 분석/설계자6 | -1 | 2015-02-16 | 2015-03-06 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 392 | 5 | 3.1.2.1.14 | 메인 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-23 | 2015-03-06 | 0.06 | 10 |  |  | 0.06 | 0 | 0 |  | 0%
| 393 | 4 | 3.1.2.2 | 전문 GAP분석 |  |  | -1 | 2015-02-09 | 2015-03-13 | 0.61 | 25 |  |  | 0.61 | 0 | 0 |  | 0%
| 394 | 5 | 3.1.2.2.1 | 마이하나 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-09 | 2015-02-27 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 395 | 5 | 3.1.2.2.2 | 부가서비스 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-16 | 2015-03-06 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 396 | 5 | 3.1.2.2.3 | 보험공제 | 현행 시스템 분석서 | 분석/설계자1 | -1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02 | 0 | 0 |  | 0%
| 397 | 5 | 3.1.2.2.4 | 예금신탁 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-09 | 2015-02-27 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 398 | 5 | 3.1.2.2.5 | 대출 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-16 | 2015-03-06 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 399 | 5 | 3.1.2.2.6 | 펀드 | 현행 시스템 분석서 | 분석/설계자2 | -1 | 2015-02-23 | 2015-03-06 | 0.04 | 10 |  |  | 0.04 | 0 | 0 |  | 0%
| 400 | 5 | 3.1.2.2.7 | 조회 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-09 | 2015-02-27 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 401 | 5 | 3.1.2.2.8 | 이체 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-16 | 2015-03-13 | 0.05 | 20 |  |  | 0.05 | 0 | 0 |  | 0%
| 402 | 5 | 3.1.2.2.9 | 카드 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-23 | 2015-03-13 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 403 | 5 | 3.1.2.2.10 | 공과금 | 현행 시스템 분석서 | 분석/설계자4 | -1 | 2015-02-09 | 2015-03-06 | 0.05 | 20 |  |  | 0.05 | 0 | 0 |  | 0%
| 404 | 5 | 3.1.2.2.12 | 외환 | 현행 시스템 분석서 | 분석/설계자5 | -1 | 2015-02-09 | 2015-03-13 | 0.05 | 25 |  |  | 0.05 | 0 | 0 |  | 0%
| 405 | 5 | 3.1.2.2.13 | 공인인증센터 | 현행 시스템 분석서 | 분석/설계자6 | -1 | 2015-02-09 | 2015-03-06 | 0.05 | 20 |  |  | 0.05 | 0 | 0 |  | 0%
| 406 | 5 | 3.1.2.2.14 | 보안매체 | 현행 시스템 분석서 | 분석/설계자6 | -1 | 2015-02-16 | 2015-03-13 | 0.05 | 20 |  |  | 0.05 | 0 | 0 |  | 0%
| 407 | 5 | 3.1.2.2.15 | 메인 | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-23 | 2015-03-13 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 408 | 4 | 3.1.2.3 | 테이블/속성 GAP분석 | 현행 시스템 분석서 | 분석/설계자 | -1 | 2015-02-11 | 2015-02-27 | 0.04 | 13 |  |  | 0.04 | 0 | 0 |  | 0%
| 409 | 3 | 3.1.3 | 통합업무확정 |  |  | -1 | 2015-02-16 | 2015-02-27 | 0 | 10 |  |  | 0 | 0 | 0 |  | 0%
| 410 | 4 | 3.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 | 기획자 | -1 | 2015-02-16 | 2015-02-27 | 0 | 10 |  |  | 0 | 0 | 0 |  | 0%
| 411 | 3 | 3.1.4 | 통합요건정의 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.08 | 10 |  |  | 0.08 | 0 | 0 |  | 0%
| 412 | 4 | 3.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 업무총괄 | -1 | 2015-03-02 | 2015-03-13 | 0.08 | 10 |  |  | 0.08 | 0 | 0 |  | 0%
| 413 | 3 | 3.1.5 | 논리모델구축 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 414 | 4 | 3.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 | BT분석/설계자 | -1 | 2015-03-16 | 2015-03-20 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 415 | 2 | 3.2 | 설계 |  |  | 0 | 2015-03-02 | 2015-04-30 | 1.3 | 44 |  |  | 1.3 | 0 | 0 |  | 0%
| 416 | 3 | 3.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-02 | 2015-04-17 | 1 | 35 |  |  | 1 | 0 | 0 |  | 0%
| 417 | 4 | 3.2.1.1 | 화면설계 |  |  | -1 | 2015-03-02 | 2015-04-19 | 0 | 35 |  |  | 0 | 0 | 0 |  | 0%
| 418 | 4 | 3.2.1.2 | 프로그램 설계 |  |  | 0 | 2015-03-02 | 2015-04-30 | 1 | 44 |  |  | 1 | 0 | 0 |  | 0%
| 419 | 5 | 3.2.1.2.1 | MyHana | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-02 | 2015-04-03 | 0.08 | 25 |  |  | 0.08 | 0 | 0 |  | 0%
| 420 | 5 | 3.2.1.2.2 | 부가서비스 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-03 | 0.04 | 15 |  |  | 0.04 | 0 | 0 |  | 0%
| 421 | 5 | 3.2.1.2.3 | 보험/공제 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-04-06 | 2015-04-17 | 0.04 | 10 |  |  | 0.04 | 0 | 0 |  | 0%
| 422 | 5 | 3.2.1.2.4 | 예금신탁(신규외) | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 0 | 0 |  | 0%
| 423 | 5 | 3.2.1.2.5 | 예금신탁(신규) | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-17 | 0.08 | 25 |  |  | 0.08 | 0 | 0 |  | 0%
| 424 | 5 | 3.2.1.2.6 | 대출 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.08 | 20 |  |  | 0.08 | 0 | 0 |  | 0%
| 425 | 5 | 3.2.1.2.7 | 펀드 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-23 | 2015-04-17 | 0.08 | 20 |  |  | 0.08 | 0 | 0 |  | 0%
| 426 | 5 | 3.2.1.2.8 | 이체 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-03 | 0.08 | 15 |  |  | 0.08 | 0 | 0 |  | 0%
| 427 | 5 | 3.2.1.2.9 | 조회 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.08 | 20 |  |  | 0.08 | 0 | 0 |  | 0%
| 428 | 5 | 3.2.1.2.10 | 카드 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-23 | 2015-04-17 | 0.08 | 20 |  |  | 0.08 | 0 | 0 |  | 0%
| 429 | 5 | 3.2.1.2.11 | 공과금 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-09 | 2015-04-10 | 0.08 | 25 |  |  | 0.08 | 0 | 0 |  | 0%
| 430 | 5 | 3.2.1.2.12 | 외환 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-17 | 0.08 | 25 |  |  | 0.08 | 0 | 0 |  | 0%
| 431 | 5 | 3.2.1.2.13 | 공인인증센터 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-17 | 0.08 | 25 |  |  | 0.08 | 0 | 0 |  | 0%
| 432 | 5 | 3.2.1.2.14 | 메인 | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-30 | 2015-04-17 | 0.04 | 15 |  |  | 0.04 | 0 | 0 |  | 0%
| 433 | 5 | 3.2.1.2.15 | 추가 변경/신규요건 설계 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | 0 | 2015-04-20 | 2015-04-30 | 0.03 | 9 |  |  | 0.03 | 0 | 0 |  | 0%
| 434 | 3 | 3.2.2 | 통합전문설계 |  |  | -1 | 2015-03-23 | 2015-04-17 | 0.3 | 20 |  |  | 0.3 | 0 | 0 |  | 0%
| 435 | 4 | 3.2.2.1 | 전문매핑 |  |  | -1 | 2015-03-23 | 2015-04-17 | 0.3 | 20 |  |  | 0.3 | 0 | 0 |  | 0%
| 436 | 5 | 3.2.2.1.1 | 전문목록작성 | 전문목록 | BT분석/설계자 | -1 | 2015-03-23 | 2015-03-27 | 0.1 | 5 |  |  | 0.1 | 0 | 0 |  | 0%
| 437 | 5 | 3.2.2.1.2 | 전문매핑정의서작성 | 전문매핑정의서 | BT분석/설계자 | -1 | 2015-03-30 | 2015-04-17 | 0.2 | 15 |  |  | 0.2 | 0 | 0 |  | 0%
| 438 | 2 | 3.3 | 구현 |  |  | 0 | 2015-02-09 | 2015-08-14 | 5.4 | 135 |  |  | 5.4 | 0 | 0 |  | 0%
| 439 | 3 | 3.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-08-14 | 0.77 | 110 |  |  | 0.77 | 0 | 0 |  | 0%
| 440 | 4 | 3.3.1.1 | 온라인 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-08-14 | 0.77 | 110 |  |  | 0.77 | 0 | 0 |  | 0%
| 441 | 5 | 3.3.1.1.1 | 보안취약성점검 및 보완 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-04-03 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 442 | 5 | 3.3.1.1.2 | MyHana |  |  | 0 | 2015-03-16 | 2015-05-29 | 0.09 | 55 |  |  | 0.09 | 0 | 0 |  | 0%
| 443 | 6 | 3.3.1.1.2.1 | 메인_분실신고 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 444 | 6 | 3.3.1.1.2.2 | 개인정보관리 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-03-27 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 445 | 6 | 3.3.1.1.2.3 | 뱅킹정보관리 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-10 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 446 | 6 | 3.3.1.1.2.4 | 통지서비스 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 447 | 6 | 3.3.1.1.2.5 | 자산관리_소득_개인신용정보 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 448 | 6 | 3.3.1.1.2.6 | 보안서비스 신청/관리 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-01 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 449 | 6 | 3.3.1.1.2.7 | 보안서비스_추천 e-Banking | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 450 | 6 | 3.3.1.1.2.8 | 보안서비스_전자금융보안 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 451 | 6 | 3.3.1.1.2.9 | 보안서비스_마이금융정보 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-29 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 452 | 5 | 3.3.1.1.3 | 부가서비스 |  |  | 0 | 2015-05-04 | 2015-06-05 | 0.02 | 25 |  |  | 0.02 | 0 | 0 |  | 0%
| 453 | 6 | 3.3.1.1.3.1 | 금융IC카드 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-29 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 454 | 6 | 3.3.1.1.3.2 | 국민주택채권_전자공무원_학생증 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-01 | 2015-06-05 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 455 | 5 | 3.3.1.1.4 | 보험/공제 |  |  | 0 | 2015-06-01 | 2015-06-12 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 456 | 6 | 3.3.1.1.4.1 | 가입내역조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-01 | 2015-06-12 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 457 | 5 | 3.3.1.1.5 | 예금신탁 |  |  | 0 | 2015-03-16 | 2015-05-22 | 0.05 | 50 |  |  | 0.05 | 0 | 0 |  | 0%
| 458 | 6 | 3.3.1.1.5.1 | 신규가입 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-04-10 | 0.02 | 20 |  |  | 0.02 | 0 | 0 |  | 0%
| 459 | 6 | 3.3.1.1.5.2 | 예금가입/해지_연금저축신탁가입/해지 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-13 | 2015-04-24 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 460 | 6 | 3.3.1.1.5.3 | 특정금전신탁_IRP_금리변경통지 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-22 | 0.02 | 20 |  |  | 0.02 | 0 | 0 |  | 0%
| 461 | 5 | 3.3.1.1.6 | 대출 |  |  | 0 | 2015-05-04 | 2015-06-19 | 0.05 | 35 |  |  | 0.05 | 0 | 0 |  | 0%
| 462 | 6 | 3.3.1.1.6.1 | 대출조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 463 | 6 | 3.3.1.1.6.2 | 대출상환/이자납입_예담대 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 464 | 6 | 3.3.1.1.6.3 | 대출신청 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-06-12 | 0.02 | 20 |  |  | 0.02 | 0 | 0 |  | 0%
| 465 | 6 | 3.3.1.1.6.4 | 원클릭_보금자리_디딤돌_신용대출 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-15 | 2015-06-19 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 466 | 5 | 3.3.1.1.7 | 펀드 |  |  | 0 | 2015-05-04 | 2015-06-15 | 0.06 | 31 |  |  | 0.06 | 0 | 0 |  | 0%
| 467 | 6 | 3.3.1.1.7.1 | 신규가입 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-15 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 468 | 6 | 3.3.1.1.7.2 | 투자의 달인_판드환매 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-22 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 469 | 6 | 3.3.1.1.7.3 | 펀드조회/추가입금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-26 | 2015-06-01 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 470 | 6 | 3.3.1.1.7.4 | 펀드서비스 신청/해제_마이펀드 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-02 | 2015-06-15 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 471 | 5 | 3.3.1.1.8 | 이체 |  |  | 0 | 2015-03-16 | 2015-05-15 | 0.09 | 45 |  |  | 0.09 | 0 | 0 |  | 0%
| 472 | 6 | 3.3.1.1.8.1 | KEB 시소 펀드적금이체 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-03-27 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 473 | 6 | 3.3.1.1.8.2 | 자금_예약_자동이체 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-10 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 474 | 6 | 3.3.1.1.8.3 | 중도금_파일_퇴직연금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 475 | 6 | 3.3.1.1.8.4 | 이체내역조회_수수료_인터넷청약_경매 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 476 | 6 | 3.3.1.1.8.5 | 기부 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-15 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 477 | 5 | 3.3.1.1.9 | 조회 |  |  | 0 | 2015-05-11 | 2015-06-09 | 0.04 | 22 |  |  | 0.04 | 0 | 0 |  | 0%
| 478 | 6 | 3.3.1.1.9.1 | 계좌조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 479 | 6 | 3.3.1.1.9.2 | 예금/신탁기타조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-22 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 480 | 6 | 3.3.1.1.9.3 | 펀드조회_대출_보험_수표조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-27 | 2015-06-02 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 481 | 6 | 3.3.1.1.9.4 | 모임통장_해외지점계좌조회 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-03 | 2015-06-09 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 482 | 5 | 3.3.1.1.10 | 카드 |  |  | 0 | 2015-06-01 | 2015-06-19 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 483 | 6 | 3.3.1.1.10.1 | my카드_조회_결제_현금서비스 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-01 | 2015-06-05 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 484 | 6 | 3.3.1.1.10.2 | 카드론_포인트/마일리지 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-08 | 2015-06-12 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 485 | 6 | 3.3.1.1.10.3 | 이용한도_M/S카드_현금카드결제 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-15 | 2015-06-19 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 486 | 5 | 3.3.1.1.11 | 공과금 |  |  | 0 | 2015-03-16 | 2015-05-22 | 0.1 | 50 |  |  | 0.1 | 0 | 0 |  | 0%
| 487 | 6 | 3.3.1.1.11.1 | MY공과금_지로_지방세 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-03-27 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 488 | 6 | 3.3.1.1.11.2 | 국세 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-10 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 489 | 6 | 3.3.1.1.11.3 | 관세_기타세입금_생활요금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 490 | 6 | 3.3.1.1.11.4 | 아파트관리비 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 491 | 6 | 3.3.1.1.11.5 | 범칙금/벌과금_연금/보험금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 492 | 6 | 3.3.1.1.11.6 | 법원공과금_기금_대학등록금 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-22 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 493 | 5 | 3.3.1.1.12 | 외환 |  |  | 0 | 2015-03-16 | 2015-05-29 | 0.12 | 55 |  |  | 0.12 | 0 | 0 |  | 0%
| 494 | 6 | 3.3.1.1.12.1 | 글로벌페이 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 495 | 6 | 3.3.1.1.12.2 | 환율 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-10 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 496 | 6 | 3.3.1.1.12.3 | 사이버환전 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-29 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 497 | 6 | 3.3.1.1.12.4 | 외환매입매도 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-04-03 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 498 | 6 | 3.3.1.1.12.5 | 해외송금_국내송금_외화송금내역 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-10 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 499 | 6 | 3.3.1.1.12.6 | 외국환거래은행지정_외화수표추심결과 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 500 | 6 | 3.3.1.1.12.7 | 외화이체 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 501 | 5 | 3.3.1.1.13 | 공인인증센터 |  |  | 0 | 2015-04-06 | 2015-05-15 | 0.06 | 30 |  |  | 0.06 | 0 | 0 |  | 0%
| 502 | 6 | 3.3.1.1.13.1 | 메인_발급_타기관 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | -1 | 2015-04-06 | 2015-04-17 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 503 | 6 | 3.3.1.1.13.2 | 인증서 복사 및 관리 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 504 | 6 | 3.3.1.1.13.3 | 인증서 갱신_폐기_조회_수수료 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-05-04 | 2015-05-15 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 505 | 5 | 2.3.1.1.14 | 메인 |  |  | 0 | 2015-05-25 | 2015-08-14 | 0.03 | 60 |  |  | 0.03 | 0 | 0 |  | 0%
| 506 | 6 | 2.3.1.1.14.1 | 로그인 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-05-25 | 2015-06-12 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 507 | 6 | 2.3.1.1.14.2 | 빠른서비스 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-06-08 | 2015-06-19 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 508 | 5 | 3.3.1.1.15 | 상품처리 대응개발 | 온라인 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-06-22 | 2015-08-14 | 0 | 40 |  |  | 0 | 0 | 0 |  | 0%
| 509 | 3 | 3.3.2 | 단위테스트 수행 |  |  | 0 | 2015-02-09 | 2015-07-17 | 4.63 | 115 |  |  | 4.63 | 0 | 0 |  | 0%
| 510 | 4 | 3.3.2.1 | 단위테스트 수행 |  |  | 0 | 2015-02-09 | 2015-07-17 | 4.63 | 115 |  |  | 4.63 | 0 | 0 |  | 0%
| 511 | 5 | 3.3.2.1.1 | MyHana |  |  | 0 | 2015-03-23 | 2015-06-12 | 0.09 | 60 |  |  | 0.09 | 0 | 0 |  | 0%
| 512 | 6 | 3.3.2.1.1.1 | 메인_분실신고 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-03-27 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 513 | 6 | 3.3.2.1.1.2 | 개인정보관리 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-30 | 2015-04-03 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 514 | 6 | 3.3.2.1.1.3 | 뱅킹정보관리 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-06 | 2015-04-17 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 515 | 6 | 3.3.2.1.1.4 | 통지서비스 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 516 | 6 | 3.3.2.1.1.5 | 자산관리_소득_개인신용정보 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-01 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 517 | 6 | 3.3.2.1.1.6 | 보안서비스 신청/관리 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 518 | 6 | 3.3.2.1.1.7 | 보안서비스_추천 e-Banking | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 519 | 6 | 3.3.2.1.1.8 | 보안서비스_전자금융보안 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-19 | 2015-05-25 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 520 | 6 | 3.3.2.1.1.9 | 보안서비스_마이금융정보 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-26 | 2015-06-12 | 0.01 | 14 |  |  | 0.01 | 0 | 0 |  | 0%
| 521 | 5 | 3.3.2.1.2 | 부가서비스 |  |  | 0 | 2015-05-11 | 2015-06-15 | 0.02 | 26 |  |  | 0.02 | 0 | 0 |  | 0%
| 522 | 6 | 3.3.2.1.2.1 | 금융IC카드 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-06-05 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 523 | 6 | 3.3.2.1.2.2 | 국민주택채권_전자공무원_학생증 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-09 | 2015-06-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 524 | 5 | 3.3.2.1.3 | 보험/공제 |  |  | 0 | 2015-06-08 | 2015-06-19 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 525 | 6 | 3.3.2.1.3.1 | 가입내역조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-08 | 2015-06-19 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 526 | 5 | 3.3.2.1.4 | 예금신탁 |  |  | 0 | 2015-03-23 | 2015-05-29 | 0.04 | 50 |  |  | 0.04 | 0 | 0 |  | 0%
| 527 | 6 | 3.3.2.1.4.1 | 신규가입 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-04-17 | 0.02 | 20 |  |  | 0.02 | 0 | 0 |  | 0%
| 528 | 6 | 3.3.2.1.4.2 | 예금가입/해지_연금저축신탁가입/해지 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-05-01 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 529 | 6 | 3.3.2.1.4.3 | 특정금전신탁_IRP_금리변경통지 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-29 | 0.01 | 20 |  |  | 0.01 | 0 | 0 |  | 0%
| 530 | 5 | 3.3.2.1.5 | 대출 |  |  | 0 | 2015-05-11 | 2015-06-26 | 0.05 | 35 |  |  | 0.05 | 0 | 0 |  | 0%
| 531 | 6 | 3.3.2.1.5.1 | 대출조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 532 | 6 | 3.3.2.1.5.2 | 대출상환/이자납입_예담대 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-22 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 533 | 6 | 3.3.2.1.5.3 | 대출신청 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-26 | 2015-06-22 | 0.02 | 20 |  |  | 0.02 | 0 | 0 |  | 0%
| 534 | 6 | 3.3.2.1.5.4 | 원클릭_보금자리_디딤돌_신용대출 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-22 | 2015-06-26 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 535 | 5 | 3.3.2.1.6 | 펀드 |  |  | 0 | 2015-05-11 | 2015-06-22 | 0.04 | 31 |  |  | 0.04 | 0 | 0 |  | 0%
| 536 | 6 | 3.3.2.1.6.1 | 신규가입 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-22 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 537 | 6 | 3.3.2.1.6.2 | 투자의 달인_판드환매 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-25 | 2015-05-29 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 538 | 6 | 3.3.2.1.6.3 | 펀드조회/추가입금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-02 | 2015-06-08 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 539 | 6 | 3.3.2.1.6.4 | 펀드서비스 신청/해제_마이펀드 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-09 | 2015-06-22 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 540 | 5 | 3.3.2.1.7 | 이체 |  |  | 0 | 2015-03-23 | 2015-05-15 | 0.08 | 40 |  |  | 0.08 | 0 | 0 |  | 0%
| 541 | 6 | 3.3.2.1.7.1 | KEB 시소 펀드적금이체 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-04-03 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 542 | 6 | 3.3.2.1.7.2 | 자금_예약_자동이체 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-06 | 2015-04-17 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 543 | 6 | 3.3.2.1.7.3 | 중도금_파일_퇴직연금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 544 | 6 | 3.3.2.1.7.4 | 이체내역조회_수수료_인터넷청약_경매 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 545 | 6 | 3.3.2.1.7.5 | 기부 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 546 | 5 | 3.3.2.1.8 | 조회 |  |  | 0 | 2015-05-19 | 2015-06-16 | 0.04 | 21 |  |  | 0.04 | 0 | 0 |  | 0%
| 547 | 6 | 3.3.2.1.8.1 | 계좌조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-19 | 2015-05-25 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 548 | 6 | 3.3.2.1.8.2 | 예금/신탁기타조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-26 | 2015-06-05 | 0.01 | 9 |  |  | 0.01 | 0 | 0 |  | 0%
| 549 | 6 | 3.3.2.1.8.3 | 펀드조회_대출_보험_수표조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-03 | 2015-06-09 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 550 | 6 | 3.3.2.1.8.4 | 모임통장_해외지점계좌조회 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-10 | 2015-06-16 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 551 | 5 | 3.3.2.1.9 | 카드 |  |  | 0 | 2015-06-08 | 2015-06-26 | 0.03 | 15 |  |  | 0.03 | 0 | 0 |  | 0%
| 552 | 6 | 3.3.2.1.9.1 | my카드_조회_결제_현금서비스 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-08 | 2015-06-12 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 553 | 6 | 3.3.2.1.9.2 | 카드론_포인트/마일리지 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-15 | 2015-06-19 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 554 | 6 | 3.3.2.1.9.3 | 이용한도_M/S카드_현금카드결제 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-22 | 2015-06-26 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 555 | 5 | 3.3.2.1.10 | 공과금 |  |  | 0 | 2015-03-23 | 2015-05-29 | 0.06 | 50 |  |  | 0.06 | 0 | 0 |  | 0%
| 556 | 6 | 3.3.2.1.10.1 | MY공과금_지로_지방세 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-04-03 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 557 | 6 | 3.3.2.1.10.2 | 국세 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-06 | 2015-04-17 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 558 | 6 | 3.3.2.1.10.3 | 관세_기타세입금_생활요금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 559 | 6 | 3.3.2.1.10.4 | 아파트관리비 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 560 | 6 | 3.3.2.1.10.5 | 범칙금/벌과금_연금/보험금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-11 | 2015-05-15 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 561 | 6 | 3.3.2.1.10.6 | 법원공과금_기금_대학등록금 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-05-29 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 562 | 5 | 3.3.2.1.11 | 외환 |  |  | 0 | 2015-03-23 | 2015-06-05 | 0.11 | 55 |  |  | 0.11 | 0 | 0 |  | 0%
| 563 | 6 | 2.3.2.1.11.1 | 글로벌페이 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-03-27 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 564 | 6 | 2.3.2.1.11.2 | 환율 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-04-13 | 2015-04-17 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 565 | 6 | 2.3.2.1.11.3 | 사이버환전 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-18 | 2015-06-05 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 566 | 6 | 2.3.2.1.11.4 | 외환매입매도 | 단위테스트 결과서 | PT개발자,BT개발자 | -1 | 2015-03-23 | 2015-04-10 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 567 | 6 | 2.3.2.1.11.5 | 해외송금_국내송금_외화송금내역 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-06 | 2015-04-24 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 568 | 6 | 2.3.2.1.11.6 | 외국환거래은행지정_외화수표추심결과 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01 | 0 | 0 |  | 0%
| 569 | 6 | 2.3.2.1.11.7 | 외화이체 | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-05-04 | 2015-05-15 | 0.02 | 10 |  |  | 0.02 | 0 | 0 |  | 0%
| 570 | 5 | 3.3.2.1.12 | 공인인증센터 |  |  | 0 | 2015-04-13 | 2015-05-22 | 0.03 | 30 |  |  | 0.03 | 0 | 0 |  | 0%
| 571 | 6 | 3.3.2.1.12.1 | 메인_발급_타기관 | 단위테스트 결과서 | 업무공통,BT개발자 | 0 | 2015-04-13 | 2015-04-24 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 572 | 6 | 3.3.2.1.12.2 | 인증서 복사 및 관리 | 단위테스트 결과서 | 업무공통,BT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 573 | 6 | 3.3.2.1.12.3 | 인증서 갱신_폐기_조회_수수료 | 단위테스트 결과서 | 업무공통,BT개발자 | 0 | 2015-05-11 | 2015-05-22 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 574 | 5 | 2.3.1.1.14 | 메인 |  |  | 0 | 2015-02-09 | 2015-07-17 | 4.03 | 115 |  |  | 4.03 | 0 | 0 |  | 0%
| 575 | 6 | 2.3.1.1.14.1 | 로그인 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-06-08 | 2015-06-26 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 576 | 6 | 2.3.1.1.14.2 | 빠른서비스 | 온라인 프로그램 소스코드 | 업무공통,BT개발자 | 0 | 2015-06-15 | 2015-06-26 | 0.01 | 10 |  |  | 0.01 | 0 | 0 |  | 0%
| 577 | 1 | 4 | 다국어뱅킹 |  |  | 0 | 2015-02-09 | 2015-07-17 | 4 | 115 |  |  | 4 | 0 | 0 | 61.74% | 0%
| 578 | 2 | 4.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-03-06 | 1.3 | 20 |  |  | 1.3 | 0 | 0 | 100% | 0%
| 579 | 3 | 4.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-17 | 0.1 | 7 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 580 | 4 | 4.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 | 분석/설계자 | -1 | 2015-02-09 | 2015-02-17 | 0.1 | 7 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 581 | 3 | 4.1.2 | GAP 분석 |  |  | -1 | 2015-02-16 | 2015-02-20 | 0.3 | 5 |  |  | 0.3 | 0 | 0 | 100% | 0%
| 582 | 4 | 4.1.2.1 | 메뉴 GAP분석 | 현행 시스템 분석서 | 분석/설계자 | -1 | 2015-02-16 | 2015-02-20 | 0.1 | 5 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 583 | 4 | 4.1.2.2 | 전문 GAP분석 | 현행 시스템 분석서 | 분석/설계자 | -1 | 2015-02-16 | 2015-02-20 | 0.1 | 5 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 584 | 4 | 4.1.2.3 | 테이블/속성 GAP분석 | 현행 시스템 분석서 | 분석/설계자 | -1 | 2015-02-16 | 2015-02-20 | 0.1 | 5 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 585 | 3 | 4.1.3 | 통합업무확정 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0 | 5 |  |  | 0 | 0 | 0 | 100% | 0%
| 586 | 4 | 4.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 | 기획자 | -1 | 2015-02-23 | 2015-02-27 | 0 | 5 |  |  | 0 | 0 | 0 | 100% | 0%
| 587 | 3 | 4.1.4 | 통합요건정의 |  |  | -1 | 2015-02-23 | 2015-03-03 | 0.5 | 7 |  |  | 0.5 | 0 | 0 | 100% | 0%
| 588 | 4 | 4.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 업무총괄 | -1 | 2015-02-23 | 2015-03-03 | 0.5 | 7 |  |  | 0.5 | 0 | 0 | 100% | 0%
| 589 | 3 | 4.1.5 | 논리모델구축 |  |  | -1 | 2015-03-02 | 2015-03-06 | 0.4 | 5 |  |  | 0.4 | 0 | 0 | 100% | 0%
| 590 | 4 | 4.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 | BT분석/설계자 | -1 | 2015-03-02 | 2015-03-06 | 0.4 | 5 |  |  | 0.4 | 0 | 0 | 100% | 0%
| 591 | 2 | 4.2 | 설계 |  |  | -1 | 2015-03-02 | 2015-03-27 | 1.3 | 20 |  |  | 1.3 | 0 | 0 | 100% | 0%
| 592 | 3 | 4.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.3 | 10 |  |  | 0.3 | 0 | 0 | 100% | 0%
| 593 | 4 | 4.2.1.1 | 화면설계 | 화면설계서 | 분석/설계자 | -1 | 2015-03-02 | 2015-03-13 | 0 | 10 |  |  | 0 | 0 | 0 | 100% | 0%
| 594 | 4 | 4.2.1.2 | 프로그램 설계 | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-02 | 2015-03-13 | 0.3 | 10 |  |  | 0.3 | 0 | 0 | 100% | 0%
| 595 | 3 | 4.2.2 | 통합전문설계 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.3 | 5 |  |  | 0.3 | 0 | 0 | 100% | 0%
| 596 | 4 | 4.2.2.1 | 전문매핑 | 전문목록 전문매핑정의서 | 분석/설계자 | -1 | 2015-03-16 | 2015-03-20 | 0.3 | 5 |  |  | 0.3 | 0 | 0 | 100% | 0%
| 597 | 3 | 4.2.3 | 배치프로세스 설계 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.1 | 5 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 598 | 4 | 4.2.3.1 | 배치프로그램 설계 | 배치프로세스 정의서 | 분석/설계자 | -1 | 2015-03-16 | 2015-03-20 | 0.1 | 5 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 599 | 3 | 4.2.4 | 파일럿 |  |  | -1 | 2015-03-23 | 2015-03-27 | 0.6 | 5 |  |  | 0.6 | 0 | 0 | 100% | 0%
| 600 | 4 | 4.2.4.1 | 파일럿 설계 | 파일럿계획서 | 분석/설계자 | -1 | 2015-03-23 | 2015-03-24 | 0.3 | 2 |  |  | 0.3 | 0 | 0 | 100% | 0%
| 601 | 4 | 4.2.4.2 | 파일럿 구현 | 다국어 적용 가이드 | 분석/설계/개발자 | -1 | 2015-03-25 | 2015-03-27 | 0.3 | 3 |  |  | 0.3 | 0 | 0 | 100% | 0%
| 602 | 2 | 4.3 | 구현 |  |  | 0 | 2015-03-27 | 2015-07-17 | 1.4 | 81 |  |  | 1.4 | 0 | 0 | 30.86% | 0%
| 603 | 3 | 4.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-27 | 2015-07-17 | 0.93 | 81 |  |  | 0.93 | 0 | 0 | 30.86% | 0%
| 604 | 4 | 4.3.1.1 | 온라인 프로그램 구현 |  |  | 0 | 2015-03-27 | 2015-07-15 | 0.92 | 79 |  |  | 0.92 | 0 | 0 | 31.65% | 0%
| 605 | 5 | 4.3.1.1.1 | 통합로그인 / 보안 프로그램 | 온라인 프로그램 소스코드 | PT개발자 | -1 | 2015-03-27 | 2015-04-08 | 0.05 | 9 |  |  | 0.05 | 0 | 0 | 100% | 0%
| 606 | 5 | 4.3.1.1.2 | 조회 |  |  | 0 | 2015-03-27 | 2015-05-15 | 0.08 | 36 |  |  | 0.08 | 0 | 0 | 69.44% | 0%
| 607 | 6 | 4.3.1.1.2.1 | 계좌현황조회 | 온라인 프로그램 소스코드 | PT개발자 | -1 | 2015-03-27 | 2015-04-03 | 0.02 | 6 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 608 | 6 | 4.3.1.1.2.2 | 거래내역조회 | 온라인 프로그램 소스코드 | PT개발자 | -1 | 2015-04-10 | 2015-04-17 | 0.02 | 6 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 609 | 6 | 4.3.1.1.2.3 | 미거래계좌조회 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-24 | 2015-05-01 | 0.02 | 6 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 610 | 6 | 4.3.1.1.2.4 | 펀드 조회 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-08 | 2015-05-15 | 0.02 | 6 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 611 | 5 | 4.3.1.1.3 | 이체 |  |  | 0 | 2015-03-27 | 2015-06-05 | 0.15 | 51 |  |  | 0.15 | 0 | 0 | 49.02% | 0%
| 612 | 6 | 4.3.1.1.3.1 | 단건이체 | 온라인 프로그램 소스코드 | PT개발자 | -1 | 2015-03-27 | 2015-04-10 | 0.03 | 11 |  |  | 0.03 | 0 | 0 | 100% | 0%
| 613 | 6 | 4.3.1.1.3.2 | 다건이체 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-10 | 2015-04-24 | 0.03 | 11 |  |  | 0.03 | 0 | 0 | 100% | 0%
| 614 | 6 | 4.3.1.1.3.3 | 예약이체 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-24 | 2015-05-08 | 0.03 | 11 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 615 | 6 | 4.3.1.1.3.4 | 자동이체 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-08 | 2015-05-22 | 0.03 | 11 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 616 | 6 | 4.3.1.1.3.5 | 이체결과 조회 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-22 | 2015-06-05 | 0.03 | 11 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 617 | 5 | 4.3.1.1.4 | 예금/해지 |  |  | 0 | 2015-03-27 | 2015-05-22 | 0.09 | 41 |  |  | 0.09 | 0 | 0 | 60.98% | 0%
| 618 | 6 | 4.3.1.1.4.1 | 상품 목록 / 상세 | 온라인 프로그램 소스코드 | PT개발자 | -1 | 2015-03-27 | 2015-04-10 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 619 | 6 | 4.3.1.1.4.2 | 상품 가입 /해지 신청 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-10 | 2015-04-24 | 0.03 | 11 |  |  | 0.03 | 0 | 0 | 100% | 0%
| 620 | 6 | 4.3.1.1.4.3 | 신청 결과 조회 / 취소 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-24 | 2015-05-08 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 621 | 6 | 4.3.1.1.4.4 | MMT 계좌조회 / 해지 / 인출 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-08 | 2015-05-22 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 622 | 5 | 4.4.1.1.5 | 지로/공과금 |  |  | 0 | 2015-03-27 | 2015-06-05 | 0.1 | 51 |  |  | 0.1 | 0 | 0 | 49.02% | 0%
| 623 | 6 | 4.4.1.1.5.1 | 조회 납부 | 온라인 프로그램 소스코드 | PT개발자 | -1 | 2015-03-27 | 2015-04-10 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 624 | 6 | 4.4.1.1.5.2 | 입력 납부 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-10 | 2015-04-24 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 625 | 6 | 4.4.1.1.5.3 | 납부 영수증 보관함 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-24 | 2015-05-08 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 626 | 6 | 4.4.1.1.5.4 | 통신요금 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-08 | 2015-05-22 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 627 | 6 | 4.4.1.1.5.5 | 전기요금 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-22 | 2015-06-05 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 628 | 5 | 4.5.1.1.6 | 공인인증썬터 |  |  | 0 | 2015-03-27 | 2015-06-05 | 0.1 | 51 |  |  | 0.1 | 0 | 0 | 49.02% | 0%
| 629 | 6 | 4.5.1.1.6.1 | 범용인증서 발급/재발급 | 온라인 프로그램 소스코드 | PT개발자 | -1 | 2015-03-27 | 2015-04-10 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 630 | 6 | 4.5.1.1.6.2 | 범용인증서 등록/해지 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-10 | 2015-04-24 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 631 | 6 | 4.5.1.1.6.3 | 인증서 관리 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-24 | 2015-05-08 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 632 | 6 | 4.5.1.1.6.4 | 은행인증서 발급/재발급 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-08 | 2015-05-22 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 633 | 6 | 4.5.1.1.6.5 | 은행인증서 등록/해지 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-22 | 2015-06-05 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 634 | 5 | 4.5.1.1.7 | 송금/외화이체 |  |  | 0 | 2015-04-27 | 2015-07-06 | 0.12 | 51 |  |  | 0.12 | 0 | 0 | 0% | 0%
| 635 | 6 | 4.5.1.1.7.1 | 송금 안내 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-04-27 | 2015-05-08 | 0.02 | 10 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 636 | 6 | 4.5.1.1.7.2 | 송금 신청 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-11 | 2015-05-22 | 0.03 | 10 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 637 | 6 | 4.5.1.1.7.3 | 송금 결과 조회 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-25 | 2015-06-05 | 0.02 | 10 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 638 | 6 | 4.5.1.1.7.4 | 외화이체 안내 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-08 | 2015-06-19 | 0.02 | 10 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 639 | 6 | 4.5.1.1.7.5 | 외화 이체 실행 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-22 | 2015-07-06 | 0.03 | 11 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 640 | 5 | 4.5.1.1.8 | 취약성 점검 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-05-04 | 2015-05-08 | 0.02 | 5 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 641 | 5 | 4.5.1.1.9 | 외환매입매도 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-15 | 2015-07-15 | 0.03 | 23 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 642 | 5 | 4.5.1.1.10 | 환율 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-15 | 2015-07-15 | 0.03 | 23 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 643 | 5 | 4.5.1.1.11 | 대출 |  |  | 0 | 2015-06-01 | 2015-07-01 | 0.07 | 23 |  |  | 0.07 | 0 | 0 | 0% | 0%
| 644 | 6 | 4.5.1.1.11.1 | 대출 현황 조회 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-01 | 2015-06-10 | 0.02 | 8 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 645 | 6 | 4.5.1.1.11.2 | 대출 상환 현황 조회 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-08 | 2015-06-17 | 0.02 | 8 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 646 | 6 | 4.5.1.1.11.3 | 대출 상환 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-15 | 2015-07-01 | 0.03 | 13 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 647 | 5 | 4.5.1.1.12 | 고객정보관리 / 한도관리 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-15 | 2015-07-01 | 0.03 | 13 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 648 | 5 | 4.5.1.1.13 | 메인페이지 / 상품안내 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-29 | 2015-07-13 | 0.03 | 11 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 649 | 5 | 4.5.1.1.14 | 퇴직연금 조회 | 온라인 프로그램 소스코드 | PT개발자 | 0 | 2015-06-29 | 2015-07-13 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 650 | 4 | 4.5.1.2 | 배치 프로그램 구현 | 배치 프로그램 소스코드 | 개발자 | 0 | 2015-07-06 | 2015-07-17 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 651 | 3 | 4.5.2 | 단위테스트 수행 |  |  | 0 | 2015-06-01 | 2015-07-17 | 0.47 | 35 |  |  | 0.47 | 0 | 0 | 0% | 0%
| 652 | 4 | 4.5.2.1 | 단위테스트 수행 |  |  | 0 | 2015-06-01 | 2015-07-17 | 0.47 | 35 |  |  | 0.47 | 0 | 0 | 0% | 0%
| 653 | 5 | 4.5.2.1.1 | 통합로그인 / 보안 프로그램 | 단위테스트 결과서 | PT개발자 | 0 | 2015-06-01 | 2015-06-07 | 0.03 | 5 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 654 | 5 | 4.5.2.1.2 | 조회 | 단위테스트 결과서 | PT개발자 | 0 | 2015-06-01 | 2015-06-07 | 0.03 | 5 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 655 | 5 | 4.5.2.1.3 | 이체 | 단위테스트 결과서 | PT개발자 | 0 | 2015-06-08 | 2015-06-17 | 0.04 | 8 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 656 | 5 | 4.5.2.1.4 | 예금/해지 | 단위테스트 결과서 | PT개발자 | 0 | 2015-06-17 | 2015-06-22 | 0.03 | 4 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 657 | 5 | 4.5.2.1.5 | 지로/공과금 | 단위테스트 결과서 | PT개발자 | 0 | 2015-06-22 | 2015-07-02 | 0.04 | 9 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 658 | 5 | 4.5.2.1.6 | 공인인증썬터 | 단위테스트 결과서 | PT개발자 | 0 | 2015-06-22 | 2015-07-02 | 0.04 | 9 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 659 | 5 | 4.5.2.1.7 | 송금/외화이체 | 단위테스트 결과서 | PT개발자 | 0 | 2015-06-27 | 2015-07-07 | 0.04 | 7 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 660 | 5 | 4.5.2.1.8 | 외환매입매도 | 단위테스트 결과서 | PT개발자 | 0 | 2015-07-02 | 2015-07-12 | 0.04 | 7 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 661 | 5 | 4.5.2.1.9 | 환율 | 단위테스트 결과서 | PT개발자 | 0 | 2015-07-07 | 2015-07-17 | 0.04 | 9 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 662 | 5 | 4.5.2.1.10 | 대출 | 단위테스트 결과서 | PT개발자 | 0 | 2015-07-07 | 2015-07-17 | 0.04 | 9 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 663 | 5 | 4.5.2.1.11 | 고객정보관리 / 한도관리 | 단위테스트 결과서 | PT개발자 | 0 | 2015-07-07 | 2015-07-17 | 0.04 | 9 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 664 | 5 | 4.5.2.1.12 | 메인페이지 / 상품안내 | 단위테스트 결과서 | PT개발자 | 0 | 2015-07-12 | 2015-07-17 | 0.03 | 5 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 665 | 5 | 4.5.2.1.13 | 퇴직연금 | 단위테스트 결과서 | PT개발자 | 0 | 2015-07-12 | 2015-07-17 | 0.03 | 5 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 666 | 1 | 5 | 외환포탈 |  |  | 0 | 2015-02-09 | 2015-07-17 | 4 | 115 |  |  | 4 | 0 | 0 | 61.74% | 0%
| 667 | 2 | 5.1 | 분석 |  |  | 0 | 2015-02-09 | 2015-07-17 | 1.3 | 115 |  |  | 1.3 | 0 | 0 | 61.74% | 0%
| 668 | 3 | 5.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.9 | 15 |  |  | 0.9 | 0 | 0 | 100% | 0%
| 669 | 4 | 5.1.1.1 | 메뉴분석(공통/환율/환전/외화예금/FX우대서비스/FX가이드/글로벌센터/MYFXKEB) | 현행시스템분석서 | 분석/설계자 | -1 | 2015-02-09 | 2015-02-27 | 0.15 | 15 |  |  | 0.15 | 0 | 0 | 100% | 0%
| 670 | 4 | 5.1.1.1 | 메뉴분석(FX딜링/글로벌뱅킹/외화송금/수출입전자무역) | 현행시스템분석서 | 분석/설계자 | -1 | 2015-02-09 | 2015-02-27 | 0.15 | 15 |  |  | 0.15 | 0 | 0 | 100% | 0%
| 671 | 4 | 5.1.1.2 | 전문분석(공통/환율/환전/외화예금/FX우대서비스/FX가이드/글로벌센터/MYFXKEB) | 현행시스템분석서 | 분석/설계자 | -1 | 2015-02-09 | 2015-02-27 | 0.15 | 15 |  |  | 0.15 | 0 | 0 | 100% | 0%
| 672 | 4 | 5.1.1.2 | 전문분석(FX딜링/글로벌뱅킹/외화송금/수출입전자무역) | 현행시스템분석서 | 분석/설계자 | -1 | 2015-02-09 | 2015-02-27 | 0.15 | 15 |  |  | 0.15 | 0 | 0 | 100% | 0%
| 673 | 4 | 5.1.1.3 | TBL분석(공통/환율/환전/외화예금/FX우대서비스/FX가이드/글로벌센터/MYFXKEB) | 현행시스템분석서 | 분석/설계자 | -1 | 2015-02-09 | 2015-02-27 | 0.15 | 15 |  |  | 0.15 | 0 | 0 | 100% | 0%
| 674 | 4 | 5.1.1.3 | TBL분석(FX딜링/글로벌뱅킹/외화송금/수출입전자무역) | 현행시스템분석서 | 분석/설계자 | -1 | 2015-02-09 | 2015-02-27 | 0.15 | 15 |  |  | 0.15 | 0 | 0 | 100% | 0%
| 675 | 3 | 5.1.2 | 통합업무확정 |  |  | -1 | 2015-02-16 | 2015-02-27 | 0 | 10 |  |  | 0 | 0 | 0 | 100% | 0%
| 676 | 4 | 5.1.2.1 | 통합메뉴구조 확정 | 통합메뉴구조도 | 기획자 | -1 | 2015-02-16 | 2015-02-27 | 0 | 10 |  |  | 0 | 0 | 0 | 100% | 0%
| 677 | 3 | 5.1.3 | 통합요건정의 |  |  | -1 | 2015-03-02 | 2015-03-06 | 0.2 | 5 |  |  | 0.2 | 0 | 0 | 100% | 0%
| 678 | 4 | 5.1.3.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 업무총괄 | -1 | 2015-03-02 | 2015-03-06 | 0.2 | 5 |  |  | 0.2 | 0 | 0 | 100% | 0%
| 679 | 3 | 5.1.4 | 논리모델구축 |  |  | -1 | 2015-03-02 | 2015-03-06 | 0.2 | 5 |  |  | 0.2 | 0 | 0 | 100% | 0%
| 680 | 4 | 5.1.4.1 | 프로세스 모델링 |  |  | -1 | 2015-03-02 | 2015-03-06 | 0.2 | 5 |  |  | 0.2 | 0 | 0 | 100% | 0%
| 681 | 5 | 5.1.4.1.1 | 프로세스 모델링(공통/환율/환전/외화예금/FX우대서비스/FX가이드/글로벌센터/MYFXKEB) | 인터페이스 정의서 | 분석/설계자 | -1 | 2015-03-02 | 2015-03-06 | 0.1 | 5 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 682 | 5 | 5.1.4.1.2 | 프로세스 모델링(FX딜링/글로벌뱅킹/외화송금/수출입전자무역) | 인터페이스 정의서 | 분석/설계자 | -1 | 2015-03-02 | 2015-03-06 | 0.1 | 5 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 683 | 2 | 5.2 | 설계 |  |  | -1 | 2015-03-02 | 2015-04-17 | 1.3 | 35 |  |  | 1.3 | 0 | 0 | 100% | 0%
| 684 | 3 | 5.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-02 | 2015-04-10 | 0.56 | 30 |  |  | 0.56 | 0 | 0 | 100% | 0%
| 685 | 4 | 5.2.1.1 | 화면설계 |  |  | -1 | 2015-03-02 | 2015-03-20 | 0 | 15 |  |  | 0 | 0 | 0 | 100% | 0%
| 686 | 5 | 5.2.1.1.1 | 화면설계(공통/환율/환전/외화예금/FX우대서비스/FX가이드/글로벌센터/MYFXKEB) | 화면설계서 | 기획자 | -1 | 2015-03-02 | 2015-03-20 | 0 | 15 |  |  | 0 | 0 | 0 | 100% | 0%
| 687 | 5 | 5.2.1.1.2 | 화면설계(FX딜링/글로벌뱅킹/외화송금/수출입전자무역) | 화면설계서 | 기획자 | -1 | 2015-03-02 | 2015-03-20 | 0 | 15 |  |  | 0 | 0 | 0 | 100% | 0%
| 688 | 4 | 5.2.1.1 | 프로그램 설계 |  |  | -1 | 2015-03-16 | 2015-04-10 | 0.56 | 20 |  |  | 0.56 | 0 | 0 | 100% | 0%
| 689 | 5 | 5.2.1.1.1 | 프로그램 설계(공통/환율/환전) | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.14 | 20 |  |  | 0.14 | 0 | 0 | 100% | 0%
| 690 | 5 | 5.2.1.1.2 | 프로그램 설계(외화예금/FX우대서비스/FX가이드/글로벌센터/MYFXKEB) | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.14 | 20 |  |  | 0.14 | 0 | 0 | 100% | 0%
| 691 | 5 | 5.2.1.1.1 | 프로그램 설계(글로벌뱅킹/외화송금/수출입전자무역) | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.14 | 20 |  |  | 0.14 | 0 | 0 | 100% | 0%
| 692 | 5 | 5.2.1.1.2 | 프로그램 설계(FX딜링) | 프로그램 목록 프로그램 사양서 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.14 | 20 |  |  | 0.14 | 0 | 0 | 100% | 0%
| 693 | 3 | 5.2.2 | 통합전문설계 |  |  | -1 | 2015-03-16 | 2015-04-10 | 0.56 | 20 |  |  | 0.56 | 0 | 0 | 100% | 0%
| 694 | 4 | 5.2.2.1 | 전문매핑 |  |  | -1 | 2015-03-16 | 2015-04-10 | 0.56 | 20 |  |  | 0.56 | 0 | 0 | 100% | 0%
| 695 | 5 | 5.2.2.1.1 | 전문매핑((공통/환율/환전) | 전문목록 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.14 | 20 |  |  | 0.14 | 0 | 0 | 100% | 0%
| 696 | 5 | 5.2.2.1.2 | 전문매핑(외화예금/FX우대서비스/FX가이드/글로벌센터/MYFXKEB) | 전문목록 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.14 | 20 |  |  | 0.14 | 0 | 0 | 100% | 0%
| 697 | 5 | 5.2.2.1.1 | 전문매핑(글로벌뱅킹/외화송금/수출입전자무역) | 전문목록 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.14 | 20 |  |  | 0.14 | 0 | 0 | 100% | 0%
| 698 | 5 | 5.2.2.1.2 | 전문매핑(FX딜링) | 전문목록 | 분석/설계자 | -1 | 2015-03-16 | 2015-04-10 | 0.14 | 20 |  |  | 0.14 | 0 | 0 | 100% | 0%
| 699 | 3 | 5.2.3 | 배치프로세스 설계 |  |  | -1 | 2015-04-06 | 2015-04-17 | 0.06 | 10 |  |  | 0.06 | 0 | 0 | 100% | 0%
| 700 | 4 | 5.2.3.1 | 배치프로그램 설계 |  |  | -1 | 2015-04-06 | 2015-04-17 | 0.06 | 10 |  |  | 0.06 | 0 | 0 | 100% | 0%
| 701 | 5 | 5.2.3.1.1 | 배치프로그램 설계 | 배치프로세스 정의서 | 분석/설계자 | -1 | 2015-04-06 | 2015-04-17 | 0.06 | 10 |  |  | 0.06 | 0 | 0 | 100% | 0%
| 702 | 3 | 5.2.4 | 통합 DB 설계 |  |  | -1 | 2015-03-02 | 2015-03-31 | 0.12 | 22 |  |  | 0.12 | 0 | 0 | 100% | 0%
| 703 | 4 | 5.2.4.1 | 양행 테이블/속성 매핑 | 논리 ERD 물리 ERD 테이블목록 테이블매핑정의서 | DBA | -1 | 2015-03-02 | 2015-03-31 | 0.06 | 22 |  |  | 0.06 | 0 | 0 | 100% | 0%
| 704 | 4 | 5.2.4.2 | 통합 데이터베이스 모델링 |  |  | -1 | 2015-03-02 | 2015-03-31 | 0.06 | 22 |  |  | 0.06 | 0 | 0 | 100% | 0%
| 705 | 2 | 5.3 | 구현 |  |  | 0 | 2015-03-23 | 2015-07-17 | 1.4 | 85 |  |  | 1.4 | 0 | 0 | 34.12% | 0%
| 706 | 3 | 5.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-23 | 2015-07-17 | 0.44 | 85 |  |  | 0.44 | 0 | 0 | 34.12% | 0%
| 707 | 4 | 5.3.1.1 | 환율(36) |  |  | -1 | 2015-03-23 | 2015-04-17 | 0.05 | 20 |  |  | 0.05 | 0 | 0 | 100% | 0%
| 708 | 5 | 5.3.1.1.1 | 메인(1) | 온라인 프로그램 소스코드 | 개발자0 | -1 | 2015-03-23 | 2015-04-17 | 0.01 | 20 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 709 | 5 | 5.3.1.1.2 | 고시환율(13) | 온라인 프로그램 소스코드 | 개발자0 | -1 | 2015-03-23 | 2015-04-01 | 0.01 | 8 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 710 | 5 | 5.3.1.1.3 | 외환시장환율정보(3) | 온라인 프로그램 소스코드 | 개발자0 | -1 | 2015-04-11 | 2015-04-14 | 0.01 | 2 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 711 | 5 | 5.3.1.1.4 | 환율제공서비스(16) | 온라인 프로그램 소스코드 | 개발자0 | -1 | 2015-04-02 | 2015-04-10 | 0.01 | 7 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 712 | 5 | 5.3.1.1.5 | 외환시장동향(3) | 온라인 프로그램 소스코드 | 개발자0 | -1 | 2015-04-15 | 2015-04-17 | 0.01 | 3 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 713 | 4 | 5.3.1.2 | 환전(61) |  |  | 0 | 2015-05-11 | 2015-06-23 | 0.05 | 32 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 714 | 5 | 5.3.1.2.1 | 사이버환전(18) | 온라인 프로그램 소스코드 | 개발자1 | 0 | 2015-05-11 | 2015-05-30 | 0.01 | 15 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 715 | 5 | 5.3.1.2.2 | 외화기프트서비스(6) | 온라인 프로그램 소스코드 | 개발자1 | 0 | 2015-06-02 | 2015-06-05 | 0.01 | 4 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 716 | 5 | 5.3.1.2.3 | 환전내역조회(1) | 온라인 프로그램 소스코드 | 개발자1 | 0 | 2015-06-09 | 2015-06-11 | 0.01 | 3 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 717 | 5 | 5.3.1.2.4 | 환전클럽(4) | 온라인 프로그램 소스코드 | 개발자1 | 0 | 2015-06-12 | 2015-06-17 | 0.01 | 4 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 718 | 5 | 5.3.1.2.5 | 환전우대(3) | 온라인 프로그램 소스코드 | 개발자1 | 0 | 2015-06-18 | 2015-06-23 | 0.01 | 4 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 719 | 4 | 5.3.1.3 | 외화송금(55) |  |  | 0 | 2015-04-06 | 2015-05-29 | 0.08 | 40 |  |  | 0.08 | 0 | 0 | 37.5% | 0%
| 720 | 5 | 5.3.1.3.1 | 해외송금(8) | 온라인 프로그램 소스코드 | 개발자2 | 0 | 2015-05-11 | 2015-05-29 | 0.01 | 15 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 721 | 5 | 5.3.1.3.2 | 국내즉시송금(1) | 온라인 프로그램 소스코드 | 개발자2 | -1 | 2015-04-06 | 2015-04-08 | 0.01 | 3 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 722 | 5 | 5.3.1.3.3 | 외화송금내역(1) | 온라인 프로그램 소스코드 | 개발자2 | -1 | 2015-04-09 | 2015-04-10 | 0.01 | 2 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 723 | 5 | 5.3.1.3.4 | 송금Tracking(1) | 온라인 프로그램 소스코드 | 개발자2 | -1 | 2015-04-13 | 2015-04-14 | 0.01 | 2 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 724 | 5 | 5.3.1.3.5 | 송금정보(2) | 온라인 프로그램 소스코드 | 개발자2 | -1 | 2015-04-15 | 2015-04-17 | 0.01 | 3 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 725 | 5 | 5.3.1.3.6 | 외국환거래은행지정(2) | 온라인 프로그램 소스코드 | 개발자2 | 0 | 2015-04-20 | 2015-04-22 | 0.01 | 3 |  |  | 0.01 | 0 | 0 | 33.33% | 0%
| 726 | 5 | 5.3.1.3.7 | 외화수표추심결과(1) | 온라인 프로그램 소스코드 | 개발자2 | 0 | 2015-04-23 | 2015-04-24 | 0.01 | 2 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 727 | 5 | 5.3.1.3.8 | 송금클럽(5) | 온라인 프로그램 소스코드 | 개발자2 | 0 | 2015-04-27 | 2015-05-08 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 728 | 4 | 5.3.1.4 | FX딜링(194) |  |  | 0 | 2015-03-23 | 2015-07-16 | 0.03 | 84 |  |  | 0.03 | 0 | 0 | 34.52% | 0%
| 729 | 5 | 5.3.1.4.1 | 인터넷FX딜링서비스(76) | 온라인 프로그램 소스코드 | 개발자4 | 0 | 2015-03-23 | 2015-05-02 | 0.01 | 30 |  |  | 0.01 | 0 | 0 | 96.67% | 0%
| 730 | 5 | 5.3.1.4.2 | 차액결제거래(66) | 온라인 프로그램 소스코드 | 개발자4 | 0 | 2015-05-07 | 2015-06-05 | 0.01 | 22 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 731 | 5 | 5.3.1.4.3 | 환율매매예약(52) | 온라인 프로그램 소스코드 | 개발자4 | 0 | 2015-06-09 | 2015-07-16 | 0.01 | 28 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 732 | 4 | 5.3.1.5 | 외화예금(53) |  |  | 0 | 2015-04-14 | 2015-06-05 | 0.07 | 39 |  |  | 0.07 | 0 | 0 | 17.95% | 0%
| 733 | 5 | 5.3.1.5.1 | 메인(1) | 온라인 프로그램 소스코드 | 개발자3 | 0 | 2015-04-14 | 2015-06-05 | 0.01 | 39 |  |  | 0.01 | 0 | 0 | 17.95% | 0%
| 734 | 5 | 5.3.1.5.2 | 외화예금안내(6) | 온라인 프로그램 소스코드 | 개발자3 | 0 | 2015-04-22 | 2015-04-28 | 0.01 | 5 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 735 | 5 | 5.3.1.5.3 | 외화예금상품(3) | 온라인 프로그램 소스코드 | 개발자3 | -1 | 2015-04-17 | 2015-04-21 | 0.01 | 3 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 736 | 5 | 5.3.1.5.4 | 외화예금e뱅킹(13) | 온라인 프로그램 소스코드 | 개발자3 | 0 | 2015-05-08 | 2015-05-21 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 737 | 5 | 5.3.1.5.5 | 외환매입매도(18) | 온라인 프로그램 소스코드 | 개발자3 | 0 | 2015-05-22 | 2015-06-05 | 0.01 | 11 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 738 | 5 | 5.3.1.5.6 | 글로벌계좌이체(9) | 온라인 프로그램 소스코드 | 개발자3 | 0 | 2015-04-29 | 2015-05-07 | 0.01 | 7 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 739 | 5 | 5.3.1.5.7 | 외화예금관련서비스(3) | 온라인 프로그램 소스코드 | 개발자3 | -1 | 2015-04-14 | 2015-04-16 | 0.01 | 3 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 740 | 4 | 5.3.1.6 | FX우대서비스(11) |  |  | 0 | 2015-06-24 | 2015-07-16 | 0.02 | 17 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 741 | 5 | 5.3.1.6.1 | 환전우대(4) | 온라인 프로그램 소스코드 | 개발자1 | 0 | 2015-06-24 | 2015-06-30 | 0.01 | 5 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 742 | 5 | 5.3.1.6.2 | 외환MoneyBag(7) | 온라인 프로그램 소스코드 | 개발자1 | 0 | 2015-07-01 | 2015-07-16 | 0.01 | 12 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 743 | 4 | 5.3.1.7 | 글로벌뱅킹(15) | 온라인 프로그램 소스코드 | 개발자2 | 0 | 2015-06-01 | 2015-07-16 | 0.01 | 34 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 744 | 4 | 5.3.1.8 | 기타(35) |  |  | 0 | 2015-04-01 | 2015-05-08 | 0.04 | 28 |  |  | 0.04 | 0 | 0 | 71.43% | 0%
| 745 | 5 | 5.3.1.8.1 | 수출입전자무역 | 온라인 프로그램 소스코드 | 개발자1 | 0 | 2015-04-27 | 2015-05-08 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 746 | 5 | 5.3.1.8.2 | FX가이드 | 온라인 프로그램 소스코드 | 개발자1 | -1 | 2015-04-01 | 2015-04-08 | 0.01 | 6 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 747 | 5 | 5.3.1.8.3 | 글로벌센터 | 온라인 프로그램 소스코드 | 개발자3 | -1 | 2015-04-01 | 2015-04-10 | 0.01 | 8 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 748 | 5 | 5.3.1.8.4 | MYFXKEB | 온라인 프로그램 소스코드 | 개발자1 | 0 | 2015-04-09 | 2015-04-24 | 0.01 | 12 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 749 | 4 | 5.3.1.9 | 배치 프로그램 구현(20) |  |  | 0 | 2015-06-08 | 2015-07-16 | 0.02 | 29 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 750 | 5 | 5.3.1.9.1 | 배치(18) | 배치 프로그램 소스코드 | 개발자3 | 0 | 2015-06-29 | 2015-07-16 | 0.01 | 14 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 751 | 5 | 5.3.1.9.2 | 데몬(21) | 쉘 프로그램 소스코드 | 개발자3 | 0 | 2015-06-08 | 2015-06-26 | 0.01 | 15 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 752 | 4 | 5.3.1.10 | 외환포탈관리자(69) |  |  | 0 | 2015-04-21 | 2015-07-16 | 0.06 | 63 |  |  | 0.06 | 0 | 0 | 0% | 0%
| 753 | 5 | 5.3.1.10.1 | 실적관리(13) | 온라인 프로그램 소스코드 | 개발자0 | 0 | 2015-07-03 | 2015-07-16 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 754 | 5 | 5.3.1.10.2 | 고객관리(9) | 온라인 프로그램 소스코드 | 개발자0 | 0 | 2015-06-19 | 2015-07-02 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 755 | 5 | 5.3.1.10.3 | 우대율관리(5) | 온라인 프로그램 소스코드 | 개발자0 | 0 | 2015-05-04 | 2015-05-15 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 756 | 5 | 5.3.1.10.4 | 통화관리(8) | 온라인 프로그램 소스코드 | 개발자0 | 0 | 2015-04-21 | 2015-05-01 | 0.01 | 9 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 757 | 5 | 5.3.1.10.5 | 주관부서업무(5) | 온라인 프로그램 소스코드 | 개발자0 | 0 | 2015-05-18 | 2015-05-28 | 0.01 | 9 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 758 | 5 | 5.3.1.10.6 | 외환포탈(FX딜링)(23) | 온라인 프로그램 소스코드 | 개발자0 | 0 | 2015-05-29 | 2015-06-18 | 0.01 | 15 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 759 | 4 | 5.3.1.11 | 외환포탈공통(42) | 공통 프로그램 소스코드 | 개발자0 | 0 | 2015-03-23 | 2015-07-17 | 0.01 | 85 |  |  | 0.01 | 0 | 0 | 34.12% | 0%
| 760 | 3 | 5.3.2 | 단위테스트 수행 |  |  | 0 | 2015-03-23 | 2015-07-17 | 0.96 | 85 |  |  | 0.96 | 0 | 0 | 34.12% | 0%
| 761 | 4 | 5.3.2.1 | 환율(36) |  |  | -1 | 2015-03-23 | 2015-04-17 | 0.1 | 20 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 762 | 5 | 5.3.2.1.1 | 메인(1) | 단위테스트결과서 | 개발자0 | -1 | 2015-03-23 | 2015-04-17 | 0.02 | 20 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 763 | 5 | 5.3.2.1.2 | 고시환율(13) | 단위테스트결과서 | 개발자0 | -1 | 2015-03-23 | 2015-04-01 | 0.02 | 8 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 764 | 5 | 5.3.2.1.3 | 외환시장환율정보(3) | 단위테스트결과서 | 개발자0 | -1 | 2015-04-11 | 2015-04-14 | 0.02 | 2 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 765 | 5 | 5.3.2.1.4 | 환율제공서비스(16) | 단위테스트결과서 | 개발자0 | -1 | 2015-04-02 | 2015-04-10 | 0.02 | 7 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 766 | 5 | 5.3.2.1.5 | 외환시장동향(3) | 단위테스트결과서 | 개발자0 | -1 | 2015-04-15 | 2015-04-17 | 0.02 | 3 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 767 | 4 | 5.3.2.2 | 환전(61) |  |  | 0 | 2015-05-11 | 2015-06-23 | 0.1 | 32 |  |  | 0.1 | 0 | 0 | 0% | 0%
| 768 | 5 | 5.3.2.2.1 | 사이버환전(18) | 단위테스트결과서 | 개발자1 | 0 | 2015-05-11 | 2015-05-30 | 0.02 | 15 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 769 | 5 | 5.3.2.2.2 | 외화기프트서비스(6) | 단위테스트결과서 | 개발자1 | 0 | 2015-06-02 | 2015-06-05 | 0.02 | 4 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 770 | 5 | 5.3.2.2.3 | 환전내역조회(1) | 단위테스트결과서 | 개발자1 | 0 | 2015-06-09 | 2015-06-11 | 0.02 | 3 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 771 | 5 | 5.3.2.2.4 | 환전클럽(4) | 단위테스트결과서 | 개발자1 | 0 | 2015-06-12 | 2015-06-17 | 0.02 | 4 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 772 | 5 | 5.3.2.2.5 | 환전우대(3) | 단위테스트결과서 | 개발자1 | 0 | 2015-06-18 | 2015-06-23 | 0.02 | 4 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 773 | 4 | 5.3.2.3 | 외화송금(55) |  |  | 0 | 2015-04-06 | 2015-05-29 | 0.16 | 40 |  |  | 0.16 | 0 | 0 | 37.5% | 0%
| 774 | 5 | 5.3.2.3.1 | 해외송금(8) | 단위테스트결과서 | 개발자2 | 0 | 2015-05-11 | 2015-05-29 | 0.02 | 15 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 775 | 5 | 5.3.2.3.2 | 국내즉시송금(1) | 단위테스트결과서 | 개발자2 | -1 | 2015-04-06 | 2015-04-08 | 0.02 | 3 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 776 | 5 | 5.3.2.3.3 | 외화송금내역(1) | 단위테스트결과서 | 개발자2 | -1 | 2015-04-09 | 2015-04-10 | 0.02 | 2 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 777 | 5 | 5.3.2.3.4 | 송금Tracking(1) | 단위테스트결과서 | 개발자2 | -1 | 2015-04-13 | 2015-04-14 | 0.02 | 2 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 778 | 5 | 5.3.2.3.5 | 송금정보(2) | 단위테스트결과서 | 개발자2 | -1 | 2015-04-15 | 2015-04-17 | 0.02 | 3 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 779 | 5 | 5.3.2.3.6 | 외국환거래은행지정(2) | 단위테스트결과서 | 개발자2 | 0 | 2015-04-20 | 2015-04-22 | 0.02 | 3 |  |  | 0.02 | 0 | 0 | 33.33% | 0%
| 780 | 5 | 5.3.2.3.7 | 외화수표추심결과(1) | 단위테스트결과서 | 개발자2 | 0 | 2015-04-23 | 2015-04-24 | 0.02 | 2 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 781 | 5 | 5.3.2.3.8 | 송금클럽(5) | 단위테스트결과서 | 개발자2 | 0 | 2015-04-27 | 2015-05-08 | 0.02 | 10 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 782 | 4 | 5.3.2.4 | FX딜링(194) |  |  | 0 | 2015-03-23 | 2015-07-16 | 0.1 | 84 |  |  | 0.1 | 0 | 0 | 34.52% | 0%
| 783 | 5 | 5.3.2.4.1 | 인터넷FX딜링서비스(76) | 단위테스트결과서 | 개발자4 | 0 | 2015-03-23 | 2015-05-02 | 0.04 | 30 |  |  | 0.04 | 0 | 0 | 96.67% | 0%
| 784 | 5 | 5.3.2.4.2 | 차액결제거래(66) | 단위테스트결과서 | 개발자4 | 0 | 2015-05-07 | 2015-06-05 | 0.02 | 22 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 785 | 5 | 5.3.2.4.3 | 환율매매예약(52) | 단위테스트결과서 | 개발자4 | 0 | 2015-06-09 | 2015-07-16 | 0.04 | 28 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 786 | 4 | 5.3.2.5 | 외화예금(53) |  |  | 0 | 2015-04-14 | 2015-06-05 | 0.14 | 39 |  |  | 0.14 | 0 | 0 | 17.95% | 0%
| 787 | 5 | 5.3.2.5.1 | 메인(1) | 단위테스트결과서 | 개발자3 | 0 | 2015-04-14 | 2015-06-05 | 0.02 | 39 |  |  | 0.02 | 0 | 0 | 17.95% | 0%
| 788 | 5 | 5.3.2.5.2 | 외화예금안내(6) | 단위테스트결과서 | 개발자3 | 0 | 2015-04-22 | 2015-04-28 | 0.02 | 5 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 789 | 5 | 5.3.2.5.3 | 외화예금상품(3) | 단위테스트결과서 | 개발자3 | -1 | 2015-04-17 | 2015-04-21 | 0.02 | 3 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 790 | 5 | 5.3.2.5.4 | 외화예금e뱅킹(13) | 단위테스트결과서 | 개발자3 | 0 | 2015-05-08 | 2015-05-21 | 0.02 | 10 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 791 | 5 | 5.3.2.5.5 | 외환매입매도(18) | 단위테스트결과서 | 개발자3 | 0 | 2015-05-22 | 2015-06-05 | 0.02 | 11 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 792 | 5 | 5.3.2.5.6 | 글로벌계좌이체(9) | 단위테스트결과서 | 개발자3 | 0 | 2015-04-29 | 2015-05-07 | 0.02 | 7 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 793 | 5 | 5.3.2.5.7 | 외화예금관련서비스(3) | 단위테스트결과서 | 개발자3 | -1 | 2015-04-14 | 2015-04-16 | 0.02 | 3 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 794 | 4 | 5.3.2.6 | FX우대서비스(11) |  |  | 0 | 2015-06-24 | 2015-07-16 | 0.04 | 17 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 795 | 5 | 5.3.2.6.1 | 환전우대(4) | 단위테스트결과서 | 개발자1 | 0 | 2015-06-24 | 2015-06-30 | 0.02 | 5 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 796 | 5 | 5.3.2.6.2 | 외환MoneyBag(7) | 단위테스트결과서 | 개발자1 | 0 | 2015-07-01 | 2015-07-16 | 0.02 | 12 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 797 | 4 | 5.3.2.7 | 글로벌뱅킹(15) | 단위테스트결과서 | 개발자2 | 0 | 2015-06-01 | 2015-07-16 | 0.06 | 34 |  |  | 0.06 | 0 | 0 | 0% | 0%
| 798 | 4 | 5.3.2.8 | 기타(35) |  |  | 0 | 2015-04-01 | 2015-05-08 | 0.08 | 28 |  |  | 0.08 | 0 | 0 | 71.43% | 0%
| 799 | 5 | 5.3.2.8.1 | 수출입전자무역 | 단위테스트결과서 | 개발자1 | 0 | 2015-04-27 | 2015-05-08 | 0.02 | 10 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 800 | 5 | 5.3.2.8.2 | FX가이드 | 단위테스트결과서 | 개발자1 | -1 | 2015-04-01 | 2015-04-08 | 0.02 | 6 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 801 | 5 | 5.3.2.8.3 | 글로벌센터 | 단위테스트결과서 | 개발자3 | -1 | 2015-04-01 | 2015-04-10 | 0.02 | 8 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 802 | 5 | 5.3.2.8.4 | MYFXKEB | 단위테스트결과서 | 개발자1 | 0 | 2015-04-09 | 2015-04-24 | 0.02 | 12 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 803 | 4 | 5.3.2.9 | 배치 프로그램 구현(20) |  |  | 0 | 2015-06-08 | 2015-07-16 | 0.04 | 29 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 804 | 5 | 5.3.2.9.1 | 배치(18) | 단위테스트결과서 | 개발자3 | 0 | 2015-06-29 | 2015-07-16 | 0.02 | 14 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 805 | 5 | 5.3.2.9.2 | 데몬(21) | 단위테스트결과서 | 개발자3 | 0 | 2015-06-08 | 2015-06-26 | 0.02 | 15 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 806 | 4 | 5.3.2.10 | 외환포탈관리자(69) |  |  | 0 | 2015-04-21 | 2015-07-16 | 0.12 | 63 |  |  | 0.12 | 0 | 0 | 0% | 0%
| 807 | 5 | 5.3.2.10.1 | 실적관리(13) | 단위테스트결과서 | 개발자0 | 0 | 2015-07-03 | 2015-07-16 | 0.02 | 10 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 808 | 5 | 5.3.2.10.2 | 고객관리(9) | 단위테스트결과서 | 개발자0 | 0 | 2015-06-19 | 2015-07-02 | 0.02 | 10 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 809 | 5 | 5.3.2.10.3 | 우대율관리(5) | 단위테스트결과서 | 개발자0 | 0 | 2015-05-04 | 2015-05-15 | 0.02 | 10 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 810 | 5 | 5.3.2.10.4 | 통화관리(8) | 단위테스트결과서 | 개발자0 | 0 | 2015-04-21 | 2015-05-01 | 0.02 | 9 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 811 | 5 | 5.3.2.10.5 | 주관부서업무(5) | 단위테스트결과서 | 개발자0 | 0 | 2015-05-18 | 2015-05-28 | 0.02 | 9 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 812 | 5 | 5.3.2.10.6 | 외환포탈(FX딜링)(23) | 단위테스트결과서 | 개발자0 | 0 | 2015-05-29 | 2015-06-18 | 0.02 | 15 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 813 | 4 | 5.3.2.11 | 외환포탈공통(42) | 단위테스트결과서 | 개발자0 | 0 | 2015-03-23 | 2015-07-17 | 0.02 | 85 |  |  | 0.02 | 0 | 0 | 34.12% | 0%
| 814 | 1 | 6 | 기업 뱅킹 |  |  | 1 |  | #REF! | #REF! | 16 |  |  | #REF! | 0 | 0 |  | 0%
| 815 | 2 | 6.1 | 분석 |  |  | 1 | 2015-02-09 | 2015-03-20 | #REF! | 5 |  |  | #REF! |  |  |  | 0%
| 816 | 3 | 6.1.1 | 현황분석 |  |  | 1 |  | 2015-03-22 | 1 | 1 |  |  | 1 |  |  |  | 0%
| 817 | 4 | 6.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 |  | 1 |  | 2015-03-24 | 1 | 30062 |  |  | 1 | 0 | 0 |  | 0%
| 818 | 5 | 6.1.1.1.1 | 이체 |  |  | 1 | 2015-02-09 | 2015-03-20 | 0.1 | 30 |  |  | 0.1 | 0 | 0 |  | 0%
| 819 | 6 | 6.1.1.1.1.1 | 계좌관리,이체 |  |  | 1 | 2015-02-09 | 2015-02-27 |  | 15 |  |  |  | 0 | 0 |  | 0%
| 820 | 6 | 6.1.1.1.1.2 | 대량이체외 |  |  | 1 | 2015-03-02 | 2015-03-10 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 821 | 6 | 6.1.1.1.1.3 | 이체결과 |  |  | 1 | 2015-03-10 | 2015-03-13 |  | 4 |  |  |  | 0 | 0 |  | 0%
| 822 | 6 | 6.1.1.1.1.4 | 글로벌이체 |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 823 | 5 | 6.1.1.1.2 | 전자결제 |  |  | 1 | 2015-02-09 | 2015-03-13 | 0.12 | 25 |  |  | 0.12 | 0 | 0 |  | 0%
| 824 | 6 | 6.1.1.1.2.1 | 판매기업 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 825 | 6 | 6.1.1.1.2.2 | 구매기업 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 826 | 6 | 6.1.1.1.2.3 | 중개기업 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 827 | 6 | 6.1.1.1.2.4 | 대행업무 |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 828 | 5 | 6.1.1.1.3 | 외국환 |  |  | 1 | 2015-02-09 | 2015-03-13 | 0.15 | 25 |  |  | 0.15 | 0 | 0 |  | 0%
| 829 | 6 | 6.1.1.1.3.1 | 외화송금 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 830 | 6 | 6.1.1.1.3.2 | 외환매매 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 831 | 6 | 6.1.1.1.3.3 | 환율/금리조회 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 832 | 6 | 6.1.1.1.3.4 | 수입 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 833 | 6 | 6.1.1.1.3.5 | 수출 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 834 | 6 | 6.1.1.1.3.6 | 수수료(수입/수출) |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 835 | 6 | 6.1.1.1.3.7 | 인터넷EDI |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 836 | 6 | 6.1.1.1.3.8 | 환리스크관리 |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 837 | 6 | 6.1.1.1.3.9 | BiCNET Global |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 838 | 6 | 6.1.1.1.3.10 | 전자무역 |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 839 | 5 | 6.1.1.1.4 | 조회 |  |  | 1 | 2015-02-09 | 2015-02-27 | 0.02 | 15 |  |  | 0.02 | 0 | 0 |  | 0%
| 840 | 6 | 6.1.1.1.4.1 | 예금/펀드 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 841 | 6 | 6.1.1.1.4.2 | 보관어음 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 842 | 6 | 6.1.1.1.4.3 | 신용카드 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 843 | 6 | 6.1.1.1.4.4 | 주류카드 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 844 | 6 | 6.1.1.1.4.5 | 보고서 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 845 | 6 | 6.1.1.1.4.6 | CMS계좌 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 846 | 5 | 6.1.1.1.5 | 신규해지 |  |  | 1 | 2015-02-16 | 2015-03-20 | 0.06 | 25 |  |  | 0.06 | 0 | 0 |  | 0%
| 847 | 6 | 6.1.1.1.5.1 | 예금 |  |  | 1 | 2015-02-16 | 2015-02-24 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 848 | 6 | 6.1.1.1.5.2 | 인터넷외화예금 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 849 | 6 | 6.1.1.1.5.3 | 퇴직연금 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 850 | 6 | 6.1.1.1.5.4 | 펀드 |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 851 | 6 | 6.1.1.1.5.5 | 특정금전신탁 |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 852 | 5 | 6.1.1.1.6 | 대출 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.05 | 30 |  |  | 0.05 | 0 | 0 |  | 0%
| 853 | 6 | 6.1.1.1.6.1 | 대출조회 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 854 | 6 | 6.1.1.1.6.2 | 대출상환/이자납입 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 855 | 6 | 6.1.1.1.6.3 | 질권설정예정계좌등록 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 856 | 6 | 6.1.1.1.6.4 | 대출신청 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-20 |  | 10 |  |  |  | 0 | 0 |  | 0%
| 857 | 5 | 6.1.1.1.7 | 공과금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-22 | 0.04 | 30 |  |  | 0.04 | 0 | 0 |  | 0%
| 858 | 6 | 6.1.1.1.7.1 | My 공과금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 859 | 6 | 6.1.1.1.7.2 | 지로 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 860 | 6 | 6.1.1.1.7.3 | 세금 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 861 | 6 | 6.1.1.1.7.4 | 생활요금/부담금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 862 | 6 | 6.1.1.1.7.5 | 벌칙금/벌과금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 863 | 6 | 6.1.1.1.7.6 | 연금/보험금 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 864 | 6 | 6.1.1.1.7.7 | 국고및기금 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 865 | 6 | 6.1.1.1.7.8 | 예약납부 조회/취소 | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 866 | 5 | 6.1.1.1.8 | 통합자금관리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.07 | 30 |  |  | 0.07 | 0 | 0 |  | 0%
| 867 | 6 | 6.1.1.1.8.1 | 당행집금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 868 | 6 | 6.1.1.1.8.2 | 인터넷계좌통합 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 869 | 6 | 6.1.1.1.8.3 | 집금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 870 | 6 | 6.1.1.1.8.4 | 배분 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 871 | 6 | 6.1.1.1.8.5 | 법인카드 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 872 | 6 | 6.1.1.1.8.6 | 서비스환경 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 873 | 6 | 6.1.1.1.8.7 | ERP연계 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 874 | 6 | 6.1.1.1.8.8 | 가상계좌 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 875 | 6 | 6.1.1.1.8.9 | 통합집금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 876 | 6 | 6.1.1.1.8.10 | 집금대행 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 877 | 6 | 6.1.1.1.8.11 | 등록금수납관리 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 878 | 6 | 6.1.1.1.8.12 | 희망키움통장II | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 879 | 5 | 6.1.1.1.9 | 부가서비스 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.04 | 25 |  |  | 0.04 | 0 | 0 |  | 0%
| 880 | 6 | 6.1.1.1.9.1 | 급여관리서비스 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 881 | 6 | 6.1.1.1.9.2 | 전화로승인 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 882 | 6 | 6.1.1.1.9.3 | 소액계좌관리/휴면계좌정리/무통장거래정리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 883 | 6 | 6.1.1.1.9.4 | 수수료관리 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 884 | 5 | 6.1.1.1.10 | 결재함 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.06 | 25 |  |  | 0.06 | 0 | 0 |  | 0%
| 885 | 6 | 6.1.1.1.10.1 | 미결재내역 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 886 | 6 | 6.1.1.1.10.2 | 결재내역 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 887 | 6 | 6.1.1.1.10.3 | 등록내역 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 888 | 6 | 6.1.1.1.10.4 | 거래함 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 889 | 5 | 6.1.1.1.11 | 사용자관리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.15 | 30 |  |  | 0.15 | 0 | 0 |  | 0%
| 890 | 6 | 6.1.1.1.11.1 | 내부통제 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-24 |  | 12 |  |  |  | 0 | 0 |  | 0%
| 891 | 6 | 6.1.1.1.11.2 | 결재서비스 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-13 |  | 10 |  |  |  | 0 | 0 |  | 0%
| 892 | 6 | 6.1.1.1.11.3 | 기타환경설정 | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 893 | 5 | 6.1.1.1.12 | 공인인증센터 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.06 | 25 |  |  | 0.06 | 0 | 0 |  | 0%
| 894 | 6 | 6.1.1.1.12.1 | 공인인증서 상세안내 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 895 | 6 | 6.1.1.1.12.2 | 인증서 신규/재발급 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 896 | 6 | 6.1.1.1.12.3 | 타행/타기관인증서 등록 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 897 | 6 | 6.1.1.1.12.4 | 인증서 관리 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 898 | 6 | 6.1.1.1.12.5 | 인증서 갱신/폐기 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 899 | 6 | 6.1.1.1.12.6 | 인증서 정보조회 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 900 | 6 | 6.1.1.1.12.7 | 영수증/세금계산서 발급 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 901 | 6 | 6.1.1.1.12.8 | 발급수수료 환불신청 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 902 | 6 | 6.1.1.1.12.9 | 스마트폰인증서복사 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 903 | 5 | 6.1.1.1.13 | 배치/관리자 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.08 | 30 |  |  | 0.08 | 0 | 0 |  | 0%
| 904 | 6 | 6.1.1.1.13.1 | 배치 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-24 |  | 12 |  |  |  | 0 | 0 |  | 0%
| 905 | 6 | 6.1.1.1.13.2 | 관리자 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-20 |  | 15 |  |  |  | 0 | 0 |  | 0%
| 906 | 3 | 6.1.2 | GAP 분석 |  |  | 1 |  | 2015-03-26 | #REF! | 1.8 |  |  | #REF! |  |  |  | 0%
| 907 | 4 | 6.1.2.1 | 메뉴 GAP분석 | 현행 시스템 분석서 |  | 1 |  | 2015-03-28 | 0.3 | 30065 |  |  | 0.3 | 0 | 0 |  | 0%
| 908 | 5 | 6.1.2.1.1 | 이체 |  |  | 1 | 2015-02-09 | 2015-03-16 | 0.04 | 26 |  |  | 0.04 | 0 | 0 |  | 0%
| 909 | 5 | 6.1.2.1.2 | 전자결제 |  |  | 1 | 2015-02-09 | 2015-03-13 | 0.05 | 25 |  |  | 0.05 | 0 | 0 |  | 0%
| 910 | 6 | 6.1.2.1.2.1 | 판매기업 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 911 | 6 | 6.1.2.1.2.2 | 구매기업 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 912 | 6 | 6.1.2.1.2.3 | 중개기업 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 913 | 6 | 6.1.2.1.2.4 | 대행업무 |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 914 | 5 | 6.1.2.1.3 | 외국환 |  |  | 1 | 2015-02-09 | 2015-03-13 | 0.05 | 25 |  |  | 0.05 | 0 | 0 |  | 0%
| 915 | 6 | 6.1.2.1.3.1 | 외화송금 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 916 | 6 | 6.1.2.1.3.2 | 외환매매 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 917 | 6 | 6.1.2.1.3.3 | 환율/금리조회 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 918 | 6 | 6.1.2.1.3.4 | 수입 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 919 | 6 | 6.1.2.1.3.5 | 수출 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 920 | 6 | 6.1.2.1.3.6 | 수수료(수입/수출) |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 921 | 6 | 6.1.2.1.3.7 | 인터넷EDI |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 922 | 6 | 6.1.2.1.3.8 | 환리스크관리 |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 923 | 6 | 6.1.2.1.3.9 | BiCNET Global |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 924 | 6 | 6.1.2.1.3.10 | 전자무역 |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 925 | 5 | 6.1.2.1.4 | 조회 |  |  | 1 | 2015-03-08 | 2015-03-23 | 0.01 | 11 |  |  | 0.01 | 0 | 0 |  | 0%
| 926 | 5 | 6.1.2.1.5 | 신규해지 |  |  | 1 | 2015-03-08 | 2015-03-23 | 0.02 | 11 |  |  | 0.02 | 0 | 0 |  | 0%
| 927 | 5 | 6.1.2.1.6 | 대출 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.02 | 30 |  |  | 0.02 | 0 | 0 |  | 0%
| 928 | 6 | 6.1.2.1.6.1 | 대출조회 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 929 | 6 | 6.1.2.1.6.2 | 대출상환/이자납입 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 930 | 6 | 6.1.2.1.6.3 | 질권설정예정계좌등록 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 931 | 6 | 6.1.2.1.6.4 | 대출신청 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-20 |  | 10 |  |  |  | 0 | 0 |  | 0%
| 932 | 5 | 6.1.2.1.7 | 공과금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-22 | 0.01 | 30 |  |  | 0.01 | 0 | 0 |  | 0%
| 933 | 6 | 6.1.2.1.7.1 | My 공과금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 934 | 6 | 6.1.2.1.7.2 | 지로 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 935 | 6 | 6.1.2.1.7.3 | 세금 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 936 | 6 | 6.1.2.1.7.4 | 생활요금/부담금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 937 | 6 | 6.1.2.1.7.5 | 벌칙금/벌과금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 938 | 6 | 6.1.2.1.7.6 | 연금/보험금 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 939 | 6 | 6.1.2.1.7.7 | 국고및기금 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 940 | 6 | 6.1.2.1.7.8 | 예약납부 조회/취소 | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 941 | 5 | 6.1.2.1.8 | 통합자금관리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.02 | 30 |  |  | 0.02 | 0 | 0 |  | 0%
| 942 | 6 | 6.1.2.1.8.1 | 당행집금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 943 | 6 | 6.1.2.1.8.2 | 인터넷계좌통합 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 944 | 6 | 6.1.2.1.8.3 | 집금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 945 | 6 | 6.1.2.1.8.4 | 배분 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 946 | 6 | 6.1.2.1.8.5 | 법인카드 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 947 | 6 | 6.1.2.1.8.6 | 서비스환경 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 948 | 6 | 6.1.2.1.8.7 | ERP연계 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 949 | 6 | 6.1.2.1.8.8 | 가상계좌 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 950 | 6 | 6.1.2.1.8.9 | 통합집금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 951 | 6 | 6.1.2.1.8.10 | 집금대행 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 952 | 6 | 6.1.2.1.8.11 | 등록금수납관리 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 953 | 6 | 6.1.2.1.8.12 | 희망키움통장II | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 954 | 5 | 6.1.2.1.9 | 부가서비스 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.01 | 25 |  |  | 0.01 | 0 | 0 |  | 0%
| 955 | 6 | 6.1.2.1.9.1 | 급여관리서비스 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 956 | 6 | 6.1.2.1.9.2 | 전화로승인 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 957 | 6 | 6.1.2.1.9.3 | 소액계좌관리/휴면계좌정리/무통장거래정리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 958 | 6 | 6.1.2.1.9.4 | 수수료관리 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 959 | 5 | 6.1.2.1.10 | 결재함 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.01 | 25 |  |  | 0.01 | 0 | 0 |  | 0%
| 960 | 6 | 6.1.2.1.10.1 | 미결재내역 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 961 | 6 | 6.1.2.1.10.2 | 결재내역 | 현행 시스템 분석서 |  | 1 | 2015-02-16 | 2015-02-24 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 962 | 6 | 6.1.2.1.10.3 | 등록내역 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 963 | 6 | 6.1.2.1.10.4 | 거래함 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 964 | 5 | 6.1.2.1.11 | 사용자관리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.05 | 30 |  |  | 0.05 | 0 | 0 |  | 0%
| 965 | 6 | 6.1.2.1.11.1 | 내부통제 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-24 |  | 12 |  |  |  | 0 | 0 |  | 0%
| 966 | 6 | 6.1.2.1.11.2 | 결재서비스 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-13 |  | 10 |  |  |  | 0 | 0 |  | 0%
| 967 | 6 | 6.1.2.1.11.3 | 기타환경설정 | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 968 | 5 | 6.1.2.1.12 | 공인인증센터 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.01 | 25 |  |  | 0.01 | 0 | 0 |  | 0%
| 969 | 6 | 6.1.2.1.12.1 | 공인인증서 상세안내 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 970 | 6 | 6.1.2.1.12.2 | 인증서 신규/재발급 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 971 | 6 | 6.1.2.1.12.3 | 타행/타기관인증서 등록 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 972 | 6 | 6.1.2.1.12.4 | 인증서 관리 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 973 | 6 | 6.1.2.1.12.5 | 인증서 갱신/폐기 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 974 | 6 | 6.1.2.1.12.6 | 인증서 정보조회 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 975 | 6 | 6.1.2.1.12.7 | 영수증/세금계산서 발급 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 976 | 6 | 6.1.2.1.12.8 | 발급수수료 환불신청 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 977 | 6 | 6.1.2.1.12.9 | 스마트폰인증서복사 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 978 | 4 | 6.1.2.2 | 전문 GAP분석 | 현행 시스템 분석서 |  | 1 |  | 2015-03-30 | 0.9 | 30066 |  |  | 0.9 | 0 | 0 |  | 0%
| 979 | 5 | 6.1.2.2.1 | 이체 |  |  | 1 | 2015-02-09 | 2015-03-20 | 0.12 | 30 |  |  | 0.12 | 0 | 0 |  | 0%
| 980 | 6 | 6.1.2.2.1.1 | 계좌관리,이체 |  |  | 1 | 2015-02-09 | 2015-02-27 |  | 15 |  |  |  | 0 | 0 |  | 0%
| 981 | 6 | 6.1.2.2.1.2 | 대량이체외 |  |  | 1 | 2015-03-02 | 2015-03-10 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 982 | 6 | 6.1.2.2.1.3 | 이체결과 |  |  | 1 | 2015-03-10 | 2015-03-13 |  | 4 |  |  |  | 0 | 0 |  | 0%
| 983 | 6 | 6.1.2.2.1.4 | 글로벌이체 |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 984 | 5 | 6.1.2.2.2 | 전자결제 |  |  | 1 | 2015-02-09 | 2015-03-13 | 0.12 | 25 |  |  | 0.12 | 0 | 0 |  | 0%
| 985 | 6 | 6.1.2.2.2.1 | 판매기업 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 986 | 6 | 6.1.2.2.2.2 | 구매기업 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 987 | 6 | 6.1.2.2.2.3 | 중개기업 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 988 | 6 | 6.1.2.2.2.4 | 대행업무 |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 989 | 5 | 6.1.2.2.3 | 외국환 |  |  | 1 | 2015-02-09 | 2015-03-13 | 0.12 | 25 |  |  | 0.12 | 0 | 0 |  | 0%
| 990 | 6 | 6.1.2.2.3.1 | 외화송금 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 991 | 6 | 6.1.2.2.3.2 | 외환매매 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 992 | 6 | 6.1.2.2.3.3 | 환율/금리조회 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 993 | 6 | 6.1.2.2.3.4 | 수입 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 994 | 6 | 6.1.2.2.3.5 | 수출 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 995 | 6 | 6.1.2.2.3.6 | 수수료(수입/수출) |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 996 | 6 | 6.1.2.2.3.7 | 인터넷EDI |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 997 | 6 | 6.1.2.2.3.8 | 환리스크관리 |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 998 | 6 | 6.1.2.2.3.9 | BiCNET Global |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 999 | 6 | 6.1.2.2.3.10 | 전자무역 |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1000 | 5 | 6.1.2.2.4 | 조회 |  |  | 1 | 2015-02-09 | 2015-02-27 | 0.05 | 15 |  |  | 0.05 | 0 | 0 |  | 0%
| 1001 | 6 | 6.1.2.2.4.1 | 예금/펀드 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 1002 | 6 | 6.1.2.2.4.2 | 보관어음 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 1003 | 6 | 6.1.2.2.4.3 | 신용카드 |  |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 1004 | 6 | 6.1.2.2.4.4 | 주류카드 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1005 | 6 | 6.1.2.2.4.5 | 보고서 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1006 | 6 | 6.1.2.2.4.6 | CMS계좌 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1007 | 5 | 6.1.2.2.5 | 신규해지 |  |  | 1 | 2015-02-16 | 2015-03-20 | 0.06 | 25 |  |  | 0.06 | 0 | 0 |  | 0%
| 1008 | 6 | 6.1.2.2.5.1 | 예금 |  |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1009 | 6 | 6.1.2.2.5.2 | 인터넷외화예금 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1010 | 6 | 6.1.2.2.5.3 | 퇴직연금 |  |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1011 | 6 | 6.1.2.2.5.4 | 펀드 |  |  | 1 | 2015-03-09 | 2015-03-13 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1012 | 6 | 6.1.2.2.5.5 | 특정금전신탁 |  |  | 1 | 2015-03-16 | 2015-03-20 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1013 | 5 | 6.1.2.2.6 | 대출 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.06 | 30 |  |  | 0.06 | 0 | 0 |  | 0%
| 1014 | 6 | 6.1.2.2.6.1 | 대출조회 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 1015 | 6 | 6.1.2.2.6.2 | 대출상환/이자납입 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1016 | 6 | 6.1.2.2.6.3 | 질권설정예정계좌등록 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1017 | 6 | 6.1.2.2.6.4 | 대출신청 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-20 |  | 10 |  |  |  | 0 | 0 |  | 0%
| 1018 | 5 | 6.1.2.2.7 | 공과금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-22 | 0.04 | 30 |  |  | 0.04 | 0 | 0 |  | 0%
| 1019 | 6 | 6.1.2.2.7.1 | My 공과금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17 |  | 7 |  |  |  | 0 | 0 |  | 0%
| 1020 | 6 | 6.1.2.2.7.2 | 지로 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27 |  | 5 |  |  |  | 0 | 0 |  | 0%
| 1021 | 6 | 6.1.2.2.7.3 | 세금 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1022 | 6 | 6.1.2.2.7.4 | 생활요금/부담금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1023 | 6 | 6.1.2.2.7.5 | 벌칙금/벌과금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1024 | 6 | 6.1.2.2.7.6 | 연금/보험금 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1025 | 6 | 6.1.2.2.7.7 | 국고및기금 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1026 | 6 | 6.1.2.2.7.8 | 예약납부 조회/취소 | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20
| 1027 | 5 | 6.1.2.2.8 | 통합자금관리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.06 | 30 |  |  | 0.06
| 1028 | 6 | 6.1.2.2.8.1 | 당행집금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1029 | 6 | 6.1.2.2.8.2 | 인터넷계좌통합 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1030 | 6 | 6.1.2.2.8.3 | 집금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1031 | 6 | 6.1.2.2.8.4 | 배분 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1032 | 6 | 6.1.2.2.8.5 | 법인카드 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1033 | 6 | 6.1.2.2.8.6 | 서비스환경 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1034 | 6 | 6.1.2.2.8.7 | ERP연계 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1035 | 6 | 6.1.2.2.8.8 | 가상계좌 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1036 | 6 | 6.1.2.2.8.9 | 통합집금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1037 | 6 | 6.1.2.2.8.10 | 집금대행 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1038 | 6 | 6.1.2.2.8.11 | 등록금수납관리 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1039 | 6 | 6.1.2.2.8.12 | 희망키움통장II | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20
| 1040 | 5 | 6.1.2.2.9 | 부가서비스 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.06 | 25 |  |  | 0.06
| 1041 | 6 | 6.1.2.2.9.1 | 급여관리서비스 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1042 | 6 | 6.1.2.2.9.2 | 전화로승인 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1043 | 6 | 6.1.2.2.9.3 | 소액계좌관리/휴면계좌정리/무통장거래정리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-13
| 1044 | 6 | 6.1.2.2.9.4 | 수수료관리 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1045 | 5 | 6.1.2.2.10 | 결재함 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.02 | 25 |  |  | 0.02
| 1046 | 6 | 6.1.2.2.10.1 | 미결재내역 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1047 | 6 | 6.1.2.2.10.2 | 결재내역 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1048 | 6 | 6.1.2.2.10.3 | 등록내역 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1049 | 6 | 6.1.2.2.10.4 | 거래함 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-17
| 1050 | 5 | 6.1.2.2.11 | 사용자관리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.09 | 30 |  |  | 0.09
| 1051 | 6 | 6.1.2.2.11.1 | 내부통제 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-27
| 1052 | 6 | 6.1.2.2.11.2 | 결재서비스 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-13
| 1053 | 6 | 6.1.2.2.11.3 | 기타환경설정 | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20
| 1054 | 5 | 6.1.2.2.12 | 공인인증센터 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.02 | 25 |  |  | 0.02
| 1055 | 6 | 6.1.2.2.12.1 | 공인인증서 상세안내 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1056 | 6 | 6.1.2.2.12.2 | 인증서 신규/재발급 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1057 | 6 | 6.1.2.2.12.3 | 타행/타기관인증서 등록 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1058 | 6 | 6.1.2.2.12.4 | 인증서 관리 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1059 | 6 | 6.1.2.2.12.5 | 인증서 갱신/폐기 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1060 | 6 | 6.1.2.2.12.6 | 인증서 정보조회 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1061 | 6 | 6.1.2.2.12.7 | 영수증/세금계산서 발급 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1062 | 6 | 6.1.2.2.12.8 | 발급수수료 환불신청 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1063 | 6 | 6.1.2.2.12.9 | 스마트폰인증서복사 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1064 | 5 | 6.1.2.2.13 | 배치/관리자 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.08 | 25 |  |  | 0.08
| 1065 | 6 | 6.1.2.2.13.1 | 배치 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-24
| 1066 | 6 | 6.1.2.2.13.2 | 관리자 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-13
| 1067 | 4 | 6.1.2.3 | 테이블/속성 GAP분석 | 현행 시스템 분석서 |  | 1 |  | 2015-04-01 | #REF! | 30068 |  |  | #REF!
| 1068 | 5 | 6.1.2.3.1 | 이체 |  |  | 1 | 2015-02-09 | 2015-03-20 | 0.06 | 30 |  |  | 0.06
| 1069 | 6 | 6.1.2.3.1.1 | 계좌관리,이체 |  |  | 1 | 2015-02-09 | 2015-02-27
| 1070 | 6 | 6.1.2.3.1.2 | 대량이체외 |  |  | 1 | 2015-03-02 | 2015-03-10
| 1071 | 6 | 6.1.2.3.1.3 | 이체결과 |  |  | 1 | 2015-03-10 | 2015-03-13
| 1072 | 6 | 6.1.2.3.1.4 | 글로벌이체 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1073 | 5 | 6.1.2.3.2 | 전자결제 |  |  | 1 | 2015-02-09 | 2015-03-13 | 0.07 | 25 |  |  | 0.07
| 1074 | 6 | 6.1.2.3.2.1 | 판매기업 |  |  | 1 | 2015-02-09 | 2015-02-17
| 1075 | 6 | 6.1.2.3.2.2 | 구매기업 |  |  | 1 | 2015-02-23 | 2015-02-27
| 1076 | 6 | 6.1.2.3.2.3 | 중개기업 |  |  | 1 | 2015-03-02 | 2015-03-06
| 1077 | 6 | 6.1.2.3.2.4 | 대행업무 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1078 | 5 | 6.1.2.3.3 | 외국환 |  |  | 1 | 2015-02-09 | 2015-03-13 | 0.09 | 25 |  |  | 0.09
| 1079 | 6 | 6.1.2.3.3.1 | 외화송금 |  |  | 1 | 2015-02-09 | 2015-02-17
| 1080 | 6 | 6.1.2.3.3.2 | 외환매매 |  |  | 1 | 2015-02-09 | 2015-02-17
| 1081 | 6 | 6.1.2.3.3.3 | 환율/금리조회 |  |  | 1 | 2015-02-23 | 2015-02-27
| 1082 | 6 | 6.1.2.3.3.4 | 수입 |  |  | 1 | 2015-02-23 | 2015-02-27
| 1083 | 6 | 6.1.2.3.3.5 | 수출 |  |  | 1 | 2015-03-02 | 2015-03-06
| 1084 | 6 | 6.1.2.3.3.6 | 수수료(수입/수출) |  |  | 1 | 2015-03-02 | 2015-03-06
| 1085 | 6 | 6.1.2.3.3.7 | 인터넷EDI |  |  | 1 | 2015-03-09 | 2015-03-13
| 1086 | 6 | 6.1.2.3.3.8 | 환리스크관리 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1087 | 6 | 6.1.2.3.3.9 | BiCNET Global |  |  | 1 | 2015-03-16 | 2015-03-20
| 1088 | 6 | 6.1.2.3.3.10 | 전자무역 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1089 | 5 | 6.1.2.3.4 | 조회 |  |  | 1 | 2015-02-09 | 2015-02-27 | 0.01 | 15 |  |  | 0.01
| 1090 | 6 | 6.1.2.3.4.1 | 예금/펀드 |  |  | 1 | 2015-02-09 | 2015-02-17
| 1091 | 6 | 6.1.2.3.4.2 | 보관어음 |  |  | 1 | 2015-02-09 | 2015-02-17
| 1092 | 6 | 6.1.2.3.4.3 | 신용카드 |  |  | 1 | 2015-02-09 | 2015-02-17
| 1093 | 6 | 6.1.2.3.4.4 | 주류카드 |  |  | 1 | 2015-02-23 | 2015-02-27
| 1094 | 6 | 6.1.2.3.4.5 | 보고서 |  |  | 1 | 2015-02-23 | 2015-02-27
| 1095 | 6 | 6.1.2.3.4.6 | CMS계좌 |  |  | 1 | 2015-02-23 | 2015-02-27
| 1096 | 5 | 6.1.2.3.5 | 신규해지 |  |  | 1 | 2015-02-16 | 2015-03-20 | 0.04 | 25 |  |  | 0.04
| 1097 | 6 | 6.1.2.3.5.1 | 예금 |  |  | 1 | 2015-02-23 | 2015-02-27
| 1098 | 6 | 6.1.2.3.5.2 | 인터넷외화예금 |  |  | 1 | 2015-03-02 | 2015-03-06
| 1099 | 6 | 6.1.2.3.5.3 | 퇴직연금 |  |  | 1 | 2015-03-02 | 2015-03-06
| 1100 | 6 | 6.1.2.3.5.4 | 펀드 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1101 | 6 | 6.1.2.3.5.5 | 특정금전신탁 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1102 | 5 | 6.1.2.3.6 | 대출 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.03 | 30 |  |  | 0.03
| 1103 | 6 | 6.1.2.3.6.1 | 대출조회 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1104 | 6 | 6.1.2.3.6.2 | 대출상환/이자납입 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1105 | 6 | 6.1.2.3.6.3 | 질권설정예정계좌등록 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1106 | 6 | 6.1.2.3.6.4 | 대출신청 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-20
| 1107 | 5 | 6.1.2.3.7 | 공과금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-22 | 0.03 | 30 |  |  | 0.03
| 1108 | 6 | 6.1.2.3.7.1 | My 공과금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1109 | 6 | 6.1.2.3.7.2 | 지로 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1110 | 6 | 6.1.2.3.7.3 | 세금 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1111 | 6 | 6.1.2.3.7.4 | 생활요금/부담금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1112 | 6 | 6.1.2.3.7.5 | 벌칙금/벌과금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1113 | 6 | 6.1.2.3.7.6 | 연금/보험금 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1114 | 6 | 6.1.2.3.7.7 | 국고및기금 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1115 | 6 | 6.1.2.3.7.8 | 예약납부 조회/취소 | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20
| 1116 | 5 | 6.1.2.3.8 | 통합자금관리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.06 | 30 |  |  | 0.06
| 1117 | 6 | 6.1.2.3.8.1 | 당행집금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1118 | 6 | 6.1.2.3.8.2 | 인터넷계좌통합 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1119 | 6 | 6.1.2.3.8.3 | 집금 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1120 | 6 | 6.1.2.3.8.4 | 배분 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1121 | 6 | 6.1.2.3.8.5 | 법인카드 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1122 | 6 | 6.1.2.3.8.6 | 서비스환경 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1123 | 6 | 6.1.2.3.8.7 | ERP연계 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1124 | 6 | 6.1.2.3.8.8 | 가상계좌 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1125 | 6 | 6.1.2.3.8.9 | 통합집금 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1126 | 6 | 6.1.2.3.8.10 | 집금대행 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1127 | 6 | 6.1.2.3.8.11 | 등록금수납관리 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1128 | 6 | 6.1.2.3.8.12 | 희망키움통장II | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20
| 1129 | 5 | 6.1.2.3.9 | 부가서비스 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.02 | 25 |  |  | 0.02
| 1130 | 6 | 6.1.2.3.9.1 | 급여관리서비스 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1131 | 6 | 6.1.2.3.9.2 | 전화로승인 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1132 | 6 | 6.1.2.3.9.3 | 소액계좌관리/휴면계좌정리/무통장거래정리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-13
| 1133 | 6 | 6.1.2.3.9.4 | 수수료관리 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1134 | 5 | 6.1.2.3.10 | 결재함 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.04 | 25 |  |  | 0.04
| 1135 | 6 | 6.1.2.3.10.1 | 미결재내역 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-13
| 1136 | 6 | 6.1.2.3.10.2 | 결재내역 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1137 | 6 | 6.1.2.3.10.3 | 등록내역 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1138 | 6 | 6.1.2.3.10.4 | 거래함 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1139 | 5 | 6.1.2.3.11 | 사용자관리 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-20 | 0.1 | 30 |  |  | 0.1
| 1140 | 6 | 6.1.2.3.11.1 | 내부통제 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-27
| 1141 | 6 | 6.1.2.3.11.2 | 결재서비스 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-13
| 1142 | 6 | 6.1.2.3.11.3 | 기타환경설정 | 현행 시스템 분석서 |  | 1 | 2015-03-16 | 2015-03-20
| 1143 | 5 | 6.1.2.3.12 | 공인인증센터 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.01 | 25 |  |  | 0.01
| 1144 | 6 | 6.1.2.3.12.1 | 공인인증서 상세안내 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1145 | 6 | 6.1.2.3.12.2 | 인증서 신규/재발급 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-17
| 1146 | 6 | 6.1.2.3.12.3 | 타행/타기관인증서 등록 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1147 | 6 | 6.1.2.3.12.4 | 인증서 관리 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1148 | 6 | 6.1.2.3.12.5 | 인증서 갱신/폐기 | 현행 시스템 분석서 |  | 1 | 2015-02-23 | 2015-02-27
| 1149 | 6 | 6.1.2.3.12.6 | 인증서 정보조회 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1150 | 6 | 6.1.2.3.12.7 | 영수증/세금계산서 발급 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-06
| 1151 | 6 | 6.1.2.3.12.8 | 발급수수료 환불신청 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1152 | 6 | 6.1.2.3.12.9 | 스마트폰인증서복사 | 현행 시스템 분석서 |  | 1 | 2015-03-09 | 2015-03-13
| 1153 | 5 | 6.1.2.3.13 | 배치/관리자 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-03-13 | 0.04 | 25 |  |  | 0.04
| 1154 | 6 | 6.1.2.3.13.1 | 배치 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-24
| 1155 | 6 | 6.1.2.3.13.2 | 관리자 | 현행 시스템 분석서 |  | 1 | 2015-03-02 | 2015-03-13
| 1156 | 3 | 6.1.3 | 통합업무확정 |  |  | 1 |  | 2015-04-03 | 0.5 | 0.5 |  |  | 0.5
| 1157 | 4 | 6.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 |  | 1 |  | 2015-04-05 | 0.5 | 30070 |  |  | 0.5
| 1158 | 5 | 6.1.3.1.1 | 이체 |  |  | 1 | 2015-03-09 | 2015-03-16 | 0.06 | 6 |  |  | 0.06
| 1159 | 5 | 6.1.3.1.2 | 전자결제 |  |  | 1 | 2015-03-09 | 2015-03-16 | 0.07 | 6 |  |  | 0.07
| 1160 | 5 | 6.1.3.1.3 | 외국환 |  |  | 1 | 2015-03-09 | 2015-03-20 | 0.08 | 10 |  |  | 0.08
| 1161 | 5 | 6.1.3.1.4 | 조회 |  |  | 1 | 2015-03-09 | 2015-03-16 | 0.02 | 6 |  |  | 0.02
| 1162 | 5 | 6.1.3.1.5 | 신규해지 |  |  | 1 | 2015-03-09 | 2015-03-16 | 0.04 | 6 |  |  | 0.04
| 1163 | 5 | 6.1.3.1.6 | 대출 | 통합메뉴구조도 |  | 1 | 2015-03-09 | 2015-03-20 | 0.03 | 10 |  |  | 0.03
| 1164 | 5 | 6.1.3.1.7 | 공과금 | 통합메뉴구조도 |  | 1 | 2015-03-09 | 2015-03-20 | 0.02 | 10 |  |  | 0.02
| 1165 | 5 | 6.1.3.1.8 | 통합자금관리 | 통합메뉴구조도 |  | 1 | 2015-03-09 | 2015-03-20 | 0.04 | 10 |  |  | 0.04
| 1166 | 5 | 6.1.3.1.9 | 부가서비스 | 통합메뉴구조도 |  | 1 | 2015-03-09 | 2015-03-20 | 0.03 | 10 |  |  | 0.03
| 1167 | 5 | 6.1.3.1.10 | 결재함 | 통합메뉴구조도 |  | 1 | 2015-03-09 | 2015-03-20 | 0.01 | 10 |  |  | 0.01
| 1168 | 5 | 6.1.3.1.11 | 사용자관리 | 통합메뉴구조도 |  | 1 | 2015-03-09 | 2015-03-20 | 0.09 | 10 |  |  | 0.09
| 1169 | 5 | 6.1.3.1.12 | 공인인증센터 | 통합메뉴구조도 |  | 1 | 2015-03-09 | 2015-03-20 | 0.01 | 10 |  |  | 0.01
| 1170 | 3 | 6.1.4 | 통합요건정의 |  |  | 1 |  | 2015-04-07 | 0.7 | 0.7 |  |  | 0.7
| 1171 | 4 | 6.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 |  | 1 |  | 2015-04-09 | 0.7 | 30074 |  |  | 0.7
| 1172 | 5 | 6.1.4.1.1 | 이체 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.08 | 15 |  |  | 0.08
| 1173 | 5 | 6.1.4.1.2 | 전자결제 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.1 | 15 |  |  | 0.1
| 1174 | 5 | 6.1.4.1.3 | 외국환 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.1 | 15 |  |  | 0.1
| 1175 | 5 | 6.1.4.1.4 | 조회 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.03 | 15 |  |  | 0.03
| 1176 | 5 | 6.1.4.1.5 | 신규해지 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.05 | 15 |  |  | 0.05
| 1177 | 5 | 6.1.4.1.6 | 대출 | 요구사항정의서 요구사항추적표 |  | 1 | 2015-03-02 | 2015-03-20 | 0.05 | 15 |  |  | 0.05
| 1178 | 5 | 6.1.4.1.7 | 공과금 | 요구사항정의서 요구사항추적표 |  | 1 | 2015-03-02 | 2015-03-20 | 0.03 | 15 |  |  | 0.03
| 1179 | 5 | 6.1.4.1.8 | 통합자금관리 | 요구사항정의서 요구사항추적표 |  | 1 | 2015-03-02 | 2015-03-20 | 0.07 | 15 |  |  | 0.07
| 1180 | 5 | 6.1.4.1.9 | 부가서비스 | 요구사항정의서 요구사항추적표 |  | 1 | 2015-03-02 | 2015-03-20 | 0.04 | 15 |  |  | 0.04
| 1181 | 5 | 6.1.4.1.10 | 결재함 | 요구사항정의서 요구사항추적표 |  | 1 | 2015-03-02 | 2015-03-20 | 0.02 | 15 |  |  | 0.02
| 1182 | 5 | 6.1.4.1.11 | 사용자관리 | 요구사항정의서 요구사항추적표 |  | 1 | 2015-03-02 | 2015-03-20 | 0.1 | 15 |  |  | 0.1
| 1183 | 5 | 6.1.4.1.12 | 공인인증센터 | 요구사항정의서 요구사항추적표 |  | 1 | 2015-03-02 | 2015-03-20 | 0.03 | 15 |  |  | 0.03
| 1184 | 3 | 6.1.5 | 논리모델구축 |  |  | 1 |  | 2015-04-11 | 1 | 1 |  |  | 1
| 1185 | 4 | 6.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 |  | 1 |  | 2015-04-13 | 1 | 30076 |  |  | 1
| 1186 | 5 | 6.1.5.1.1 | 이체 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.1 | 15 |  |  | 0.1
| 1187 | 5 | 6.1.5.1.2 | 전자결제 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.13 | 15 |  |  | 0.13
| 1188 | 5 | 6.1.5.1.3 | 외국환 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.14 | 15 |  |  | 0.14
| 1189 | 5 | 6.1.5.1.4 | 조회 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.03 | 15 |  |  | 0.03
| 1190 | 5 | 6.1.5.1.5 | 신규해지 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.07 | 15 |  |  | 0.07
| 1191 | 5 | 6.1.5.1.6 | 대출 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-03-20 | 0.07 | 15 |  |  | 0.07
| 1192 | 5 | 6.1.5.1.7 | 공과금 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-03-20 | 0.05 | 15 |  |  | 0.05
| 1193 | 5 | 6.1.5.1.8 | 통합자금관리 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-03-20 | 0.07 | 15 |  |  | 0.07
| 1194 | 5 | 6.1.5.1.9 | 부가서비스 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-03-20 | 0.06 | 15 |  |  | 0.06
| 1195 | 5 | 6.1.5.1.10 | 결재함 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-03-20 | 0.04 | 15 |  |  | 0.04
| 1196 | 5 | 6.1.5.1.11 | 사용자관리 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-03-20 | 0.2 | 15 |  |  | 0.2
| 1197 | 5 | 6.1.5.1.12 | 공인인증센터 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-03-20 | 0.04 | 15 |  |  | 0.04
| 1198 | 2 | 6.2 | 설계 |  |  | 1 | 2015-02-25 | 2015-04-24 | #REF! | 5 |  |  | #REF!
| 1199 | 3 | 6.2.1 | 통합온라인 프로세스 설계 |  |  | 1 |  | 2015-04-26 | #REF! | 1.4 |  |  | #REF!
| 1200 | 4 | 6.2.1.1 | 화면설계 | 화면설계서 |  | 1 |  | 2015-04-28 | #REF! | 30087 |  |  | #REF!
| 1201 | 5 | 6.2.1.1.1 | 이체 |  |  | 1 | 2015-02-25 | 2015-04-24 | 0.08 | 43 |  |  | 0.08
| 1202 | 6 | 6.2.1.1.1.1 | 계좌관리,이체 |  |  | 1 | 2015-03-02 | 2015-03-20
| 1203 | 6 | 6.2.1.1.1.2 | 대량이체외 |  |  | 1 | 2015-03-23 | 2015-04-03
| 1204 | 6 | 6.2.1.1.1.3 | 이체결과 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1205 | 6 | 6.2.1.1.1.4 | 글로벌이체 |  |  | 1 | 2015-04-13 | 2015-04-24
| 1206 | 5 | 6.2.1.1.2 | 전자결제 |  |  | 1 | 2015-02-23 | 2015-04-17 | 0.08 | 40 |  |  | 0.08
| 1207 | 5 | 6.2.1.1.3 | 외국환 |  |  | 1 | 2015-02-25 | 2015-04-17 | 0.1 | 38 |  |  | 0.1
| 1208 | 6 | 6.2.1.1.3.1 | 외화송금 |  |  | 1 | 2015-02-25 | 2015-03-06
| 1209 | 6 | 6.2.1.1.3.2 | 외환매매 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1210 | 6 | 6.2.1.1.3.3 | 환율/금리조회 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1211 | 6 | 6.2.1.1.3.4 | 수입 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1212 | 6 | 6.2.1.1.3.5 | 수출 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1213 | 6 | 6.2.1.1.3.6 | 수수료(수입/수출) |  |  | 1 | 2015-03-30 | 2015-04-03
| 1214 | 6 | 6.2.1.1.3.7 | 인터넷EDI |  |  | 1 | 2015-03-30 | 2015-04-03
| 1215 | 6 | 6.2.1.1.3.8 | 환리스크관리 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1216 | 6 | 6.2.1.1.3.9 | BiCNET Global |  |  | 1 | 2015-04-06 | 2015-04-10
| 1217 | 6 | 6.2.1.1.3.10 | 전자무역 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1218 | 5 | 6.2.1.1.4 | 조회 |  |  | 1 | 2015-03-02 | 2015-04-03 | 0.01 | 25 |  |  | 0.01
| 1219 | 6 | 6.2.1.1.4.1 | 예금/펀드 |  |  | 1 | 2015-03-02 | 2015-03-13
| 1220 | 6 | 6.2.1.1.4.2 | 보관어음 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1221 | 6 | 6.2.1.1.4.3 | 신용카드 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1222 | 6 | 6.2.1.1.4.4 | 주류카드 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1223 | 6 | 6.2.1.1.4.5 | 보고서 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1224 | 6 | 6.2.1.1.4.6 | CMS계좌 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1225 | 5 | 6.2.1.1.5 | 신규해지 |  |  | 1 | 2015-04-06 | 2015-04-24 | 0.02 | 15 |  |  | 0.02
| 1226 | 6 | 6.2.1.1.5.1 | 예금 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1227 | 6 | 6.2.1.1.5.2 | 인터넷외화예금 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1228 | 6 | 6.2.1.1.5.3 | 퇴직연금 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1229 | 6 | 6.2.1.1.5.4 | 펀드 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1230 | 6 | 6.2.1.1.5.5 | 특정금전신탁 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1231 | 5 | 6.2.1.1.6 | 대출 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-04-03 | 0.02 | 25 |  |  | 0.02
| 1232 | 5 | 6.2.1.1.7 | 공과금 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-04-03 | 0.01 | 25 |  |  | 0.01
| 1233 | 5 | 6.2.1.1.8 | 통합자금관리 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-04-03 | 0.02 | 25 |  |  | 0.02
| 1234 | 5 | 6.2.1.1.9 | 부가서비스 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-04-03 | 0.02 | 25 |  |  | 0.02
| 1235 | 5 | 6.2.1.1.10 | 결재함 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-04-03 | 0.03 | 25 |  |  | 0.03
| 1236 | 5 | 6.2.1.1.11 | 사용자관리 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-04-03 | 0.1 | 25 |  |  | 0.1
| 1237 | 5 | 6.2.1.1.12 | 공인인증센터 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-04-03 | 0.01 | 25 |  |  | 0.01
| 1238 | 4 | 6.2.1.2 | 프로그램 설계 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-05-01 | 1.1 | 45 |  |  | 1.1
| 1239 | 5 | 6.2.1.2.1 | 이체 |  |  | 1 | 2015-03-09 | 2015-05-01 | 0.12 | 40 |  |  | 0.12
| 1240 | 6 | 6.2.1.2.1.1 | 계좌관리,이체 |  |  | 1 | 2015-03-09 | 2015-03-27
| 1241 | 6 | 6.2.1.2.1.2 | 대량이체외 |  |  | 1 | 2015-03-30 | 2015-04-10
| 1242 | 6 | 6.2.1.2.1.3 | 이체결과 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1243 | 6 | 6.2.1.2.1.4 | 글로벌이체 |  |  | 1 | 2015-04-20 | 2015-05-01
| 1244 | 5 | 6.2.1.2.2 | 전자결제 |  |  | 1 | 2015-03-02 | 2015-05-01 | 0.14 | 45 |  |  | 0.14
| 1245 | 6 | 6.2.1.2.2.1 | 판매기업 |  |  | 1 | 2015-03-02 | 2015-03-20
| 1246 | 6 | 6.2.1.2.2.2 | 구매기업 |  |  | 1 | 2015-03-23 | 2015-04-03
| 1247 | 6 | 6.2.1.2.2.3 | 중개기업 |  |  | 1 | 2015-04-13 | 2015-04-24
| 1248 | 6 | 6.2.1.2.2.4 | 대행업무 |  |  | 1 | 2015-04-20 | 2015-05-01
| 1249 | 5 | 6.2.1.2.3 | 외국환 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.16 | 40 |  |  | 0.16
| 1250 | 6 | 6.2.1.2.3.1 | 외화송금 |  |  | 1 | 2015-03-02 | 2015-03-13
| 1251 | 6 | 6.2.1.2.3.2 | 외환매매 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1252 | 6 | 6.2.1.2.3.3 | 환율/금리조회 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1253 | 6 | 6.2.1.2.3.4 | 수입 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1254 | 6 | 6.2.1.2.3.5 | 수출 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1255 | 6 | 6.2.1.2.3.6 | 수수료(수입/수출) |  |  | 1 | 2015-04-06 | 2015-04-10
| 1256 | 6 | 6.2.1.2.3.7 | 인터넷EDI |  |  | 1 | 2015-04-06 | 2015-04-10
| 1257 | 6 | 6.2.1.2.3.8 | 환리스크관리 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1258 | 6 | 6.2.1.2.3.9 | BiCNET Global |  |  | 1 | 2015-04-13 | 2015-04-17
| 1259 | 6 | 6.2.1.2.3.10 | 전자무역 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1260 | 5 | 6.2.1.2.4 | 조회 |  |  | 1 | 2015-03-02 | 2015-04-03 | 0.03 | 25 |  |  | 0.03
| 1261 | 6 | 6.2.1.2.4.1 | 예금/펀드 |  |  | 1 | 2015-03-02 | 2015-03-06
| 1262 | 6 | 6.2.1.2.4.2 | 보관어음 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1263 | 6 | 6.2.1.2.4.3 | 신용카드 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1264 | 6 | 6.2.1.2.4.4 | 주류카드 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1265 | 6 | 6.2.1.2.4.5 | 보고서 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1266 | 6 | 6.2.1.2.4.6 | CMS계좌 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1267 | 5 | 6.2.1.2.5 | 신규해지 |  |  | 1 | 2015-03-30 | 2015-04-03 | 0.06 | 5 |  |  | 0.06
| 1268 | 6 | 6.2.1.2.5.1 | 예금 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1269 | 6 | 6.2.1.2.5.2 | 인터넷외화예금 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1270 | 6 | 6.2.1.2.5.3 | 퇴직연금 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1271 | 6 | 6.2.1.2.5.4 | 펀드 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1272 | 6 | 6.2.1.2.5.5 | 특정금전신탁 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1273 | 5 | 6.2.1.2.6 | 대출 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-05-01 | 0.06 | 45 |  |  | 0.06
| 1274 | 6 | 6.2.1.2.6.1 | 대출조회 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1275 | 6 | 6.2.1.2.6.2 | 대출상환/이자납입 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1276 | 6 | 6.2.1.2.6.3 | 질권설정예정계좌등록 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1277 | 6 | 6.2.1.2.6.4 | 대출신청 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-05-01
| 1278 | 5 | 6.2.1.2.7 | 공과금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-05-01 | 0.04 | 45 |  |  | 0.04
| 1279 | 6 | 6.2.1.2.7.1 | My 공과금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1280 | 6 | 6.2.1.2.7.2 | 지로 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1281 | 6 | 6.2.1.2.7.3 | 세금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1282 | 6 | 6.2.1.2.7.4 | 생활요금/부담금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1283 | 6 | 6.2.1.2.7.5 | 벌칙금/벌과금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1284 | 6 | 6.2.1.2.7.6 | 연금/보험금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1285 | 6 | 6.2.1.2.7.7 | 국고및기금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-27 | 2015-05-01
| 1286 | 6 | 6.2.1.2.7.8 | 예약납부 조회/취소 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-27 | 2015-05-01
| 1287 | 5 | 6.2.1.2.8 | 통합자금관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-05-01 | 0.08 | 45 |  |  | 0.08
| 1288 | 6 | 6.2.1.2.8.1 | 당행집금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1289 | 6 | 6.2.1.2.8.2 | 인터넷계좌통합 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1290 | 6 | 6.2.1.2.8.3 | 집금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1291 | 6 | 6.2.1.2.8.4 | 배분 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1292 | 6 | 6.2.1.2.8.5 | 법인카드 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1293 | 6 | 6.2.1.2.8.6 | 서비스환경 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1294 | 6 | 6.2.1.2.8.7 | ERP연계 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1295 | 6 | 6.2.1.2.8.8 | 가상계좌 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1296 | 6 | 6.2.1.2.8.9 | 통합집금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1297 | 6 | 6.2.1.2.8.10 | 집금대행 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1298 | 6 | 6.2.1.2.8.11 | 등록금수납관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-27 | 2015-05-01
| 1299 | 6 | 6.2.1.2.8.12 | 희망키움통장II | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-27 | 2015-05-01
| 1300 | 5 | 6.2.1.2.9 | 부가서비스 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-24 | 0.05 | 40 |  |  | 0.05
| 1301 | 6 | 6.2.1.2.9.1 | 급여관리서비스 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1302 | 6 | 6.2.1.2.9.2 | 전화로승인 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1303 | 6 | 6.2.1.2.9.3 | 소액계좌관리/휴면계좌정리/무통장거래정리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1304 | 6 | 6.2.1.2.9.4 | 수수료관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1305 | 5 | 6.2.1.2.10 | 결재함 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-24 | 0.02 | 40 |  |  | 0.02
| 1306 | 6 | 6.2.1.2.10.1 | 미결재내역 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1307 | 6 | 6.2.1.2.10.2 | 결재내역 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1308 | 6 | 6.2.1.2.10.3 | 등록내역 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1309 | 6 | 6.2.1.2.10.4 | 거래함 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1310 | 5 | 6.2.1.2.11 | 사용자관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-05-01 | 0.2 | 45 |  |  | 0.2
| 1311 | 6 | 6.2.1.2.11.1 | 내부통제 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-20
| 1312 | 6 | 6.2.1.2.11.2 | 결재서비스 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-23 | 2015-04-10
| 1313 | 6 | 6.2.1.2.11.3 | 기타환경설정 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1314 | 6 | 6.2.1.2.11.4 | 환경설정마법사 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-27 | 2015-05-01
| 1315 | 5 | 6.2.1.2.12 | 공인인증센터 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-05-01 | 0.05 | 45 |  |  | 0.05
| 1316 | 6 | 6.2.1.2.12.1 | 공인인증서 상세안내 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1317 | 6 | 6.2.1.2.12.2 | 인증서 신규/재발급 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1318 | 6 | 6.2.1.2.12.3 | 타행/타기관인증서 등록 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1319 | 6 | 6.2.1.2.12.4 | 인증서 관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1320 | 6 | 6.2.1.2.12.5 | 인증서 갱신/폐기 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1321 | 6 | 6.2.1.2.12.6 | 인증서 정보조회 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1322 | 6 | 6.2.1.2.12.7 | 영수증/세금계산서 발급 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-17
| 1323 | 6 | 6.2.1.2.12.8 | 발급수수료 환불신청 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-20 | 2015-04-24
| 1324 | 6 | 6.2.1.2.12.9 | 스마트폰인증서복사 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-27 | 2015-05-01
| 1325 | 5 | 6.2.1.2.13 | 배치/관리자 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-05-01 | 0.09 | 45 |  |  | 0.09
| 1326 | 6 | 6.2.1.2.13.1 | 배치 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-03
| 1327 | 6 | 6.2.1.2.13.2 | 관리자 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-24
| 1328 | 3 | 6.2.2 | 통합전문설계 |  |  | 1 |  | 2015-04-30 | 1.3 | 1.5 |  |  | 1.3
| 1329 | 4 | 6.2.2.1 | 전문매핑 | 전문목록 전문매핑정의서 |  | 1 |  | 2015-05-02 | 1.3 | 30090 |  |  | 1.3
| 1330 | 5 | 6.2.2.1.1 | 이체 |  |  | 1 | 2015-02-25 | 2015-04-24 | 0.15 | 43 |  |  | 0.15
| 1331 | 6 | 6.2.2.1.1.1 | 계좌관리,이체 |  |  | 1 | 2015-03-02 | 2015-03-20
| 1332 | 6 | 6.2.2.1.1.2 | 대량이체외 |  |  | 1 | 2015-03-23 | 2015-04-03
| 1333 | 6 | 6.2.2.1.1.3 | 이체결과 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1334 | 6 | 6.2.2.1.1.4 | 글로벌이체 |  |  | 1 | 2015-04-13 | 2015-04-24
| 1335 | 5 | 6.2.2.1.2 | 전자결제 |  |  | 1 | 2015-02-25 | 2015-04-24 | 0.2 | 43 |  |  | 0.2
| 1336 | 6 | 6.2.2.1.2.1 | 판매기업 |  |  | 1 | 2015-02-25 | 2015-03-13
| 1337 | 6 | 6.2.2.1.2.2 | 구매기업 |  |  | 1 | 2015-03-16 | 2015-03-27
| 1338 | 6 | 6.2.2.1.2.3 | 중개기업 |  |  | 1 | 2015-04-06 | 2015-04-17
| 1339 | 6 | 6.2.2.1.2.4 | 대행업무 |  |  | 1 | 2015-04-13 | 2015-04-24
| 1340 | 5 | 6.2.2.1.3 | 외국환 |  |  | 1 | 2015-02-25 | 2015-04-17 | 0.2 | 38 |  |  | 0.2
| 1341 | 6 | 6.2.2.1.3.1 | 외화송금 |  |  | 1 | 2015-02-25 | 2015-03-06
| 1342 | 6 | 6.2.2.1.3.2 | 외환매매 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1343 | 6 | 6.2.2.1.3.3 | 환율/금리조회 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1344 | 6 | 6.2.2.1.3.4 | 수입 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1345 | 6 | 6.2.2.1.3.5 | 수출 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1346 | 6 | 6.2.2.1.3.6 | 수수료(수입/수출) |  |  | 1 | 2015-03-30 | 2015-04-03
| 1347 | 6 | 6.2.2.1.3.7 | 인터넷EDI |  |  | 1 | 2015-03-30 | 2015-04-03
| 1348 | 6 | 6.2.2.1.3.8 | 환리스크관리 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1349 | 6 | 6.2.2.1.3.9 | BiCNET Global |  |  | 1 | 2015-04-06 | 2015-04-10
| 1350 | 6 | 6.2.2.1.3.10 | 전자무역 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1351 | 5 | 6.2.2.1.4 | 조회 |  |  | 1 | 2015-03-02 | 2015-04-03 | 0.06 | 25 |  |  | 0.06
| 1352 | 6 | 6.2.2.1.4.1 | 예금/펀드 |  |  | 1 | 2015-03-02 | 2015-03-13
| 1353 | 6 | 6.2.2.1.4.2 | 보관어음 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1354 | 6 | 6.2.2.1.4.3 | 신용카드 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1355 | 6 | 6.2.2.1.4.4 | 주류카드 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1356 | 6 | 6.2.2.1.4.5 | 보고서 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1357 | 6 | 6.2.2.1.4.6 | CMS계좌 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1358 | 5 | 6.2.2.1.5 | 신규해지 |  |  | 1 | 2015-04-06 | 2015-04-24 | 0.08 | 15 |  |  | 0.08
| 1359 | 6 | 6.2.2.1.5.1 | 예금 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1360 | 6 | 6.2.2.1.5.2 | 인터넷외화예금 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1361 | 6 | 6.2.2.1.5.3 | 퇴직연금 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1362 | 6 | 6.2.2.1.5.4 | 펀드 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1363 | 6 | 6.2.2.1.5.5 | 특정금전신탁 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1364 | 5 | 6.2.2.1.6 | 대출 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-24 | 0.08 | 40 |  |  | 0.08
| 1365 | 6 | 6.2.2.1.6.1 | 대출조회 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1366 | 6 | 6.2.2.1.6.2 | 대출상환/이자납입 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1367 | 6 | 6.2.2.1.6.3 | 질권설정예정계좌등록 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1368 | 6 | 6.2.2.1.6.4 | 대출신청 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1369 | 5 | 6.2.2.1.7 | 공과금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-24 | 0.06 | 40 |  |  | 0.06
| 1370 | 6 | 6.2.2.1.7.1 | My 공과금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1371 | 6 | 6.2.2.1.7.2 | 지로 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1372 | 6 | 6.2.2.1.7.3 | 세금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1373 | 6 | 6.2.2.1.7.4 | 생활요금/부담금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1374 | 6 | 6.2.2.1.7.5 | 벌칙금/벌과금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1375 | 6 | 6.2.2.1.7.6 | 연금/보험금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1376 | 6 | 6.2.2.1.7.7 | 국고및기금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1377 | 6 | 6.2.2.1.7.8 | 예약납부 조회/취소 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1378 | 5 | 6.2.2.1.8 | 통합자금관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-24 | 0.08 | 40 |  |  | 0.08
| 1379 | 6 | 6.2.2.1.8.1 | 당행집금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1380 | 6 | 6.2.2.1.8.2 | 인터넷계좌통합 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1381 | 6 | 6.2.2.1.8.3 | 집금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1382 | 6 | 6.2.2.1.8.4 | 배분 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1383 | 6 | 6.2.2.1.8.5 | 법인카드 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1384 | 6 | 6.2.2.1.8.6 | 서비스환경 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1385 | 6 | 6.2.2.1.8.7 | ERP연계 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1386 | 6 | 6.2.2.1.8.8 | 가상계좌 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1387 | 6 | 6.2.2.1.8.9 | 통합집금 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1388 | 6 | 6.2.2.1.8.10 | 집금대행 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1389 | 6 | 6.2.2.1.8.11 | 등록금수납관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1390 | 6 | 6.2.2.1.8.12 | 희망키움통장II | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1391 | 5 | 6.2.2.1.9 | 부가서비스 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-24 | 0.07 | 40 |  |  | 0.07
| 1392 | 6 | 6.2.2.1.9.1 | 급여관리서비스 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1393 | 6 | 6.2.2.1.9.2 | 전화로승인 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1394 | 6 | 6.2.2.1.9.3 | 소액계좌관리/휴면계좌정리/무통장거래정리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1395 | 6 | 6.2.2.1.9.4 | 수수료관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1396 | 5 | 6.2.2.1.10 | 결재함 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-24 | 0.04 | 40 |  |  | 0.04
| 1397 | 6 | 6.2.2.1.10.1 | 미결재내역 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1398 | 6 | 6.2.2.1.10.2 | 결재내역 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1399 | 6 | 6.2.2.1.10.3 | 등록내역 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1400 | 6 | 6.2.2.1.10.4 | 거래함 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1401 | 5 | 6.2.2.1.11 | 사용자관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-10 | 0.12 | 30 |  |  | 0.12
| 1402 | 6 | 6.2.2.1.11.1 | 내부통제 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1403 | 6 | 6.2.2.1.11.2 | 결재서비스 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1404 | 6 | 6.2.2.1.11.3 | 기타환경설정 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1405 | 5 | 6.2.2.1.12 | 공인인증센터 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-24 | 0.05 | 40 |  |  | 0.05
| 1406 | 6 | 6.2.2.1.12.1 | 공인인증서 상세안내 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1407 | 6 | 6.2.2.1.12.2 | 인증서 신규/재발급 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-13
| 1408 | 6 | 6.2.2.1.12.3 | 타행/타기관인증서 등록 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1409 | 6 | 6.2.2.1.12.4 | 인증서 관리 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-16 | 2015-03-27
| 1410 | 6 | 6.2.2.1.12.5 | 인증서 갱신/폐기 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1411 | 6 | 6.2.2.1.12.6 | 인증서 정보조회 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-10
| 1412 | 6 | 6.2.2.1.12.7 | 영수증/세금계산서 발급 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1413 | 6 | 6.2.2.1.12.8 | 발급수수료 환불신청 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1414 | 6 | 6.2.2.1.12.9 | 스마트폰인증서복사 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-04-13 | 2015-04-24
| 1415 | 5 | 6.2.2.1.13 | 배치/관리자 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-04-24 | 0.11 | 40 |  |  | 0.11
| 1416 | 6 | 6.2.2.1.13.1 | 배치 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-27
| 1417 | 6 | 6.2.2.1.13.2 | 관리자 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-30 | 2015-04-24
| 1418 | 3 | 6.2.3 | 배치프로세스 설계 |  |  | 1 |  | 2015-05-04 | 0.9 | 0.9 |  |  | 0.9
| 1419 | 4 | 6.2.3.1 | 배치프로그램 설계 | 배치프로세스 정의서 |  | 1 |  | 2015-05-06 | 0.9 | 30093 |  |  | 0.9
| 1420 | 3 | 6.2.4 | 통합 DB 설계 |  |  | 1 |  | 2015-05-04 | 1.2 | 1.2 |  |  | 1.2 |  |  |  |  | 5
| 1421 | 4 | 6.2.4.1 | 양행 테이블/속성 매핑 | 논리 ERD 물리 ERD 테이블목록 테이블매핑정의서 |  | 1 |  | 2015-05-08 | 1 | 30095 |  |  | 1
| 1422 | 5 | 6.2.4.1.1 | 이체 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.11 | 40 |  |  | 0.11
| 1423 | 5 | 6.2.4.1.2 | 전자결제 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.13 | 40 |  |  | 0.13
| 1424 | 5 | 6.2.4.1.3 | 외국환 |  |  | 1 | 2015-04-20 | 2015-04-24 | 0.15 | 5 |  |  | 0.15
| 1425 | 5 | 6.2.4.1.4 | 조회 |  |  | 1 | 2015-04-20 | 2015-04-24 | 0.03 | 5 |  |  | 0.03
| 1426 | 5 | 6.2.4.1.5 | 신규해지 |  |  | 1 | 2015-04-20 | 2015-04-24 | 0.06 | 5 |  |  | 0.06
| 1427 | 5 | 6.2.4.1.6 | 대출 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.06 | 40 |  |  | 0.06
| 1428 | 5 | 6.2.4.1.7 | 공과금 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.05 | 40 |  |  | 0.05
| 1429 | 5 | 6.2.4.1.8 | 통합자금관리 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.08 | 40 |  |  | 0.08
| 1430 | 5 | 6.2.4.1.9 | 부가서비스 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.03 | 40 |  |  | 0.03
| 1431 | 5 | 6.2.4.1.10 | 결재함 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.08 | 40 |  |  | 0.08
| 1432 | 5 | 6.2.4.1.11 | 사용자관리 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.18 | 40 |  |  | 0.18
| 1433 | 5 | 6.2.4.1.12 | 공인인증센터 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.04 | 40 |  |  | 0.04
| 1434 | 4 | 6.2.4.2 | 통합 데이터베이스 모델링 |  |  | 1 |  | 2015-05-06 | 0.2 | 30093 |  |  | 0.2
| 1435 | 5 | 6.2.4.2.1 | 이체 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.02 | 40 |  |  | 0.02
| 1436 | 5 | 6.2.4.2.2 | 전자결제 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.02 | 40 |  |  | 0.02
| 1437 | 5 | 6.2.4.2.3 | 외국환 |  |  | 1 | 2015-04-20 | 2015-04-24 | 0.02 | 5 |  |  | 0.02
| 1438 | 5 | 6.2.4.2.4 | 조회 |  |  | 1 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01
| 1439 | 5 | 6.2.4.2.5 | 신규해지 |  |  | 1 | 2015-04-20 | 2015-04-24 | 0.01 | 5 |  |  | 0.01
| 1440 | 5 | 6.2.4.2.6 | 대출 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.01 | 40 |  |  | 0.01
| 1441 | 5 | 6.2.4.2.7 | 공과금 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.01 | 40 |  |  | 0.01
| 1442 | 5 | 6.2.4.2.8 | 통합자금관리 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.02 | 40 |  |  | 0.02
| 1443 | 5 | 6.2.4.2.9 | 부가서비스 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.01 | 40 |  |  | 0.01
| 1444 | 5 | 6.2.4.2.10 | 결재함 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.02 | 40 |  |  | 0.02
| 1445 | 5 | 6.2.4.2.11 | 사용자관리 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.04 | 40 |  |  | 0.04
| 1446 | 5 | 6.2.4.2.12 | 공인인증센터 |  |  | 1 | 2015-03-02 | 2015-04-24 | 0.01 | 40 |  |  | 0.01
| 1447 | 2 | 6.3 | 구현 |  |  | 1 | 2015-03-02 | 2015-06-12 | #REF! | 6 |  |  | #REF!
| 1448 | 3 | 6.3.1 | 프로그램 구현 |  |  | 1 |  | 2015-06-14 | #REF! | 3 |  |  | #REF!
| 1449 | 4 | 6.3.1.1 | 온라인 프로그램 구현 | 온라인 프로그램 소스코드 |  | 1 |  | 2015-06-16 | 2.5 | 30122 |  |  | 2.5
| 1450 | 5 | 6.3.1.1.1 | 이체 |  |  | 1 | 2015-03-02 | 2015-06-12 | 0.3 | 75 |  |  | 0.3
| 1451 | 6 | 6.3.1.1.1.1 | 즉시이체 |  |  | 1 | 2015-03-02 | 2015-03-27
| 1452 | 6 | 6.3.1.1.1.2 | 계좌관리,이체 |  |  | 1 | 2015-03-30 | 2015-06-12
| 1453 | 6 | 6.3.1.1.1.3 | 대량이체외,이체결과 |  |  | 1 | 2015-04-01 | 2015-06-12
| 1454 | 6 | 6.3.1.1.1.4 | 글로벌이체 |  |  | 1 | 2015-05-04 | 2015-06-12
| 1455 | 5 | 6.3.1.1.2 | 전자결제 |  |  | 1 | 2015-03-02 | 2015-06-12 | 0.4 | 75 |  |  | 0.4
| 1456 | 6 | 6.3.1.1.2.1 | 판매기업 |  |  | 1 | 2015-03-02 | 2015-04-10
| 1457 | 7 | 6.3.1.1.2.1.1 | 대출(선입금)실행/결과 조회 |  |  | 1 | 2015-03-02 | 2015-03-06
| 1458 | 7 | 6.3.1.1.2.1.2 | 판매입금총괄조회 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1459 | 7 | 6.3.1.1.2.1.3 | 채권관리 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1460 | 7 | 6.3.1.1.2.1.4 | 약정정보/한도관리 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1461 | 7 | 6.3.1.1.2.1.5 | 판매기업신규약정 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1462 | 7 | 6.3.1.1.2.1.6 | 보고서 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1463 | 7 | 6.3.1.1.2.1.7 | e-구매론벤더기업약정/거래내역조회 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1464 | 6 | 6.3.1.1.2.2 | 구매기업 |  |  | 1 | 2015-04-13 | 2015-05-15
| 1465 | 7 | 6.3.1.1.2.2.1 | 구매결제총괄조회 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1466 | 7 | 6.3.1.1.2.2.2 | 채권관리 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1467 | 7 | 6.3.1.1.2.2.3 | 약정정보/한도관리 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1468 | 7 | 6.3.1.1.2.2.4 | 대출상환/선결제 |  |  | 1 | 2015-05-04 | 2015-05-08
| 1469 | 7 | 6.3.1.1.2.2.5 | 구매기업신규약정 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1470 | 7 | 6.3.1.1.2.2.6 | 보고서 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1471 | 6 | 6.3.1.1.2.3 | 중개기업 |  |  | 1 | 2015-05-18 | 2015-05-29
| 1472 | 7 | 6.3.1.1.2.3.1 | 매매진행상황조회 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1473 | 7 | 6.3.1.1.2.3.2 | B2B수수료 조회 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1474 | 7 | 6.3.1.1.2.3.2 | 약정정보조회 |  |  | 1 | 2015-05-25 | 2015-05-29
| 1475 | 6 | 6.3.1.1.2.4 | 대행업무 |  |  | 1 | 2015-06-01 | 2015-06-12
| 1476 | 7 | 6.3.1.1.2.4.1 | 발송처리결과등록 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1477 | 7 | 6.3.1.1.2.4.2 | 처리등록결과확인 |  |  | 1 | 2015-06-08 | 2015-06-12
| 1478 | 7 | 6.3.1.1.2.4.3 | 양도통지원장조회 |  |  | 1 | 2015-06-08 | 2015-06-12
| 1479 | 5 | 6.3.1.1.3 | 외국환 |  |  | 1 | 2015-03-02 | 2015-06-12 | 0.45 | 75 |  |  | 0.45
| 1480 | 6 | 6.3.1.1.3.1 | 외화송금 |  |  | 1 | 2015-03-02 | 2015-03-20
| 1481 | 6 | 6.3.1.1.3.2 | 외환매매 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1482 | 6 | 6.3.1.1.3.3 | 환율/금리조회 |  |  | 1 | 2015-03-30 | 2015-04-10
| 1483 | 6 | 6.3.1.1.3.4 | 수입 |  |  | 1 | 2015-04-13 | 2015-04-24
| 1484 | 6 | 6.3.1.1.3.5 | 수출 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1485 | 6 | 6.3.1.1.3.6 | 수수료(수입/수출) |  |  | 1 | 2015-05-04 | 2015-05-08
| 1486 | 6 | 6.3.1.1.3.7 | 인터넷EDI |  |  | 1 | 2015-05-11 | 2015-05-15
| 1487 | 6 | 6.3.1.1.3.8 | 환리스크관리 |  |  | 1 | 2015-05-18 | 2015-05-29
| 1488 | 6 | 6.3.1.1.3.9 | BiCNET Global |  |  | 1 | 2015-06-01 | 2015-06-05
| 1489 | 6 | 6.3.1.1.3.10 | 전자무역 |  |  | 1 | 2015-06-08 | 2015-06-12
| 1490 | 5 | 6.3.1.1.4 | 조회 |  |  | 1 | 2015-03-02 | 2015-06-12 | 0.09 | 75 |  |  | 0.09
| 1491 | 6 | 6.3.1.1.4.1 | 예금/펀드 |  |  | 1 | 2015-03-02 | 2015-03-20
| 1492 | 6 | 6.3.1.1.4.2 | 보관어음 |  |  | 1 | 2015-03-23 | 2015-04-10
| 1493 | 6 | 6.3.1.1.4.3 | 신용카드 |  |  | 1 | 2015-04-13 | 2015-05-01
| 1494 | 6 | 6.3.1.1.4.4 | 주류카드 |  |  | 1 | 2015-05-04 | 2015-05-22
| 1495 | 6 | 6.3.1.1.4.5 | 보고서 |  |  | 1 | 2015-05-26 | 2015-06-12
| 1496 | 6 | 6.3.1.1.4.6 | CMS계좌 |  |  | 1 | 2015-05-26 | 2015-06-12
| 1497 | 5 | 6.3.1.1.5 | 신규해지 |  |  | 1 | 2015-03-02 | 2015-06-12 | 0.13 | 75 |  |  | 0.13
| 1498 | 6 | 6.3.1.1.5.1 | 예금 |  |  | 1 | 2015-03-02 | 2015-03-20
| 1499 | 6 | 6.3.1.1.5.2 | 인터넷외화예금 |  |  | 1 | 2015-03-23 | 2015-04-10
| 1500 | 6 | 6.3.1.1.5.3 | 퇴직연금 |  |  | 1 | 2015-04-13 | 2015-05-01
| 1501 | 6 | 6.3.1.1.5.4 | 펀드 |  |  | 1 | 2015-05-04 | 2015-05-22
| 1502 | 6 | 6.3.1.1.5.5 | 특정금전신탁 |  |  | 1 | 2015-05-26 | 2015-06-12
| 1503 | 5 | 6.3.1.1.6 | 대출 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12 | 0.13 | 75 |  |  | 0.13
| 1504 | 6 | 6.3.1.1.6.1 | 대출조회 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-03-27
| 1505 | 6 | 6.3.1.1.6.2 | 대출상환/이자납입 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-30 | 2015-04-17
| 1506 | 6 | 6.3.1.1.6.3 | 질권설정예정계좌등록 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-20 | 2015-05-08
| 1507 | 6 | 6.3.1.1.6.4 | 대출신청 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-11 | 2015-05-29
| 1508 | 5 | 6.3.1.1.7 | 공과금 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12 | 0.1 | 75 |  |  | 0.1
| 1509 | 6 | 6.3.1.1.7.1 | My 공과금 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-03-13
| 1510 | 6 | 6.3.1.1.7.2 | 지로 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-16 | 2015-03-27
| 1511 | 6 | 6.3.1.1.7.3 | 세금 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-30 | 2015-04-10
| 1512 | 6 | 6.3.1.1.7.4 | 생활요금/부담금 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-13 | 2015-04-24
| 1513 | 6 | 6.3.1.1.7.5 | 벌칙금/벌과금 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-27 | 2015-05-08
| 1514 | 6 | 6.3.1.1.7.6 | 연금/보험금 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-11 | 2015-05-22
| 1515 | 6 | 6.3.1.1.7.7 | 국고및기금 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-26 | 2015-06-05
| 1516 | 6 | 6.3.1.1.7.8 | 예약납부 조회/취소 | 온라인 프로그램 소스코드 |  | 1 | 2015-06-08 | 2015-06-12
| 1517 | 5 | 6.3.1.1.8 | 통합자금관리 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12 | 0.14 | 75 |  |  | 0.14
| 1518 | 6 | 6.3.1.1.8.1 | 당행집금 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-03-13
| 1519 | 6 | 6.3.1.1.8.2 | 인터넷계좌통합 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-03-13
| 1520 | 6 | 6.3.1.1.8.3 | 집금 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-16 | 2015-03-27
| 1521 | 6 | 6.3.1.1.8.4 | 배분 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-16 | 2015-03-27
| 1522 | 6 | 6.3.1.1.8.5 | 법인카드 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-30 | 2015-04-10
| 1523 | 6 | 6.3.1.1.8.6 | 서비스환경 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-30 | 2015-04-10
| 1524 | 6 | 6.3.1.1.8.7 | ERP연계 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-13 | 2015-04-24
| 1525 | 6 | 6.3.1.1.8.8 | 가상계좌 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-27 | 2015-05-08
| 1526 | 6 | 6.3.1.1.8.9 | 통합집금 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-11 | 2015-05-22
| 1527 | 6 | 6.3.1.1.8.10 | 집금대행 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-11 | 2015-05-22
| 1528 | 6 | 6.3.1.1.8.11 | 등록금수납관리 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-26 | 2015-06-05
| 1529 | 6 | 6.3.1.1.8.12 | 희망키움통장II | 온라인 프로그램 소스코드 |  | 1 | 2015-06-08 | 2015-06-12
| 1530 | 5 | 6.3.1.1.9 | 부가서비스 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12 | 0.08 | 75 |  |  | 0.08
| 1531 | 6 | 6.3.1.1.9.1 | 급여관리서비스 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-03-13
| 1532 | 6 | 6.3.1.1.9.2 | 전화로승인 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-16 | 2015-03-27
| 1533 | 6 | 6.3.1.1.9.3 | 소액계좌관리/휴면계좌정리/무통장거래정리 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-30 | 2015-04-10
| 1534 | 6 | 6.3.1.1.9.4 | 수수료관리 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-13 | 2015-04-24
| 1535 | 5 | 6.3.1.1.10 | 결재함 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12 | 0.08 | 75 |  |  | 0.08
| 1536 | 6 | 6.3.1.1.10.1 | 미결재내역 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-27 | 2015-05-08
| 1537 | 6 | 6.3.1.1.10.2 | 결재내역 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-11 | 2015-05-22
| 1538 | 6 | 6.3.1.1.10.3 | 등록내역 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-26 | 2015-06-05
| 1539 | 6 | 6.3.1.1.10.4 | 거래함 | 온라인 프로그램 소스코드 |  | 1 | 2015-06-08 | 2015-06-12
| 1540 | 5 | 6.3.1.1.11 | 사용자관리 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12 | 0.5 | 75 |  |  | 0.5
| 1541 | 6 | 6.3.1.1.11.1 | 내부통제 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-04-03
| 1542 | 6 | 6.3.1.1.11.2 | 결재서비스 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-06 | 2015-05-08
| 1543 | 6 | 6.3.1.1.11.3 | 기타환경설정 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-11 | 2015-06-12
| 1544 | 5 | 6.3.1.1.12 | 공인인증센터 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12 | 0.1 | 75 |  |  | 0.1
| 1545 | 6 | 6.3.1.1.12.1 | 공인인증서 상세안내 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-04-03
| 1546 | 6 | 6.3.1.1.12.2 | 인증서 신규/재발급 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-04-03
| 1547 | 6 | 6.3.1.1.12.3 | 타행/타기관인증서 등록 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-06 | 2015-04-17
| 1548 | 6 | 6.3.1.1.12.4 | 인증서 관리 | 온라인 프로그램 소스코드 |  | 1 | 2015-04-20 | 2015-05-01
| 1549 | 6 | 6.3.1.1.12.5 | 인증서 갱신/폐기 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-04 | 2015-05-15
| 1550 | 6 | 6.3.1.1.12.6 | 인증서 정보조회 | 온라인 프로그램 소스코드 |  | 1 | 2015-06-01 | 2015-06-05
| 1551 | 6 | 6.3.1.1.12.7 | 영수증/세금계산서 발급 | 온라인 프로그램 소스코드 |  | 1 | 2015-05-18 | 2015-05-29
| 1552 | 6 | 6.3.1.1.12.8 | 발급수수료 환불신청 | 온라인 프로그램 소스코드 |  | 1 | 2015-06-08 | 2015-06-12
| 1553 | 6 | 6.3.1.1.12.9 | 스마트폰인증서복사 | 온라인 프로그램 소스코드 |  | 1 | 2015-06-08 | 2015-06-12
| 1554 | 4 | 6.3.1.2 | 배치 프로그램 구현 | 배치 프로그램 소스코드 |  | 1 |  | 2015-06-18 | 0.5 | 30124 |  |  | 0.5
| 1555 | 5 | 6.3.1.2.2 | 전자결제 |  |  | 1 | 2015-03-02 | 2015-06-12 | 0.12 | 75 |  |  | 0.12
| 1556 | 5 | 6.3.1.2.3 | 외국환 |  |  | 1 | 2015-03-02 | 2015-06-12 | 0.12 | 75 |  |  | 0.12
| 1557 | 5 | 6.3.1.2.13 | 배치/관리자 | 배치 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12 | 0.26 | 75 |  |  | 0.26
| 1558 | 6 | 6.3.1.2.13.1 | 배치 | 배치 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12
| 1559 | 6 | 6.3.1.2.13.2 | 관리자 | 배치 프로그램 소스코드 |  | 1 | 2015-03-02 | 2015-06-12
| 1560 | 3 | 6.3.2 | 단위테스트 수행 |  |  | 1 |  | 2015-06-18 | 3 | 3 |  |  | 3
| 1561 | 4 | 6.3.2.1 | 단위테스트 수행 | 단위테스트 결과서 |  | 1 |  | 2015-06-20 | 3 | 30125 |  |  | 3
| 1562 | 5 | 6.3.2.1.1 | 이체 |  |  | 1 | 2015-05-01 | 2015-06-19 | 0.35 | 36 |  |  | 0.35
| 1563 | 5 | 6.3.2.1.2 | 전자결제 |  |  | 1 | 2015-03-02 | 2015-06-12 | 0.4 | 75 |  |  | 0.4
| 1564 | 6 | 6.3.2.1.2.1 | 판매기업 |  |  | 1 | 2015-03-02 | 2015-04-10
| 1565 | 6 | 6.3.2.1.2.2 | 구매기업 |  |  | 1 | 2015-04-13 | 2015-05-15
| 1566 | 6 | 6.3.2.1.2.3 | 중개기업 |  |  | 1 | 2015-05-18 | 2015-05-29
| 1567 | 6 | 6.3.2.1.2.4 | 대행업무 |  |  | 1 | 2015-06-01 | 2015-06-12
| 1568 | 5 | 6.3.2.1.3 | 외국환 |  |  | 1 | 2015-03-16 | 2015-06-12 | 0.4 | 65 |  |  | 0.4
| 1569 | 6 | 6.3.2.1.3.1 | 외화송금 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1570 | 6 | 6.3.2.1.3.2 | 외환매매 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1571 | 6 | 6.3.2.1.3.3 | 환율/금리조회 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1572 | 6 | 6.3.2.1.3.4 | 수입 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1573 | 6 | 6.3.2.1.3.5 | 수출 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1574 | 6 | 6.3.2.1.3.6 | 수수료(수입/수출) |  |  | 1 | 2015-05-04 | 2015-05-08
| 1575 | 6 | 6.3.2.1.3.7 | 인터넷EDI |  |  | 1 | 2015-05-11 | 2015-05-15
| 1576 | 6 | 6.3.2.1.3.8 | 환리스크관리 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1577 | 6 | 6.3.2.1.3.9 | BiCNET Global |  |  | 1 | 2015-06-01 | 2015-06-05
| 1578 | 6 | 6.3.2.1.3.10 | 전자무역 |  |  | 1 | 2015-06-08 | 2015-06-12
| 1579 | 5 | 6.3.2.1.4 | 조회 |  |  | 1 | 2015-05-01 | 2015-06-19 | 0.09 | 36 |  |  | 0.09
| 1580 | 5 | 6.3.2.1.5 | 신규해지 |  |  | 1 | 2015-05-01 | 2015-06-19 | 0.15 | 36 |  |  | 0.15
| 1581 | 5 | 6.3.2.1.6 | 대출 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-06-12 | 0.15 | 45 |  |  | 0.15
| 1582 | 6 | 6.3.2.1.6.1 | 대출조회 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-04-24
| 1583 | 6 | 6.3.2.1.6.2 | 대출상환/이자납입 | 단위테스트 결과서 |  | 1 | 2015-04-27 | 2015-05-08
| 1584 | 6 | 6.3.2.1.6.3 | 질권설정예정계좌등록 | 단위테스트 결과서 |  | 1 | 2015-05-11 | 2015-05-22
| 1585 | 6 | 6.3.2.1.6.4 | 대출신청 | 단위테스트 결과서 |  | 1 | 2015-05-26 | 2015-06-12
| 1586 | 5 | 6.3.2.1.7 | 공과금 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-06-12 | 0.1 | 45 |  |  | 0.1
| 1587 | 6 | 6.3.2.1.7.1 | My 공과금 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-04-17
| 1588 | 6 | 6.3.2.1.7.2 | 지로 | 단위테스트 결과서 |  | 1 | 2015-04-20 | 2015-04-24
| 1589 | 6 | 6.3.2.1.7.3 | 세금 | 단위테스트 결과서 |  | 1 | 2015-04-27 | 2015-05-01
| 1590 | 6 | 6.3.2.1.7.4 | 생활요금/부담금 | 단위테스트 결과서 |  | 1 | 2015-05-04 | 2015-05-15
| 1591 | 6 | 6.3.2.1.7.5 | 벌칙금/벌과금 | 단위테스트 결과서 |  | 1 | 2015-05-18 | 2015-05-22
| 1592 | 6 | 6.3.2.1.7.6 | 연금/보험금 | 단위테스트 결과서 |  | 1 | 2015-05-26 | 2015-05-29
| 1593 | 6 | 6.3.2.1.7.7 | 국고및기금 | 단위테스트 결과서 |  | 1 | 2015-06-01 | 2015-06-05
| 1594 | 6 | 6.3.2.1.7.8 | 예약납부 조회/취소 | 단위테스트 결과서 |  | 1 | 2015-06-08 | 2015-06-12
| 1595 | 5 | 6.3.2.1.8 | 통합자금관리 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-06-12 | 0.14 | 45 |  |  | 0.14
| 1596 | 6 | 6.3.2.1.8.1 | 당행집금 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-04-17
| 1597 | 6 | 6.3.2.1.8.2 | 인터넷계좌통합 | 단위테스트 결과서 |  | 1 | 2015-04-20 | 2015-04-24
| 1598 | 6 | 6.3.2.1.8.3 | 집금 | 단위테스트 결과서 |  | 1 | 2015-04-27 | 2015-05-01
| 1599 | 6 | 6.3.2.1.8.4 | 배분 | 단위테스트 결과서 |  | 1 | 2015-05-04 | 2015-05-15
| 1600 | 6 | 6.3.2.1.8.5 | 법인카드 | 단위테스트 결과서 |  | 1 | 2015-05-04 | 2015-05-15
| 1601 | 6 | 6.3.2.1.8.6 | 서비스환경 | 단위테스트 결과서 |  | 1 | 2015-05-18 | 2015-05-22
| 1602 | 6 | 6.3.2.1.8.7 | ERP연계 | 단위테스트 결과서 |  | 1 | 2015-05-18 | 2015-05-22
| 1603 | 6 | 6.3.2.1.8.8 | 가상계좌 | 단위테스트 결과서 |  | 1 | 2015-05-26 | 2015-05-29
| 1604 | 6 | 6.3.2.1.8.9 | 통합집금 | 단위테스트 결과서 |  | 1 | 2015-05-26 | 2015-05-29
| 1605 | 6 | 6.3.2.1.8.10 | 집금대행 | 단위테스트 결과서 |  | 1 | 2015-06-01 | 2015-06-05
| 1606 | 6 | 6.3.2.1.8.11 | 등록금수납관리 | 단위테스트 결과서 |  | 1 | 2015-06-08 | 2015-06-12
| 1607 | 6 | 6.3.2.1.8.12 | 희망키움통장II | 단위테스트 결과서 |  | 1 | 2015-06-08 | 2015-06-12
| 1608 | 5 | 6.3.2.1.9 | 부가서비스 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-06-12 | 0.1 | 45 |  |  | 0.1
| 1609 | 6 | 6.3.2.1.9.1 | 급여관리서비스 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-04-24
| 1610 | 6 | 6.3.2.1.9.2 | 전화로승인 | 단위테스트 결과서 |  | 1 | 2015-04-27 | 2015-05-08
| 1611 | 6 | 6.3.2.1.9.3 | 소액계좌관리/휴면계좌정리/무통장거래정리 | 단위테스트 결과서 |  | 1 | 2015-05-11 | 2015-05-22
| 1612 | 6 | 6.3.2.1.9.4 | 수수료관리 | 단위테스트 결과서 |  | 1 | 2015-05-26 | 2015-06-12
| 1613 | 5 | 6.3.2.1.10 | 결재함 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-06-12 | 0.1 | 45 |  |  | 0.1
| 1614 | 6 | 6.3.2.1.10.1 | 미결재내역 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-04-24
| 1615 | 6 | 6.3.2.1.10.2 | 결재내역 | 단위테스트 결과서 |  | 1 | 2015-04-27 | 2015-05-08
| 1616 | 6 | 6.3.2.1.10.3 | 등록내역 | 단위테스트 결과서 |  | 1 | 2015-05-11 | 2015-05-22
| 1617 | 6 | 6.3.2.1.10.4 | 거래함 | 단위테스트 결과서 |  | 1 | 2015-05-26 | 2015-06-12
| 1618 | 5 | 6.3.2.1.11 | 사용자관리 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-06-12 | 0.5 | 45 |  |  | 0.5
| 1619 | 6 | 6.3.2.1.11.1 | 내부통제 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-05-01
| 1620 | 6 | 6.3.2.1.11.2 | 결재서비스 | 단위테스트 결과서 |  | 1 | 2015-05-04 | 2015-05-22
| 1621 | 6 | 6.3.2.1.11.3 | 기타환경설정 | 단위테스트 결과서 |  | 1 | 2015-05-26 | 2015-06-12
| 1622 | 5 | 6.3.2.1.12 | 공인인증센터 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-06-12 | 0.15 | 45 |  |  | 0.15
| 1623 | 6 | 6.3.2.1.12.1 | 공인인증서 상세안내 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-04-17
| 1624 | 6 | 6.3.2.1.12.2 | 인증서 신규/재발급 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-04-17
| 1625 | 6 | 6.3.2.1.12.3 | 타행/타기관인증서 등록 | 단위테스트 결과서 |  | 1 | 2015-04-20 | 2015-04-24
| 1626 | 6 | 6.3.2.1.12.4 | 인증서 관리 | 단위테스트 결과서 |  | 1 | 2015-04-27 | 2015-05-01
| 1627 | 6 | 6.3.2.1.12.5 | 인증서 갱신/폐기 | 단위테스트 결과서 |  | 1 | 2015-05-04 | 2015-05-15
| 1628 | 6 | 6.3.2.1.12.6 | 인증서 정보조회 | 단위테스트 결과서 |  | 1 | 2015-05-18 | 2015-05-22
| 1629 | 6 | 6.3.2.1.12.7 | 영수증/세금계산서 발급 | 단위테스트 결과서 |  | 1 | 2015-05-26 | 2015-05-29
| 1630 | 6 | 6.3.2.1.12.8 | 발급수수료 환불신청 | 단위테스트 결과서 |  | 1 | 2015-06-01 | 2015-06-05
| 1631 | 6 | 6.3.2.1.12.9 | 스마트폰인증서복사 | 단위테스트 결과서 |  | 1 | 2015-06-08 | 2015-06-12
| 1632 | 5 | 6.3.2.1.13 | 배치/관리자 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-06-12 | 0.37 | 45 |  |  | 0.37
| 1633 | 6 | 6.3.2.1.13.1 | 배치 | 단위테스트 결과서 |  | 1 | 2015-04-13 | 2015-05-15
| 1634 | 6 | 6.3.2.1.13.2 | 관리자 | 단위테스트 결과서 |  | 1 | 2015-05-18 | 2015-06-12
| 1635 | 1 | 7 | 글로벌 맞춤 뱅킹 |  |  | 1 |  | #REF! | 4.68 | 5 |  |  | 4.68
| 1636 | 2 | 7.1 | 분석 |  |  | 1 | 2015-02-09 | 2015-03-06 | 1.62 | 1.5 |  |  | 1.62
| 1637 | 3 | 7.1.1 | 현황분석 |  |  | 1 | 2015-02-09 | 2015-02-27 | 0.3 | 0.3 |  |  | 0.3
| 1638 | 4 | 7.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-27 | 0.3 | 15 |  |  | 0.3
| 1639 | 5 | 7.1.1.1.1 | 로그인 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.02 | 5 |  |  | 0.02
| 1640 | 5 | 7.1.1.1.2 | 관리자서비스 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.03 | 5 |  |  | 0.03
| 1641 | 5 | 7.1.1.1.3 | 조회/보고서 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1642 | 5 | 7.1.1.1.4 | 지급 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.03 | 5 |  |  | 0.03
| 1643 | 5 | 7.1.1.1.5 | 예금/대출 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.02 | 10 |  |  | 0.02
| 1644 | 5 | 7.1.1.1.6 | 전자결재 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.04 | 10 |  |  | 0.04
| 1645 | 5 | 7.1.1.1.7 | 외환/수출입 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.04 | 10 |  |  | 0.04
| 1646 | 5 | 7.1.1.1.8 | 카드/부가서비스 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.02 | 10 |  |  | 0.02
| 1647 | 5 | 7.1.1.1.9 | 자금관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02
| 1648 | 5 | 7.1.1.1.10 | 결재함/거래함 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1649 | 5 | 7.1.1.1.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02
| 1650 | 5 | 7.1.1.1.12 | 고시/수납관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02
| 1651 | 5 | 7.1.1.1.13 | 정산/대사관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02
| 1652 | 3 | 7.1.2 | GAP 분석 |  |  | 1 | 2015-02-09 | 2015-02-27 | 0.53 | 0.4 |  |  | 0.53
| 1653 | 4 | 7.1.2.1 | 메뉴 GAP분석 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-27 | 0.13 | 15 |  |  | 0.13
| 1654 | 5 | 7.1.2.1.1 | 로그인 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1655 | 5 | 7.1.2.1.2 | 관리자서비스 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1656 | 5 | 7.1.2.1.3 | 조회/보고서 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1657 | 5 | 7.1.2.1.4 | 지급 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1658 | 5 | 7.1.2.1.5 | 예금/대출 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.01 | 10 |  |  | 0.01
| 1659 | 5 | 7.1.2.1.6 | 전자결재 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.01 | 10 |  |  | 0.01
| 1660 | 5 | 7.1.2.1.7 | 외환/수출입 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.01 | 10 |  |  | 0.01
| 1661 | 5 | 7.1.2.1.8 | 카드/부가서비스 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.01 | 10 |  |  | 0.01
| 1662 | 5 | 7.1.2.1.9 | 자금관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1663 | 5 | 7.1.2.1.10 | 결재함/거래함 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1664 | 5 | 7.1.2.1.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1665 | 5 | 7.1.2.1.12 | 고시/수납관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1666 | 5 | 7.1.2.1.13 | 정산/대사관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1667 | 4 | 7.1.2.2 | 전문 GAP분석 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-27 | 0.27 | 15 |  |  | 0.27
| 1668 | 5 | 7.1.2.2.1 | 로그인 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.02 | 5 |  |  | 0.02
| 1669 | 5 | 7.1.2.2.2 | 관리자서비스 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.03 | 5 |  |  | 0.03
| 1670 | 5 | 7.1.2.2.3 | 조회/보고서 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1671 | 5 | 7.1.2.2.4 | 지급 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.03 | 5 |  |  | 0.03
| 1672 | 5 | 7.1.2.2.5 | 예금/대출 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.02 | 10 |  |  | 0.02
| 1673 | 5 | 7.1.2.2.6 | 전자결재 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.03 | 10 |  |  | 0.03
| 1674 | 5 | 7.1.2.2.7 | 외환/수출입 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.03 | 10 |  |  | 0.03
| 1675 | 5 | 7.1.2.2.8 | 카드/부가서비스 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.02 | 10 |  |  | 0.02
| 1676 | 5 | 7.1.2.2.9 | 자금관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02
| 1677 | 5 | 7.1.2.2.10 | 결재함/거래함 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1678 | 5 | 7.1.2.2.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02
| 1679 | 5 | 7.1.2.2.12 | 고시/수납관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1680 | 5 | 7.1.2.2.13 | 정산/대사관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02
| 1681 | 4 | 7.1.2.3 | 테이블/속성 GAP분석 | 현행 시스템 분석서 |  | 1 | 2015-02-09 | 2015-02-27 | 0.13 | 15 |  |  | 0.13
| 1682 | 5 | 7.1.2.3.1 | 로그인 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1683 | 5 | 7.1.2.3.2 | 관리자서비스 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1684 | 5 | 7.1.2.3.3 | 조회/보고서 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1685 | 5 | 7.1.2.3.4 | 지급 |  |  | 1 | 2015-02-09 | 2015-02-13 | 0.01 | 5 |  |  | 0.01
| 1686 | 5 | 7.1.2.3.5 | 예금/대출 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.01 | 10 |  |  | 0.01
| 1687 | 5 | 7.1.2.3.6 | 전자결재 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.01 | 10 |  |  | 0.01
| 1688 | 5 | 7.1.2.3.7 | 외환/수출입 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.01 | 10 |  |  | 0.01
| 1689 | 5 | 7.1.2.3.8 | 카드/부가서비스 |  |  | 1 | 2015-02-16 | 2015-02-27 | 0.01 | 10 |  |  | 0.01
| 1690 | 5 | 7.1.2.3.9 | 자금관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1691 | 5 | 7.1.2.3.10 | 결재함/거래함 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1692 | 5 | 7.1.2.3.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1693 | 5 | 7.1.2.3.12 | 고시/수납관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1694 | 5 | 7.1.2.3.13 | 정산/대사관리 |  |  | 1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01
| 1695 | 3 | 7.1.3 | 통합업무확정 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.22 | 0.25 |  |  | 0.22
| 1696 | 4 | 7.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 |  | 1 | 2015-03-02 | 2015-03-06 | 0.22 | 5 |  |  | 0.22
| 1697 | 5 | 7.1.3.1.1 | 로그인 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1698 | 5 | 7.1.3.1.2 | 관리자서비스 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1699 | 5 | 7.1.3.1.3 | 조회/보고서 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1700 | 5 | 7.1.3.1.4 | 지급 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1701 | 5 | 7.1.3.1.5 | 예금/대출 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1702 | 5 | 7.1.3.1.6 | 전자결재 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1703 | 5 | 7.1.3.1.7 | 외환/수출입 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1704 | 5 | 7.1.3.1.8 | 카드/부가서비스 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1705 | 5 | 7.1.3.1.9 | 자금관리 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1706 | 5 | 7.1.3.1.10 | 결재함/거래함 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1707 | 5 | 7.1.3.1.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1708 | 5 | 7.1.3.1.12 | 고시/수납관리 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1709 | 5 | 7.1.3.1.13 | 정산/대사관리 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1710 | 3 | 7.1.4 | 통합요건정의 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.25 | 0.25 |  |  | 0.25
| 1711 | 4 | 7.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 |  | 1 | 2015-03-02 | 2015-03-06 | 0.25 | 5 |  |  | 0.25
| 1712 | 5 | 7.1.4.1.1 | 로그인 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1713 | 5 | 7.1.4.1.2 | 관리자서비스 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.03 | 5 |  |  | 0.03
| 1714 | 5 | 7.1.4.1.3 | 조회/보고서 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1715 | 5 | 7.1.4.1.4 | 지급 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.03 | 5 |  |  | 0.03
| 1716 | 5 | 7.1.4.1.5 | 예금/대출 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1717 | 5 | 7.1.4.1.6 | 전자결재 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.03 | 5 |  |  | 0.03
| 1718 | 5 | 7.1.4.1.7 | 외환/수출입 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.03 | 5 |  |  | 0.03
| 1719 | 5 | 7.1.4.1.8 | 카드/부가서비스 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1720 | 5 | 7.1.4.1.9 | 자금관리 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1721 | 5 | 7.1.4.1.10 | 결재함/거래함 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1722 | 5 | 7.1.4.1.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1723 | 5 | 7.1.4.1.12 | 고시/수납관리 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1724 | 5 | 7.1.4.1.13 | 정산/대사관리 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1725 | 3 | 7.1.5 | 논리모델구축 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.32 | 0.3 |  |  | 0.32
| 1726 | 4 | 7.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 |  | 1 | 2015-03-02 | 2015-03-06 | 0.32 | 5 |  |  | 0.32
| 1727 | 5 | 7.1.5.1.1 | 로그인 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1728 | 5 | 7.1.5.1.2 | 관리자서비스 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.03 | 5 |  |  | 0.03
| 1729 | 5 | 7.1.5.1.3 | 조회/보고서 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1730 | 5 | 7.1.5.1.4 | 지급 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.04 | 5 |  |  | 0.04
| 1731 | 5 | 7.1.5.1.5 | 예금/대출 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1732 | 5 | 7.1.5.1.6 | 전자결재 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.04 | 5 |  |  | 0.04
| 1733 | 5 | 7.1.5.1.7 | 외환/수출입 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.04 | 5 |  |  | 0.04
| 1734 | 5 | 7.1.5.1.8 | 카드/부가서비스 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1735 | 5 | 7.1.5.1.9 | 자금관리 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1736 | 5 | 7.1.5.1.10 | 결재함/거래함 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1737 | 5 | 7.1.5.1.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1738 | 5 | 7.1.5.1.12 | 고시/수납관리 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1739 | 5 | 7.1.5.1.13 | 정산/대사관리 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1740 | 2 | 7.2 | 설계 |  |  | 1 | 2015-03-02 | 2015-03-25 | 1.26 | 1.5 |  |  | 1.26
| 1741 | 3 | 7.2.1 | 통합온라인 프로세스 설계 |  |  | 1 | 2015-03-02 | 2015-03-20 | 0.31 | 0.4 |  |  | 0.31
| 1742 | 4 | 7.2.1.1 | 화면설계 | 화면설계서 |  | 1 | 2015-03-02 | 2015-03-20 | 0.15 | 15 |  |  | 0.15
| 1743 | 4 | 7.2.1.2 | 프로그램 설계 | 프로그램 목록 프로그램 사양서 |  | 1 | 2015-03-02 | 2015-03-20 | 0.16 | 15 |  |  | 0.16
| 1744 | 5 | 7.2.1.2.1 | 로그인 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1745 | 5 | 7.2.1.2.2 | 관리자서비스 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1746 | 5 | 7.2.1.2.3 | 조회/보고서 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1747 | 5 | 7.2.1.2.4 | 지급 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1748 | 5 | 7.2.1.2.5 | 예금/대출 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.01 | 5 |  |  | 0.01
| 1749 | 5 | 7.2.1.2.6 | 전자결재 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.02 | 5 |  |  | 0.02
| 1750 | 5 | 7.2.1.2.7 | 외환/수출입 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.02 | 5 |  |  | 0.02
| 1751 | 5 | 7.2.1.2.8 | 카드/부가서비스 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.01 | 5 |  |  | 0.01
| 1752 | 5 | 7.2.1.2.9 | 자금관리 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.01 | 5 |  |  | 0.01
| 1753 | 5 | 7.2.1.2.10 | 결재함/거래함 |  |  | 1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01
| 1754 | 5 | 7.2.1.2.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01
| 1755 | 5 | 7.2.1.2.12 | 고시/수납관리 |  |  | 1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01
| 1756 | 5 | 7.2.1.2.13 | 정산/대사관리 |  |  | 1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01
| 1757 | 3 | 7.2.2 | 통합전문설계 |  |  | 1 | 2015-02-23 | 2015-03-18 | 0.35 | 0.6 |  |  | 0.35
| 1758 | 4 | 7.2.2.1 | 전문매핑 | 전문목록 전문매핑정의서 |  | 1 | 2015-03-02 | 2015-03-25 | 0.35 | 18 |  |  | 0.35
| 1759 | 5 | 7.2.2.1.1 | 로그인 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.01 | 5 |  |  | 0.01
| 1760 | 5 | 7.2.2.1.2 | 관리자서비스 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1761 | 5 | 7.2.2.1.3 | 조회/보고서 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02
| 1762 | 5 | 7.2.2.1.4 | 지급 |  |  | 1 | 2015-03-02 | 2015-03-06 | 0.04 | 5 |  |  | 0.04
| 1763 | 5 | 7.2.2.1.5 | 예금/대출 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.03 | 5 |  |  | 0.03
| 1764 | 5 | 7.2.2.1.6 | 전자결재 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.06 | 5 |  |  | 0.06
| 1765 | 5 | 7.2.2.1.7 | 외환/수출입 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.06 | 5 |  |  | 0.06
| 1766 | 5 | 7.2.2.1.8 | 카드/부가서비스 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.02 | 5 |  |  | 0.02
| 1767 | 5 | 7.2.2.1.9 | 자금관리 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.02 | 5 |  |  | 0.02
| 1768 | 5 | 7.2.2.1.10 | 결재함/거래함 |  |  | 1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01
| 1769 | 5 | 7.2.2.1.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02
| 1770 | 5 | 7.2.2.1.12 | 고시/수납관리 |  |  | 1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02
| 1771 | 5 | 7.2.2.1.13 | 정산/대사관리 |  |  | 1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02
| 1772 | 3 | 7.2.3 | 배치프로세스 설계 |  |  | 1 | 2015-02-23 | 2015-03-18 | 0.25 | 0.2 |  |  | 0.25
| 1773 | 4 | 7.2.3.1 | 배치프로그램 설계 | 배치프로세스 정의서 |  | 1 | 2015-03-02 | 2015-03-25 | 0.25 | 18 |  |  | 0.25
| 1774 | 3 | 7.2.4 | 통합 DB 설계 |  |  | 1 | 2015-02-23 | 2015-03-25 | 0.35 | 0.3 |  |  | 0.35 |  |  |  |  | 1.5
| 1775 | 4 | 7.2.4.1 | 양행 테이블/속성 매핑 | 논리 ERD 물리 ERD 테이블목록 테이블매핑정의서 |  | 1 | 2015-02-23 | 2015-03-25 | 0.25 | 23 |  |  | 0.25
| 1776 | 4 | 7.2.4.1 | 통합 데이터베이스 모델링 |  |  | 1 | 2015-02-23 | 2015-03-25 | 0.1 | 23 |  |  | 0.1
| 1777 | 2 | 7.3 | 구현 |  |  | 1 | 2015-03-09 | 2015-06-19 | 1.8 | 2 |  |  | 1.8
| 1778 | 3 | 7.3.1 | 프로그램 구현 |  |  | 1 | 2015-03-09 | 2015-06-19 | 0.9 | 1 |  |  | 0.9
| 1779 | 4 | 7.3.1.1 | 온라인 프로그램 구현 | 온라인 프로그램 소스코드 |  | 1 | 2015-03-09 | 2015-06-19 | 0.8 | 75 |  |  | 0.8
| 1780 | 5 | 7.3.1.1.1 | 로그인 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.03 | 5 |  |  | 0.03
| 1781 | 6 | 7.3.1.1.1.1 | 총괄관리자비번변경 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1782 | 5 | 7.3.1.1.2 | 관리자서비스 |  |  | 1 | 2015-03-09 | 2015-05-01 | 0.06 | 40 |  |  | 0.06
| 1783 | 6 | 7.3.1.1.1.1 | 간편환경설정 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1784 | 6 | 7.3.1.1.1.2 | 약정조회 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1785 | 6 | 7.3.1.1.1.3 | 이용환경 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1786 | 6 | 7.3.1.1.1.4 | 맞춤화면설정 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1787 | 6 | 7.3.1.1.1.5 | 이용자관리 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1788 | 6 | 7.3.1.1.1.6 | 결재관리 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1789 | 6 | 7.3.1.1.1.7 | 통제관리 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1790 | 6 | 7.3.1.1.1.8 | 공지관리 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1791 | 5 | 7.3.1.1.3 | 조회/보고서 |  |  | 1 | 2015-03-09 | 2015-05-01 | 0.04 | 40 |  |  | 0.04
| 1792 | 6 | 7.3.1.1.3.1 | 수납금(KEBiSBs) |  |  | 1 | 2015-03-09 | 2015-03-13
| 1793 | 6 | 7.3.1.1.3.2 | 통합계좌 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1794 | 6 | 7.3.1.1.3.3 | 대출 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1795 | 6 | 7.3.1.1.3.4 | 외환 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1796 | 6 | 7.3.1.1.3.5 | 수출입 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1797 | 6 | 7.3.1.1.3.6 | 전자결재 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1798 | 6 | 7.3.1.1.3.7 | 카드 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1799 | 6 | 7.3.1.1.3.8 | 금융정보 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1800 | 5 | 7.3.1.1.4 | 지급 |  |  | 1 | 2015-03-09 | 2015-05-01 | 0.12 | 40 |  |  | 0.12
| 1801 | 6 | 7.3.1.1.4.1 | 이체 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1802 | 6 | 7.3.1.1.4.2 | 송금 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1803 | 6 | 7.3.1.1.4.3 | 관세 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1804 | 6 | 7.3.1.1.4.4 | 공과금 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1805 | 6 | 7.3.1.1.4.5 | 퇴직연금 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1806 | 6 | 7.3.1.1.4.6 | 외국인근로자급여송금 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1807 | 6 | 7.3.1.1.4.7 | 해외출장비지급 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1808 | 6 | 7.3.1.1.4.8 | 송금수표발행 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1809 | 5 | 7.3.1.1.5 | 예금/대출 |  |  | 1 | 2015-05-04 | 2015-05-22 | 0.06 | 15 |  |  | 0.06
ㄷ | 1810 | 6 | 7.3.1.1.5.1 | 예금 |  |  | 1 | 2015-05-04 | 2015-05-08
| 1811 | 6 | 7.3.1.1.5.2 | 펀드 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1812 | 6 | 7.3.1.1.5.3 | 신탁 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1813 | 6 | 7.3.1.1.5.4 | 대출 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1814 | 5 | 7.3.1.1.6 | 전자결재 |  |  | 1 | 2015-05-04 | 2015-05-22 | 0.15 | 15 |  |  | 0.15
| 1815 | 6 | 7.3.1.1.6.1 | 구매기업 |  |  | 1 | 2015-05-04 | 2015-05-08
| 1816 | 6 | 7.3.1.1.6.2 | 판매기업 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1817 | 6 | 7.3.1.1.6.3 | 전자어음 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1818 | 5 | 7.3.1.1.7 | 외환/수출입 |  |  | 1 | 2015-05-04 | 2015-06-12 | 0.08 | 30 |  |  | 0.08
| 1819 | 6 | 7.3.1.1.7.1 | 외환 |  |  | 1 | 2015-05-04 | 2015-05-08
| 1820 | 6 | 7.3.1.1.7.2 | 외화수표 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1821 | 6 | 7.3.1.1.7.3 | 수출 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1822 | 6 | 7.3.1.1.7.4 | 수입 |  |  | 1 | 2015-05-25 | 2015-05-29
| 1823 | 6 | 7.3.1.1.7.5 | 내국신용장 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1824 | 6 | 7.3.1.1.7.6 | 수출입수수료 |  |  | 1 | 2015-06-08 | 2015-06-12
| 1825 | 5 | 7.3.1.1.8 | 카드/부가서비스 |  |  | 1 | 2015-05-25 | 2015-06-05 | 0.05 | 10 |  |  | 0.05
| 1826 | 6 | 7.3.1.1.8.1 | 카드 |  |  | 1 | 2015-05-25 | 2015-05-29
| 1827 | 6 | 7.3.1.1.8.2 | 수수료정보 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1828 | 5 | 7.3.1.1.9 | 자금관리 |  |  | 1 | 2015-05-25 | 2015-06-12 | 0.06 | 15 |  |  | 0.06
| 1829 | 6 | 7.3.1.1.9.1 | GCMS Plus |  |  | 1 | 2015-05-25 | 2015-05-29
| 1830 | 6 | 7.3.1.1.9.2 | GCMS |  |  | 1 | 2015-06-08 | 2015-06-12
| 1831 | 5 | 7.3.1.1.10 | 결재함/거래함 |  |  | 1 | 2015-05-25 | 2015-06-05 | 0.03 | 10 |  |  | 0.03
| 1832 | 6 | 7.3.1.1.10.1 | 결재함 |  |  | 1 | 2015-05-25 | 2015-05-29
| 1833 | 6 | 7.3.1.1.10.2 | 거래함 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1834 | 5 | 7.3.1.1.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-05-04 | 2015-06-19 | 0.04 | 35 |  |  | 0.04
| 1835 | 6 | 7.3.1.1.11.1 | 학교정보관리 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1836 | 6 | 7.3.1.1.11.2 | 학생정보관리 |  |  | 1 | 2015-06-08 | 2015-06-12
| 1837 | 6 | 7.3.1.1.11.3 | 학년/반관리 |  |  | 1 | 2015-06-15 | 2015-06-19
| 1838 | 6 | 7.3.1.1.11.4 | 동아리관리 |  |  | 1 | 2015-05-04 | 2015-05-08
| 1839 | 6 | 7.3.1.1.11.5 | 학부정보관리 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1840 | 6 | 7.3.1.1.11.6 | 납부항목관리 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1841 | 6 | 7.3.1.1.11.7 | 가상계좌관리 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1842 | 6 | 7.3.1.1.11.8 | 수납/발신정보관리 |  |  | 1 | 2015-06-15 | 2015-06-19
| 1843 | 5 | 7.3.1.1.12 | 고시/수납관리 |  |  | 1 | 2015-06-01 | 2015-06-19 | 0.04 | 15 |  |  | 0.04
| 1844 | 6 | 7.3.1.1.12.1 | 고지관리 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1845 | 6 | 7.3.1.1.12.2 | 수납현황조회 |  |  | 1 | 2015-06-15 | 2015-06-19
| 1846 | 5 | 7.3.1.1.13 | 정산/대사관리 |  |  | 1 | 2015-06-01 | 2015-06-19 | 0.04 | 15 |  |  | 0.04
| 1847 | 6 | 7.3.1.1.13.1 | 정산/대사 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1848 | 6 | 7.3.1.1.13.2 | 환불내역조회 |  |  | 1 | 2015-06-15 | 2015-06-19
| 1849 | 4 | 7.3.1.2 | 배치 프로그램 구현 | 배치 프로그램 소스코드 |  | 1 | 2015-06-05 | 2015-06-19 | 0.1 | 11 |  |  | 0.1
| 1850 | 3 | 7.3.2 | 단위테스트 수행 |  |  | 1 | 2015-03-09 | 2015-06-19 | 0.9 | 1 |  |  | 0.9
| 1851 | 4 | 7.3.2.1 | 단위테스트 수행 | 단위테스트 결과서 |  | 1 | 2015-03-09 | 2015-06-19 | 0.9 | 75 |  |  | 0.9
| 1852 | 5 | 7.3.2.1.1 | 로그인 |  |  | 1 | 2015-03-09 | 2015-03-13 | 0.03 | 5 |  |  | 0.03
| 1853 | 6 | 7.3.2.1.1.1 | 총괄관리자비번변경 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1854 | 5 | 7.3.2.1.2 | 관리자서비스 |  |  | 1 | 2015-03-09 | 2015-05-01 | 0.06 | 40 |  |  | 0.06
| 1855 | 6 | 7.3.2.1.1.1 | 간편환경설정 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1856 | 6 | 7.3.2.1.1.2 | 약정조회 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1857 | 6 | 7.3.2.1.1.3 | 이용환경 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1858 | 6 | 7.3.2.1.1.4 | 맞춤화면설정 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1859 | 6 | 7.3.2.1.1.5 | 이용자관리 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1860 | 6 | 7.3.2.1.1.6 | 결재관리 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1861 | 6 | 7.3.2.1.1.7 | 통제관리 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1862 | 6 | 7.3.2.1.1.8 | 공지관리 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1863 | 5 | 7.3.2.1.3 | 조회/보고서 |  |  | 1 | 2015-03-09 | 2015-05-01 | 0.04 | 40 |  |  | 0.04
| 1864 | 6 | 7.3.2.1.3.1 | 수납금(KEBiSBs) |  |  | 1 | 2015-03-09 | 2015-03-13
| 1865 | 6 | 7.3.2.1.3.2 | 통합계좌 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1866 | 6 | 7.3.2.1.3.3 | 대출 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1867 | 6 | 7.3.2.1.3.4 | 외환 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1868 | 6 | 7.3.2.1.3.5 | 수출입 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1869 | 6 | 7.3.2.1.3.6 | 전자결재 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1870 | 6 | 7.3.2.1.3.7 | 카드 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1871 | 6 | 7.3.2.1.3.8 | 금융정보 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1872 | 5 | 7.3.2.1.4 | 지급 |  |  | 1 | 2015-03-09 | 2015-05-01 | 0.1 | 40 |  |  | 0.1
| 1873 | 6 | 7.3.2.1.4.1 | 이체 |  |  | 1 | 2015-03-09 | 2015-03-13
| 1874 | 6 | 7.3.2.1.4.2 | 송금 |  |  | 1 | 2015-03-16 | 2015-03-20
| 1875 | 6 | 7.3.2.1.4.3 | 관세 |  |  | 1 | 2015-03-23 | 2015-03-27
| 1876 | 6 | 7.3.2.1.4.4 | 공과금 |  |  | 1 | 2015-03-30 | 2015-04-03
| 1877 | 6 | 7.3.2.1.4.5 | 퇴직연금 |  |  | 1 | 2015-04-06 | 2015-04-10
| 1878 | 6 | 7.3.2.1.4.6 | 외국인근로자급여송금 |  |  | 1 | 2015-04-13 | 2015-04-17
| 1879 | 6 | 7.3.2.1.4.7 | 해외출장비지급 |  |  | 1 | 2015-04-20 | 2015-04-24
| 1880 | 6 | 7.3.2.1.4.8 | 송금수표발행 |  |  | 1 | 2015-04-27 | 2015-05-01
| 1881 | 5 | 7.3.2.1.5 | 예금/대출 |  |  | 1 | 2015-05-04 | 2015-05-22 | 0.06 | 15 |  |  | 0.06
ㄷ | 1882 | 6 | 7.3.2.1.5.1 | 예금 |  |  | 1 | 2015-05-04 | 2015-05-08
| 1883 | 6 | 7.3.2.1.5.2 | 펀드 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1884 | 6 | 7.3.2.1.5.3 | 신탁 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1885 | 6 | 7.3.2.1.5.4 | 대출 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1886 | 5 | 7.3.2.1.6 | 전자결재 |  |  | 1 | 2015-05-04 | 2015-05-22 | 0.15 | 15 |  |  | 0.15
| 1887 | 6 | 7.3.2.1.6.1 | 구매기업 |  |  | 1 | 2015-05-04 | 2015-05-08
| 1888 | 6 | 7.3.2.1.6.2 | 판매기업 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1889 | 6 | 7.3.2.1.6.3 | 전자어음 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1890 | 5 | 7.3.2.1.7 | 외환/수출입 |  |  | 1 | 2015-05-04 | 2015-06-12 | 0.12 | 30 |  |  | 0.12
| 1891 | 6 | 7.3.2.1.7.1 | 외환 |  |  | 1 | 2015-05-04 | 2015-05-08
| 1892 | 6 | 7.3.2.1.7.2 | 외화수표 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1893 | 6 | 7.3.2.1.7.3 | 수출 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1894 | 6 | 7.3.2.1.7.4 | 수입 |  |  | 1 | 2015-05-25 | 2015-05-29
| 1895 | 6 | 7.3.2.1.7.5 | 내국신용장 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1896 | 6 | 7.3.2.1.7.6 | 수출입수수료 |  |  | 1 | 2015-06-08 | 2015-06-12
| 1897 | 5 | 7.3.2.1.8 | 카드/부가서비스 |  |  | 1 | 2015-05-25 | 2015-06-05 | 0.06 | 10 |  |  | 0.06
| 1898 | 6 | 7.3.2.1.8.1 | 카드 |  |  | 1 | 2015-05-25 | 2015-05-29
| 1899 | 6 | 7.3.2.1.8.2 | 수수료정보 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1900 | 5 | 7.3.2.1.9 | 자금관리 |  |  | 1 | 2015-05-25 | 2015-06-12 | 0.06 | 15 |  |  | 0.06
| 1901 | 6 | 7.3.2.1.9.1 | GCMS Plus |  |  | 1 | 2015-05-25 | 2015-05-29
| 1902 | 6 | 7.3.2.1.9.2 | GCMS |  |  | 1 | 2015-06-08 | 2015-06-12
| 1903 | 5 | 7.3.2.1.10 | 결재함/거래함 |  |  | 1 | 2015-05-25 | 2015-06-05 | 0.04 | 10 |  |  | 0.04
| 1904 | 6 | 7.3.2.1.10.1 | 결재함 |  |  | 1 | 2015-05-25 | 2015-05-29
| 1905 | 6 | 7.3.2.1.10.2 | 거래함 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1906 | 5 | 7.3.2.1.11 | 수납정보관리(KEBiSBs) |  |  | 1 | 2015-05-04 | 2015-06-19 | 0.06 | 35 |  |  | 0.06
| 1907 | 6 | 7.3.2.1.11.1 | 학교정보관리 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1908 | 6 | 7.3.2.1.11.2 | 학생정보관리 |  |  | 1 | 2015-06-08 | 2015-06-12
| 1909 | 6 | 7.3.2.1.11.3 | 학년/반관리 |  |  | 1 | 2015-06-15 | 2015-06-19
| 1910 | 6 | 7.3.2.1.11.4 | 동아리관리 |  |  | 1 | 2015-05-04 | 2015-05-08
| 1911 | 6 | 7.3.2.1.11.5 | 학부정보관리 |  |  | 1 | 2015-05-11 | 2015-05-15
| 1912 | 6 | 7.3.2.1.11.6 | 납부항목관리 |  |  | 1 | 2015-05-18 | 2015-05-22
| 1913 | 6 | 7.3.2.1.11.7 | 가상계좌관리 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1914 | 6 | 7.3.2.1.11.8 | 수납/발신정보관리 |  |  | 1 | 2015-06-15 | 2015-06-19
| 1915 | 5 | 7.3.2.1.12 | 고시/수납관리 |  |  | 1 | 2015-06-01 | 2015-06-19 | 0.06 | 15 |  |  | 0.06
| 1916 | 6 | 7.3.2.1.12.1 | 고지관리 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1917 | 6 | 7.3.2.1.12.2 | 수납현황조회 |  |  | 1 | 2015-06-15 | 2015-06-19
| 1918 | 5 | 7.3.2.1.13 | 정산/대사관리 |  |  | 1 | 2015-06-01 | 2015-06-19 | 0.06 | 15 |  |  | 0.06
| 1919 | 6 | 7.3.2.1.13.1 | 정산/대사 |  |  | 1 | 2015-06-01 | 2015-06-05
| 1920 | 6 | 7.3.2.1.13.2 | 환불내역조회 |  |  | 1 | 2015-06-15 | 2015-06-19
| 1921 | 1 | 8 | 외화결제(i-VOSTRO) |  |  | 0 | 2015-02-09 | 2015-06-19 | 2.5 | 95 |  |  | 2.5 | 0 | 0 |  | 0%
| 1922 | 2 | 8.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-03-06 | 0.5 | 20 |  |  | 0.5 | 0 | 0 |  | 0%
| 1923 | 3 | 8.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-14 | 0.05 | 5 |  |  | 0.05 | 0 | 0 |  | 0%
| 1924 | 4 | 8.1.1.1 | 현행시스템분석 |  |  | -1 | 2015-02-09 | 2015-02-14 | 0.05 | 5 |  |  | 0.05 | 0 | 0 |  | 0%
| 1925 | 3 | 8.1.2 | GAP 분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.34 | 15 |  |  | 0.34 | 0 | 0 |  | 0%
| 1926 | 4 | 8.1.2.1 | 메뉴 GAP분석 |  |  | -1 | 2015-02-09 | 2015-02-20 | 0.09 | 10 |  |  | 0.09 | 0 | 0 |  | 0%
| 1927 | 5 | 8.1.2.1.1 | i-VOSTRO Admin | 현행 시스템 분석서 | 분석/설계자4 | -1 | 2015-02-09 | 2015-02-20 | 0.03 | 10 |  |  | 0.03 | 0 | 0 |  | 0%
| 1928 | 5 | 8.1.2.1.2 | CLS-WEB | 현행 시스템 분석서 | 분석/설계자5 | -1 | 2015-02-09 | 2015-02-20 | 0.03 | 10 |  |  | 0.03 | 0 | 0 |  | 0%
| 1929 | 5 | 8.1.2.1.3 | Clearing WEB | 현행 시스템 분석서 | 분석/설계자6 | -1 | 2015-02-09 | 2015-02-20 | 0.03 | 10 |  |  | 0.03 | 0 | 0 |  | 0%
| 1930 | 4 | 8.1.2.2 | 전문 GAP분석 |  |  | -1 | 2015-02-16 | 2015-02-20 | 0.2 | 5 |  |  | 0.2 | 0 | 0 |  | 0%
| 1931 | 5 | 8.1.2.2.1 | i-VOSTRO AP(FAT) | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-16 | 2015-02-20 | 0.04 | 5 |  |  | 0.04 | 0 | 0 |  | 0%
| 1932 | 5 | 8.1.2.2.2 | i-VOSTRO AP(GCMS) | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-16 | 2015-02-20 | 0.04 | 5 |  |  | 0.04 | 0 | 0 |  | 0%
| 1933 | 5 | 2.1.2.2.3 | CLS-WEB | 현행 시스템 분석서 | 분석/설계자3 | -1 | 2015-02-16 | 2015-02-20 | 0.04 | 5 |  |  | 0.04 | 0 | 0 |  | 0%
| 1934 | 5 | 2.1.2.2.4 | Clearing WEB | 현행 시스템 분석서 | 분석/설계자4 | -1 | 2015-02-16 | 2015-02-20 | 0.04 | 5 |  |  | 0.04 | 0 | 0 |  | 0%
| 1935 | 5 | 2.1.2.2.5 | H/M | 현행 시스템 분석서 | 분석/설계자4 | -1 | 2015-02-16 | 2015-02-20 | 0.04 | 5 |  |  | 0.04 | 0 | 0 |  | 0%
| 1936 | 4 | 2.1.2.3 | 테이블/속성 GAP분석 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.05 | 5 |  |  | 0.05 | 0 | 0 |  | 0%
| 1937 | 5 | 2.1.2.3.1 | i-VOSTRO WEB, AP 테이블/속성 | 현행 시스템 분석서 | 분석/설계자 | -1 | 2015-02-23 | 2015-02-27 | 0.05 | 5 |  |  | 0.05 | 0 | 0 |  | 0%
| 1938 | 3 | 8.1.3 | 통합요건정의 |  |  | -1 | 2015-03-02 | 2015-03-06 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 1939 | 4 | 2.1.3.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 업무총괄 | -1 | 2015-03-02 | 2015-03-06 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 1940 | 3 | 8.1.4 | 논리모델구축 |  |  | -1 | 2015-03-02 | 2015-03-06 | 0.05 | 5 |  |  | 0.05 | 0 | 0 |  | 0%
| 1941 | 4 | 2.1.4.1 | 프로세스 모델링 | 인터페이스 정의서 | BT분석/설계자 | -1 | 2015-03-02 | 2015-03-06 | 0.05 | 5 |  |  | 0.05 | 0 | 0 |  | 0%
| 1942 | 2 | 8.2 | 설계 |  |  | -1 | 2015-03-09 | 2015-04-03 | 0.5 | 20 |  |  | 0.5 | 0 | 0 |  | 0%
| 1943 | 3 | 8.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-09 | 2015-04-03 | 0.36 | 20 |  |  | 0.36 | 0 | 0 |  | 0%
| 1944 | 4 | 2.2.1.1 | 화면설계 |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.18 | 5 |  |  | 0.18 | 0 | 0 |  | 0%
| 1945 | 5 | 2.2.1.1.1 | i-VOSTRO Admin | 화면정의서 | PT분석/설계자 | -1 | 2015-03-09 | 2015-03-13 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 1946 | 5 | 2.2.1.1.2 | CLS-WEB | 화면정의서 | PT분석/설계자 | -1 | 2015-03-09 | 2015-03-13 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 1947 | 5 | 2.2.1.1.3 | Clearing WEB | 화면정의서 | PT분석/설계자 | -1 | 2015-03-09 | 2015-03-13 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 1948 | 4 | 2.2.1.2 | 프로그램 설계 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.18 | 5 |  |  | 0.18 | 0 | 0 |  | 0%
| 1949 | 5 | 2.2.1.2.1 | i-VOSTRO Admin | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-03-20 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 1950 | 5 | 2.2.1.2.2 | CLS-WEB | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-03-20 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 1951 | 5 | 2.2.1.2.3 | Clearing WEB | 프로그램 목록 프로그램 사양서 | PT분석/설계자 | -1 | 2015-03-16 | 2015-03-20 | 0.06 | 5 |  |  | 0.06 | 0 | 0 |  | 0%
| 1952 | 3 | 8.2.2 | 통합전문설계 |  |  | -1 | 2015-03-23 | 2015-04-03 | 0.14 | 10 |  |  | 0.14 | 0 | 0 |  | 0%
| 1953 | 4 | 2.2.2.1 | 전문매핑 |  |  | -1 | 2015-03-23 | 2015-04-03 | 0.14 | 10 |  |  | 0.14 | 0 | 0 |  | 0%
| 1954 | 5 | 2.2.2.1.1 | 전문목록작성 | 전문목록 | BT분석/설계자 | -1 | 2015-03-23 | 2015-03-27 | 0.07 | 5 |  |  | 0.07 | 0 | 0 |  | 0%
| 1955 | 5 | 2.2.2.1.2 | 전문매핑정의서작성 | 전문매핑정의서 | BT분석/설계자 | -1 | 2015-03-30 | 2015-04-03 | 0.07 | 5 |  |  | 0.07 | 0 | 0 |  | 0%
| 1956 | 2 | 8.3 | 구현 |  |  | 0 | 2015-03-16 | 2015-06-19 | 1.5 | 70 |  |  | 1.5 | 0 | 0 |  | 0%
| 1957 | 3 | 8.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-06-19 | 0.9 | 70 |  |  | 0.9 | 0 | 0 |  | 0%
| 1958 | 4 | 2.3.1.1 | 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-06-19 | 0.9 | 70 |  |  | 0.9 | 0 | 0 |  | 0%
| 1959 | 5 | 2.3.1.1.1 | 보안취약성점검 및 보완 | 프로그램 소스코드 | PT개발자,BT개발자 | -1 | 2015-03-16 | 2015-04-03 | 0.15 | 15 |  |  | 0.15 | 0 | 0 |  | 0%
| 1960 | 5 | 2.3.1.1.2 | i-VOSTRO AP | 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-06 | 2015-06-05 | 0.15 | 45 |  |  | 0.15 | 0 | 0 |  | 0%
| 1961 | 5 | 2.3.1.1.3 | i-VOSTRO Admin | 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-06 | 2015-06-05 | 0.15 | 45 |  |  | 0.15 | 0 | 0 |  | 0%
| 1962 | 5 | 2.3.1.1.4 | CLS-WEB | 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-06 | 2015-06-05 | 0.15 | 45 |  |  | 0.15 | 0 | 0 |  | 0%
| 1963 | 5 | 2.3.1.1.5 | Clearing WEB | 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-06 | 2015-06-05 | 0.15 | 45 |  |  | 0.15 | 0 | 0 |  | 0%
| 1964 | 5 | 2.3.1.1.6 | H/M | 프로그램 소스코드 | PT개발자,BT개발자 | 0 | 2015-04-06 | 2015-06-05 | 0.15 | 45 |  |  | 0.15 | 0 | 0 |  | 0%
| 1965 | 3 | 8.3.2 | 단위테스트 수행 |  |  | 0 | 2015-04-20 | 2015-06-12 | 0.6 | 40 |  |  | 0.6 | 0 | 0 |  | 0%
| 1966 | 4 | 2.3.2.1 | 단위테스트 수행 |  |  | 0 | 2015-04-20 | 2015-06-12 | 0.6 | 40 |  |  | 0.6 | 0 | 0 |  | 0%
| 1967 | 5 | 2.3.2.1.1 | i-VOSTRO AP | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-06-12 | 0.12 | 40 |  |  | 0.12 | 0 | 0 |  | 0%
| 1968 | 5 | 2.3.2.1.2 | i-VOSTRO Admin | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-06-12 | 0.12 | 40 |  |  | 0.12 | 0 | 0 |  | 0%
| 1969 | 5 | 2.3.2.1.3 | CLS-WEB | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-06-12 | 0.12 | 40 |  |  | 0.12 | 0 | 0 |  | 0%
| 1970 | 5 | 2.3.2.1.4 | Clearing WEB | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-06-12 | 0.12 | 40 |  |  | 0.12 | 0 | 0 |  | 0%
| 1971 | 5 | 2.3.2.1.5 | H/M | 단위테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-04-20 | 2015-06-12 | 0.12 | 40 |  |  | 0.12 | 0 | 0 |  | 0%
| 1972 | 2 | 8.4 | 테스트 |  |  | 0 | 2015-06-15 | 2015-10-02 | 1.5 | 80 |  |  | 1.5 | 0 | 0 |  | 0%
| 1973 | 3 | 8.4.1 | 통합테스트 |  |  | 0 | 2015-06-15 | 2015-09-25 | 1 | 75 |  |  | 1 | 0 | 0 |  | 0%
| 1974 | 4 | 2.4.1.1 | 통합테스트 계획 |  |  | 0 | 2015-06-15 | 2015-09-11 | 0.1 | 65 |  |  | 0.1 | 0 | 0 |  | 0%
| 1975 | 5 | 2.4.1.1.1 | 통합테스트 계획 수립(연계채널 테스트계획 반영) | 통합테스트계획서/시나리오 | PT개발자,BT개발자 | 0 | 2015-06-15 | 2015-06-19 | 0.2 | 5 |  |  | 0.2 | 0 | 0 |  | 0%
| 1976 | 4 | 2.4.2.1 | 통합테스트 수행 (1차) |  |  | 0 | 2015-06-22 | 2015-07-10 | 0.2 | 15 |  |  | 0.2 | 0 | 0 |  | 0%
| 1977 | 5 | 2.4.2.1.1 | VOSTRO 연계 채널검증(국내채널별 연계검증) | 통합테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-06-22 | 2015-07-10 | 0.2 | 15 |  |  | 0.2 | 0 | 0 |  | 0%
| 1978 | 4 | 2.4.3.1 | 통합테스트 수행 (2차) |  |  | 0 | 2015-07-13 | 2015-07-31 | 0.2 | 15 |  |  | 0.2 | 0 | 0 |  | 0%
| 1979 | 5 | 2.4.3.1.1 | VOSTRO 연계 채널검증(국내영업점 연계검증) | 통합테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-07-13 | 2015-07-31 | 0.2 | 15 |  |  | 0.2 | 0 | 0 |  | 0%
| 1980 | 4 | 2.4.4.1 | 통합테스트 수행 (3차) |  |  | 0 | 2015-08-03 | 2015-08-28 | 0.25 | 20 |  |  | 0.25 | 0 | 0 |  | 0%
| 1981 | 5 | 2.4.4.1.1 | VOSTRO 연계 채널검증(국외영업점 연계검증) | 통합테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-08-03 | 2015-08-28 | 0.25 | 20 |  |  | 0.25 | 0 | 0 |  | 0%
| 1982 | 4 | 2.4.5.1 | 통합테스트 수행 (4차) |  |  | 0 | 2015-08-31 | 2015-09-25 | 0.25 | 20 |  |  | 0.25 | 0 | 0 |  | 0%
| 1983 | 5 | 2.4.5.1.1 | VOSTRO 연계 채널검증(통합점검) | 통합테스트 결과서 | PT개발자,BT개발자 | 0 | 2015-08-31 | 2015-09-25 | 0.25 | 20 |  |  | 0.25 | 0 | 0 |  | 0%
| 1984 | 3 | 8.5.1 | 인수테스트 |  |  | 0 | 2015-09-21 | 2015-10-02 | 0.5 | 10 |  |  | 0.5 | 0 | 0 |  | 0%
| 1985 | 4 | 2.5.1.1 | 인수테스트 수행 |  |  | 0 | 2015-09-21 | 2015-10-02 | 0.5 | 10 |  |  | 0.5 | 0 | 0 |  | 0%
| 1986 | 5 | 2.5.1.1.1 | VOSTRO 연계 채널검증 | 인수테스트시나리오/결과서 |  | 0 | 2015-09-21 | 2015-10-02 | 0.25 | 10 |  |  | 0.25 | 0 | 0 |  | 0%
| 1987 | 5 | 2.5.1.1.2 | VOSTRO WEB 서비스 검증 | 인수테스트시나리오/결과서 |  | 0 | 2015-09-21 | 2015-10-02 | 0.25 | 10 |  |  | 0.25 | 0 | 0 |  | 0%
| 1988 | 1 | 8 | CMS |  |  | 0 | 2015-02-09 | 2015-06-12 | 9 | 90 |  |  | 9
| 1989 | 2 | 9.1 | 분석 |  |  | 0 | 2015-02-09 | 2015-06-12 | 1.5 | 90 |  |  | 1.5 |  |  |  | 100%
| 1990 | 3 | 9.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.3 | 15 |  |  | 0.3 |  |  |  | 100%
| 1991 | 4 | 9.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 |  | -1 | 2015-02-09 | 2015-02-27 | 0.3 | 15 |  |  | 0.3 |  |  |  | 0%
| 1992 | 5 | 9.1.1.1.1 | BiCNET |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.04 | 15 |  |  | 0.04 |  |  |  | 0%
| 1993 | 6 | 9.1.1.1.1.1 | 통합자금관리 |  |  | -1 | 2015-02-09 | 2015-02-13 |  | 5 | [6 empty] | 0%
| 1994 | 6 | 9.1.1.1.1.2 | 자금수납 |  |  | -1 | 2015-02-09 | 2015-02-13 |  | 5 | [6 empty] | 0%
| 1995 | 6 | 9.1.1.1.1.3 | 자금지급 |  |  | -1 | 2015-02-09 | 2015-02-13 |  | 5 | [6 empty] | 0%
| 1996 | 6 | 9.1.1.1.1.4 | 법인카드 |  |  | -1 | 2015-02-16 | 2015-02-20 |  | 5 | [6 empty] | 0%
| 1997 | 6 | 9.1.1.1.1.5 | 수출입외환 |  |  | -1 | 2015-02-16 | 2015-02-20 |  | 5 | [6 empty] | 0%
| 1998 | 6 | 9.1.1.1.1.6 | 부가서비스 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 1999 | 6 | 9.1.1.1.1.7 | 사용자관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2000 | 6 | 9.1.1.1.1.8 | 특화서비스 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2001 | 5 | 9.1.1.1.2 | BiCNET light |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2002 | 6 | 9.1.1.1.2.1 | 계좌관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2003 | 6 | 9.1.1.1.2.2 | 조회 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2004 | 6 | 9.1.1.1.2.3 | 집금실행 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 100%
| 2005 | 6 | 9.1.1.1.2.4 | 이체 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2006 | 6 | 9.1.1.1.2.5 | 법인카드 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2007 | 6 | 9.1.1.1.2.6 | 보고서 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2008 | 6 | 9.1.1.1.2.7 | 사용자관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2009 | 6 | 9.1.1.1.2.8 | 하나CBS |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2010 | 6 | 9.1.1.1.2.9 | 하나CBS light |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2011 | 6 | 9.1.1.1.2.10 | 특화서비스 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2012 | 5 | 9.1.1.1.3 | In-House뱅킹PLUS |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.09 | 15 |  |  | 0.09 |  |  |  | 0%
| 2013 | 6 | 9.1.1.1.3.1 | 업무관리 |  |  | -1 | 2015-02-09 | 2015-02-13 |  | 5 | [6 empty] | 0%
| 2014 | 6 | 9.1.1.1.3.2 | 조회¦보고서 |  |  | -1 | 2015-02-09 | 2015-02-13 |  | 5 | [6 empty] | 0%
| 2015 | 6 | 9.1.1.1.3.3 | 자금관리 |  |  | -1 | 2015-02-16 | 2015-02-20 |  | 5 | [6 empty] | 0%
| 2016 | 6 | 9.1.1.1.3.4 | 지급¦이체 |  |  | -1 | 2015-02-16 | 2015-02-20 |  | 5 | [6 empty] | 0%
| 2017 | 6 | 9.1.1.1.3.5 | 예금¦대출 |  |  | -1 | 2015-02-16 | 2015-02-20 |  | 5 | [6 empty] | 0%
| 2018 | 6 | 9.1.1.1.3.6 | 전자결제 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2019 | 6 | 9.1.1.1.3.7 | 수출입 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2020 | 6 | 9.1.1.1.3.8 | 법인카드 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2021 | 6 | 9.1.1.1.3.9 | 시스템관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 100%
| 2022 | 5 | 9.1.1.1.4 | GCMS PLUS |  |  | -1 | 2015-02-16 | 2015-02-27 | 0.05 | 10 |  |  | 0.05 |  |  |  | 0%
| 2023 | 6 | 9.1.1.1.4.1 | 은행계좌 |  |  | -1 | 2015-02-16 | 2015-02-20 |  | 5 | [6 empty] | 100%
| 2024 | 6 | 9.1.1.1.4.2 | 통합카드 |  |  | -1 | 2015-02-16 | 2015-02-20 |  | 5 | [6 empty] | 0%
| 2025 | 6 | 9.1.1.1.4.3 | 증권 |  |  | -1 | 2015-02-16 | 2015-02-20 |  | 5 | [6 empty] | 100%
| 2026 | 6 | 9.1.1.1.4.4 | 전자결제/어음 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2027 | 6 | 9.1.1.1.4.5 | 지급 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 100%
| 2028 | 6 | 9.1.1.1.4.6 | 집금/배분 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 100%
| 2029 | 6 | 9.1.1.1.4.7 | 전자세금계산서 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2030 | 6 | 9.1.1.1.4.8 | 서비스관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2031 | 6 | 9.1.1.1.4.9 | ERP연계관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2032 | 5 | 9.1.1.1.5 | In-House뱅킹MEGA |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.03 | 5 |  |  | 0.03 |  |  |  | 0%
| 2033 | 6 | 9.1.1.1.5.1 | 통합조회 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2034 | 6 | 9.1.1.1.5.2 | 지급관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2035 | 6 | 9.1.1.1.5.3 | 자금관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2036 | 6 | 9.1.1.1.5.4 | 법인카드 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2037 | 6 | 9.1.1.1.5.5 | 글로벌서비스 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2038 | 6 | 9.1.1.1.5.6 | 서비스관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2039 | 6 | 9.1.1.1.5.7 | 시스템관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2040 | 5 | 9.1.1.1.6 | 인터넷자금관리 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.03 | 5 |  |  | 0.03 |  |  |  | 0%
| 2041 | 6 | 9.1.1.1.6.1 | 인터넷계좌통합 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2042 | 6 | 9.1.1.1.6.2 | 집금 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2043 | 6 | 9.1.1.1.6.3 | 배분 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2044 | 6 | 9.1.1.1.6.4 | 법인카드관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2045 | 6 | 9.1.1.1.6.5 | 서비스환경 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2046 | 6 | 9.1.1.1.6.6 | ERP환경 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2047 | 5 | 9.1.1.1.7 | KEB Smart-Tax |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2048 | 5 | 9.1.1.1.8 | 공통 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.03 | 5 |  |  | 0.03 |  |  |  | 0%
| 2049 | 3 | 9.1.2 | GAP 분석 |  |  | -1 | 2015-02-23 | 2015-03-20 | 0.5 | 20 |  |  | 0.5 |  |  |  | 0%
| 2050 | 4 | 9.1.2.1 | 메뉴 GAP분석 | 현행 시스템 분석서 |  | -1 | 2015-02-23 | 2015-02-27 | 0.1 | 5 |  |  | 0.1 |  |  |  | 0%
| 2051 | 5 | 9.1.2.1.1 | BiCNET |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2052 | 5 | 9.1.2.1.2 | BiCNET light |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2053 | 5 | 9.1.2.1.3 | In-House뱅킹PLUS |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.03 | 5 |  |  | 0.03 |  |  |  | 0%
| 2054 | 5 | 9.1.2.1.4 | GCMS PLUS |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2055 | 5 | 9.1.2.1.5 | In-House뱅킹MEGA |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2056 | 5 | 9.1.2.1.6 | 인터넷자금관리 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01 |  |  |  | 100%
| 2057 | 5 | 9.1.2.1.7 | KEB Smart-Tax |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2058 | 4 | 9.1.2.2 | 전문 GAP분석 | 현행 시스템 분석서 |  | -1 | 2015-02-23 | 2015-03-20 | 0.3 | 20 |  |  | 0.3 |  |  |  | 0%
| 2059 | 5 | 9.1.2.2.1 | BiCNET |  |  | -1 | 2015-02-23 | 2015-03-06 | 0.05 | 10 |  |  | 0.05 |  |  |  | 0%
| 2060 | 6 | 9.1.2.2.1.1 | 통합자금관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2061 | 6 | 9.1.2.2.1.2 | 자금수납 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2062 | 6 | 9.1.2.2.1.3 | 자금지급 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2063 | 6 | 9.1.2.2.1.4 | 법인카드 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2064 | 6 | 9.1.2.2.1.5 | 수출입외환 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2065 | 6 | 9.1.2.2.1.6 | 부가서비스 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2066 | 6 | 9.1.2.2.1.7 | 사용자관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2067 | 6 | 9.1.2.2.1.8 | 특화서비스 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2068 | 5 | 9.1.2.2.2 | BiCNET light |  |  | -1 | 2015-03-02 | 2015-03-06 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2069 | 6 | 9.1.2.2.2.1 | 계좌관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2070 | 6 | 9.1.2.2.2.2 | 조회 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2071 | 6 | 9.1.2.2.2.3 | 집금실행 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2072 | 6 | 9.1.2.2.2.4 | 이체 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2073 | 6 | 9.1.2.2.2.5 | 법인카드 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2074 | 6 | 9.1.2.2.2.6 | 보고서 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2075 | 6 | 9.1.2.2.2.7 | 사용자관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2076 | 6 | 9.1.2.2.2.8 | 하나CBS |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2077 | 6 | 9.1.2.2.2.9 | 하나CBS light |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2078 | 6 | 9.1.2.2.2.10 | 특화서비스 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2079 | 5 | 9.1.2.2.3 | In-House뱅킹PLUS |  |  | -1 | 2015-02-23 | 2015-03-06 | 0.1 | 10 |  |  | 0.1 |  |  |  | 0%
| 2080 | 6 | 9.1.2.2.3.1 | 업무관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2081 | 6 | 9.1.2.2.3.2 | 조회¦보고서 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2082 | 6 | 9.1.2.2.3.3 | 자금관리 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 0%
| 2083 | 6 | 9.1.2.2.3.4 | 지급¦이체 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 100%
| 2084 | 6 | 9.1.2.2.3.5 | 예금¦대출 |  |  | -1 | 2015-02-23 | 2015-02-27 |  | 5 | [6 empty] | 100%
| 2085 | 6 | 9.1.2.2.3.6 | 전자결제 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2086 | 6 | 9.1.2.2.3.7 | 수출입 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2087 | 6 | 9.1.2.2.3.8 | 법인카드 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2088 | 6 | 9.1.2.2.3.9 | 시스템관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2089 | 5 | 9.1.2.2.4 | GCMS PLUS |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.05 | 5 |  |  | 0.05 |  |  |  | 0%
| 2090 | 6 | 9.1.2.2.4.1 | 은행계좌 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2091 | 6 | 9.1.2.2.4.2 | 통합카드 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2092 | 6 | 9.1.2.2.4.3 | 증권 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2093 | 6 | 9.1.2.2.4.4 | 전자결제/어음 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2094 | 6 | 9.1.2.2.4.5 | 지급 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2095 | 6 | 9.1.2.2.4.6 | 집금/배분 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2096 | 6 | 9.1.2.2.4.7 | 전자세금계산서 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2097 | 6 | 9.1.2.2.4.8 | 서비스관리 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2098 | 6 | 9.1.2.2.4.9 | ERP연계관리 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2099 | 5 | 9.1.2.2.5 | In-House뱅킹MEGA |  |  | -1 | 2015-03-09 | 2015-03-20 | 0.03 | 10 |  |  | 0.03 |  |  |  | 0%
| 2100 | 6 | 9.1.2.2.5.1 | 통합조회 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2101 | 6 | 9.1.2.2.5.2 | 지급관리 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2102 | 6 | 9.1.2.2.5.3 | 자금관리 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 100%
| 2103 | 6 | 9.1.2.2.5.4 | 법인카드 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 100%
| 2104 | 6 | 9.1.2.2.5.5 | 글로벌서비스 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2105 | 6 | 9.1.2.2.5.6 | 서비스관리 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2106 | 6 | 9.1.2.2.5.7 | 시스템관리 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2107 | 5 | 9.1.2.2.6 | 인터넷자금관리 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.04 | 10 |  |  | 0.04 |  |  |  | 0%
| 2108 | 6 | 9.1.2.2.6.1 | 인터넷계좌통합 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2109 | 6 | 9.1.2.2.6.2 | 집금 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2110 | 6 | 9.1.2.2.6.3 | 배분 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2111 | 6 | 9.1.2.2.6.4 | 법인카드관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2112 | 6 | 9.1.2.2.6.5 | 서비스환경 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2113 | 6 | 9.1.2.2.6.6 | ERP환경 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2114 | 5 | 9.1.2.2.7 | KEB Smart-Tax |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2115 | 4 | 9.1.2.3 | 테이블/속성 GAP분석 | 현행 시스템 분석서 |  | -1 | 2015-03-09 | 2015-03-13 | 0.1 | 5 |  |  | 0.1 |  |  |  | 0%
| 2116 | 5 | 9.1.2.3.1 | BiCNET |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2117 | 5 | 9.1.2.3.2 | BiCNET light |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.01 | 5 |  |  | 0.01 |  |  |  | 100%
| 2118 | 5 | 9.1.2.3.3 | In-House뱅킹PLUS |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.03 | 5 |  |  | 0.03 |  |  |  | 0%
| 2119 | 5 | 9.1.2.3.4 | GCMS PLUS |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2120 | 5 | 9.1.2.3.5 | In-House뱅킹MEGA |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2121 | 5 | 9.1.2.3.6 | 인터넷자금관리 |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2122 | 5 | 9.1.2.3.7 | KEB Smart-Tax |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2123 | 3 | 9.1.3 | 통합업무확정 |  |  | -1 | 2015-03-09 | 2015-03-20 | 0.3 | 10 |  |  | 0.3 |  |  |  | 0%
| 2124 | 4 | 9.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 |  | -1 | 2015-03-09 | 2015-03-20 | 0.3 | 10 |  |  | 0.3 |  |  |  | 0%
| 2125 | 5 | 9.1.3.1.1 | BiCNET |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.05 | 5 |  |  | 0.05 |  |  |  | 0%
| 2126 | 5 | 9.1.3.1.2 | BiCNET light |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2127 | 5 | 9.1.3.1.3 | In-House뱅킹PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.1 | 5 |  |  | 0.1 |  |  |  | 0%
| 2128 | 5 | 9.1.3.1.4 | GCMS PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.05 | 5 |  |  | 0.05 |  |  |  | 0%
| 2129 | 5 | 9.1.3.1.5 | In-House뱅킹MEGA |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.03 | 5 |  |  | 0.03 |  |  |  | 0%
| 2130 | 5 | 9.1.3.1.6 | 인터넷자금관리 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.04 | 5 |  |  | 0.04 |  |  |  | 0%
| 2131 | 5 | 9.1.3.1.7 | KEB Smart-Tax |  |  | -1 | 2015-03-09 | 2015-03-20 | 0.01 | 10 |  |  | 0.01 |  |  |  | 0%
| 2132 | 3 | 9.1.4 | 통합요건정의 |  |  | -1 | 2015-03-09 | 2015-03-20 | 0.2 | 10 |  |  | 0.2 |  |  |  | 0%
| 2133 | 4 | 9.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 |  | -1 | 2015-03-09 | 2015-03-20 | 0.2 | 10 |  |  | 0.2 |  |  |  | 0%
| 2134 | 5 | 9.1.4.1.1 | BiCNET |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.04 | 5 |  |  | 0.04 |  |  |  | 100%
| 2135 | 5 | 9.1.4.1.2 | BiCNET light |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2136 | 5 | 9.1.4.1.3 | In-House뱅킹PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.06 | 5 |  |  | 0.06 |  |  |  | 100%
| 2137 | 5 | 9.1.4.1.4 | GCMS PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2138 | 5 | 9.1.4.1.5 | In-House뱅킹MEGA |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 100%
| 2139 | 5 | 9.1.4.1.6 | 인터넷자금관리 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2140 | 5 | 9.1.4.1.7 | KEB Smart-Tax |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 100%
| 2141 | 3 | 9.1.5 | 논리모델구축 |  |  | 0 | 2015-03-09 | 2015-06-12 | 0.2 | 70 |  |  | 0.2 |  |  |  | 0%
| 2142 | 4 | 9.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 |  | 0 | 2015-03-09 | 2015-06-12 | 0.2 | 70 |  |  | 0.2 |  |  |  | 0%
| 2143 | 5 | 9.1.5.1.1 | BiCNET |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.04 | 5 |  |  | 0.04 |  |  |  | 0%
| 2144 | 5 | 9.1.5.1.2 | BiCNET light |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2145 | 5 | 9.1.5.1.3 | In-House뱅킹PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.06 | 5 |  |  | 0.06 |  |  |  | 0%
| 2146 | 5 | 9.1.5.1.4 | GCMS PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2147 | 5 | 9.1.5.1.5 | In-House뱅킹MEGA |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2148 | 5 | 9.1.5.1.6 | 인터넷자금관리 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2149 | 5 | 9.1.5.1.7 | KEB Smart-Tax |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2150 | 2 | 9.2 | 설계 |  |  | 0 | 2015-02-09 | 2015-06-12 | 1.5 | 90 |  |  | 1.5 |  |  |  | 0%
| 2151 | 3 | 9.2.1 | 통합온라인 프로세스 설계 |  |  | 0 | 2015-03-09 | 2015-06-12 | 0.7 | 70 |  |  | 0.7 |  |  |  | 0%
| 2152 | 4 | 9.2.1.1 | 화면설계 | 화면설계서 |  | 0 | 2015-03-09 | 2015-06-12 | 0.4 | 70 |  |  | 0.4 |  |  |  | 0%
| 2153 | 5 | 9.2.1.1.1 | BiCNET |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.8 | 5 |  |  | 0.8 |  |  |  | 0%
| 2154 | 5 | 9.2.1.1.2 | BiCNET light |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.2 | 5 |  |  | 0.2 |  |  |  | 0%
| 2155 | 5 | 9.2.1.1.3 | In-House뱅킹PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 2 | 5 |  |  | 2 |  |  |  | 0%
| 2156 | 5 | 9.2.1.1.4 | GCMS PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.58 | 5 |  |  | 0.58 |  |  |  | 0%
| 2157 | 5 | 9.2.1.1.5 | In-House뱅킹MEGA |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2158 | 5 | 9.2.1.1.6 | 인터넷자금관리 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.4 | 5 |  |  | 0.4 |  |  |  | 0%
| 2159 | 5 | 9.2.1.1.7 | KEB Smart-Tax |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2160 | 4 | 9.2.1.2 | 프로그램 설계 | 프로그램 목록 프로그램 사양서 |  | 0 | 2015-03-09 | 2015-06-12 | 0.3 | 70 |  |  | 0.3 |  |  |  | 0%
| 2161 | 5 | 9.2.1.2.1 | BiCNET |  |  | 0 | 2015-03-09 | 2015-06-12 | 0.65 | 70 |  |  | 0.65 |  |  |  | 0%
| 2162 | 5 | 9.2.1.2.2 | BiCNET light |  |  | 0 | 2015-03-09 | 2015-06-12 | 0.18 | 70 |  |  | 0.18 |  |  |  | 0%
| 2163 | 5 | 9.2.1.2.3 | In-House뱅킹PLUS |  |  | 0 | 2015-03-16 | 2015-06-12 | 1.25 | 65 |  |  | 1.25 |  |  |  | 0%
| 2164 | 5 | 9.2.1.2.4 | GCMS PLUS |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.35 | 65 |  |  | 0.35 |  |  |  | 0%
| 2165 | 5 | 9.2.1.2.5 | In-House뱅킹MEGA |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.01 | 65 |  |  | 0.01 |  |  |  | 0%
| 2166 | 5 | 9.2.1.2.6 | 인터넷자금관리 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.3 | 65 |  |  | 0.3 |  |  |  | 0%
| 2167 | 5 | 9.2.1.2.6 | KEB Smart-Tax |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.01 | 65 |  |  | 0.01 |  |  |  | 0%
| 2168 | 5 | 9.2.1.2.6 | 공통 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.25 | 65 |  |  | 0.25 |  |  |  | 0%
| 2169 | 3 | 9.2.2 | 통합전문설계 |  |  | 0 | 2015-02-09 | 2015-06-12 | 0.8 | 90 |  |  | 0.8 |  |  |  | 100%
| 2170 | 4 | 9.2.2.1 | 전문매핑 |  |  | 0 | 2015-02-09 | 2015-06-12 | 0.5 | 90 |  |  | 0.5 |  |  |  | 0%
| 2171 | 5 | 9.2.2.1.1 | BiCNET |  |  | -1 | 2015-03-02 | 2015-03-20 | 0.1 | 15 |  |  | 0.1 |  |  |  | 0%
| 2172 | 6 | 9.2.2.1.1.1 | 통합자금관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2173 | 6 | 9.2.2.1.1.2 | 자금수납 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2174 | 6 | 9.2.2.1.1.3 | 자금지급 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2175 | 6 | 9.2.2.1.1.4 | 법인카드 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2176 | 6 | 9.2.2.1.1.5 | 수출입외환 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2177 | 6 | 9.2.2.1.1.6 | 부가서비스 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2178 | 6 | 9.2.2.1.1.7 | 사용자관리 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2179 | 6 | 9.2.2.1.1.8 | 특화서비스 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2180 | 5 | 9.2.2.1.2 | BiCNET light |  |  | -1 | 2015-03-09 | 2015-03-20 | 0.03 | 10 |  |  | 0.03 |  |  |  | 0%
| 2181 | 6 | 9.2.2.1.2.1 | 계좌관리 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2182 | 6 | 9.2.2.1.2.2 | 조회 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2183 | 6 | 9.2.2.1.2.3 | 집금실행 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2184 | 6 | 9.2.2.1.2.4 | 이체 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2185 | 6 | 9.2.2.1.2.5 | 법인카드 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2186 | 6 | 9.2.2.1.2.6 | 보고서 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2187 | 6 | 9.2.2.1.2.7 | 사용자관리 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2188 | 6 | 9.2.2.1.2.8 | 하나CBS |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2189 | 6 | 9.2.2.1.2.9 | 하나CBS light |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2190 | 6 | 9.2.2.1.2.10 | 특화서비스 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2191 | 5 | 9.2.2.1.3 | In-House뱅킹PLUS |  |  | 0 | 2015-02-09 | 2015-06-12 | 0.25 | 90 |  |  | 0.25 |  |  |  | 0%
| 2192 | 6 | 9.2.2.1.3.1 | 업무관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2193 | 6 | 9.2.2.1.3.2 | 조회¦보고서 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2194 | 6 | 9.2.2.1.3.3 | 자금관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2195 | 6 | 9.2.2.1.3.4 | 지급¦이체 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2196 | 6 | 9.2.2.1.3.5 | 예금¦대출 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 100%
| 2197 | 6 | 9.2.2.1.3.6 | 전자결제 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 100%
| 2198 | 6 | 9.2.2.1.3.7 | 수출입 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2199 | 6 | 9.2.2.1.3.8 | 법인카드 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2200 | 6 | 9.2.2.1.3.9 | 시스템관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2201 | 5 | 9.2.2.1.4 | GCMS PLUS |  |  | -1 | 2015-03-09 | 2015-03-20 | 0.04 | 10 |  |  | 0.04 |  |  |  | 0%
| 2202 | 6 | 9.2.2.1.4.1 | 은행계좌 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2203 | 6 | 9.2.2.1.4.2 | 통합카드 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2204 | 6 | 9.2.2.1.4.3 | 증권 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2205 | 6 | 9.2.2.1.4.4 | 전자결제/어음 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2206 | 6 | 9.2.2.1.4.5 | 지급 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2207 | 6 | 9.2.2.1.4.6 | 집금/배분 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2208 | 6 | 9.2.2.1.4.7 | 전자세금계산서 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2209 | 6 | 9.2.2.1.4.8 | 서비스관리 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2210 | 6 | 9.2.2.1.4.9 | ERP연계관리 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2211 | 5 | 9.2.2.1.5 | In-House뱅킹MEGA |  |  | -1 | 2015-03-09 | 2015-03-20 | 0.01 | 10 |  |  | 0.01 |  |  |  | 0%
| 2212 | 6 | 9.2.2.1.5.1 | 통합조회 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2213 | 6 | 9.2.2.1.5.2 | 지급관리 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2214 | 6 | 9.2.2.1.5.3 | 자금관리 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2215 | 6 | 9.2.2.1.5.4 | 법인카드 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 100%
| 2216 | 6 | 9.2.2.1.5.5 | 글로벌서비스 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 100%
| 2217 | 6 | 9.2.2.1.5.6 | 서비스관리 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2218 | 6 | 9.2.2.1.5.7 | 시스템관리 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2219 | 5 | 9.2.2.1.6 | 인터넷자금관리 |  |  | -1 | 2015-03-02 | 2015-03-20 | 0.06 | 15 |  |  | 0.06 |  |  |  | 0%
| 2220 | 6 | 9.2.2.1.6.1 | 인터넷계좌통합 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2221 | 6 | 9.2.2.1.6.2 | 집금 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2222 | 6 | 9.2.2.1.6.3 | 배분 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2223 | 6 | 9.2.2.1.6.4 | 법인카드관리 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2224 | 6 | 9.2.2.1.6.5 | 서비스환경 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2225 | 6 | 9.2.2.1.6.6 | ERP환경 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2226 | 5 | 9.2.2.1.7 | KEB Smart-Tax |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2227 | 3 | 9.2.3 | 통합DB설계 |  |  | -1 |  |  |  | 0 | [6 empty] | 0%
| 2228 | 4 | 9.2.3.1 | 양행 테이블/속성 매핑 | 논리 ERD 물리 ERD 테이블목록 테이블매핑정의서 |  | -1 | 2015-03-16 | 2015-03-20 | 0.15 | 5 |  |  | 0.15 |  |  |  | 0%
| 2229 | 5 | 9.2.3.1.1 | BiCNET |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.04 | 5 |  |  | 0.04 |  |  |  | 0%
| 2230 | 5 | 9.2.3.1.2 | BiCNET light |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 100%
| 2231 | 5 | 9.2.3.1.3 | In-House뱅킹PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.1 | 5 |  |  | 0.1 |  |  |  | 0%
| 2232 | 5 | 9.2.3.1.4 | GCMS PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2233 | 5 | 9.2.3.1.5 | In-House뱅킹MEGA |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2234 | 5 | 9.2.3.1.6 | 인터넷자금관리 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2235 | 5 | 9.2.3.1.7 | KEB Smart-Tax |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2236 | 4 | 9.2.3.2 | 통합데이터베이스모델링 | 논리 ERD 물리 ERD 테이블목록 테이블매핑정의서 |  | -1 | 2015-03-16 | 2015-03-20 | 0.1 | 5 |  |  | 0.1 |  |  |  | 0%
| 2237 | 5 | 9.2.3.2.1 | BiCNET |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2238 | 5 | 9.2.3.2.2 | BiCNET light |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2239 | 5 | 9.2.3.2.3 | In-House뱅킹PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.03 | 5 |  |  | 0.03 |  |  |  | 0%
| 2240 | 5 | 9.2.3.2.4 | GCMS PLUS |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2241 | 5 | 9.2.3.2.5 | In-House뱅킹MEGA |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2242 | 5 | 9.2.3.2.6 | 인터넷자금관리 |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2243 | 5 | 9.2.3.2.7 | KEB Smart-Tax |  |  | -1 | 2015-03-16 | 2015-03-20 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2244 | 3 | 9.2.4 | 배치프로세스 설계 |  |  | -1 |  |  |  | 0 | [6 empty] | 0%
| 2245 | 4 | 9.2.4.1 | 배치프로그램설계 (해당사항없음) | 배치프로세스 정의서 |  | -1 |  |  |  | 0 | [6 empty] | 0%
| 2246 | 3 | 9.2.5 | 테스트 설계 |  |  | -1 |  |  |  | 0 | [6 empty] | 100%
| 2247 | 2 | 9.3 | 구현 |  |  | 0 | 2015-02-09 | 2015-06-12 | 6 | 90 |  |  | 6 |  |  |  | 0%
| 2248 | 3 | 9.3.1 | 프로그램 구현 |  |  | 0 | 2015-02-09 | 2015-06-12 | 4.5 | 90 |  |  | 4.5 |  |  |  | 0%
| 2249 | 4 | 9.3.1.1 | 온라인 프로그램 구현 | 온라인 프로그램 소스코드 |  | 0 | 2015-02-09 | 2015-06-12 | 4.5 | 90 |  |  | 4.5 |  |  |  | 0%
| 2250 | 5 | 9.3.1.1.1 | BiCNET |  |  | 0 | 2015-03-02 | 2015-06-05 | 0.1 | 70 |  |  | 0.1 |  |  |  | 0%
| 2251 | 6 | 9.3.1.1.1.1 | 통합자금관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2252 | 6 | 9.3.1.1.1.2 | 자금수납 |  |  | -1 | 2015-03-30 | 2015-04-03 |  | 5 | [6 empty] | 0%
| 2253 | 6 | 9.3.1.1.1.3 | 자금수납-전자결제 |  |  | 0 | 2015-05-04 | 2015-05-08 |  | 5 | [6 empty] | 0%
| 2254 | 6 | 9.3.1.1.1.4 | 자금지급 |  |  | -1 | 2015-04-06 | 2015-04-10 |  | 5 | [6 empty] | 0%
| 2255 | 6 | 9.3.1.1.1.5 | 자금지급-전자결제 |  |  | 0 | 2015-05-04 | 2015-05-08 |  | 5 | [6 empty] | 0%
| 2256 | 6 | 9.3.1.1.1.6 | 자금지급-공과금/퇴직연금 |  |  | -1 | 2015-04-13 | 2015-04-17 |  | 5 | [6 empty] | 0%
| 2257 | 6 | 9.3.1.1.1.7 | 법인카드 |  |  | -1 | 2015-03-23 | 2015-03-27 |  | 5 | [6 empty] | 0%
| 2258 | 6 | 9.3.1.1.1.8 | 수출입외환 |  |  | 0 | 2015-05-25 | 2015-06-05 |  | 10 | [6 empty] | 0%
| 2259 | 6 | 9.3.1.1.1.9 | 부가서비스 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2260 | 6 | 9.3.1.1.1.10 | 사용자관리 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2261 | 6 | 9.3.1.1.1.11 | 특화서비스 |  |  | -1 | 2015-04-06 | 2015-04-10 |  | 5 | [6 empty] | 0%
| 2262 | 5 | 9.3.1.1.2 | BiCNET light |  |  | 0 | 2015-03-23 | 2015-05-22 | 0.03 | 45 |  |  | 0.03 |  |  |  | 0%
| 2263 | 6 | 9.3.1.1.2.1 | 계좌관리 |  |  | -1 | 2015-03-23 | 2015-03-27 |  | 5 | [6 empty] | 0%
| 2264 | 6 | 9.3.1.1.2.2 | 조회 |  |  | -1 | 2015-03-23 | 2015-03-27 |  | 5 | [6 empty] | 0%
| 2265 | 6 | 9.3.1.1.2.3 | 집금실행 |  |  | -1 | 2015-03-23 | 2015-03-27 |  | 5 | [6 empty] | 0%
| 2266 | 6 | 9.3.1.1.2.4 | 이체 |  |  | -1 | 2015-04-13 | 2015-04-17 |  | 5 | [6 empty] | 0%
| 2267 | 6 | 9.3.1.1.2.5 | 법인카드 |  |  | 0 | 2015-04-20 | 2015-04-24 |  | 5 | [6 empty] | 0%
| 2268 | 6 | 9.3.1.1.2.6 | 보고서 |  |  | 0 | 2015-04-20 | 2015-04-24 |  | 5 | [6 empty] | 0%
| 2269 | 6 | 9.3.1.1.2.7 | 사용자관리 |  |  | 0 | 2015-04-20 | 2015-04-24 |  | 5 | [6 empty] | 0%
| 2270 | 6 | 9.3.1.1.2.8 | 하나CBS |  |  | 0 | 2015-04-27 | 2015-05-01 |  | 5 | [6 empty] | 100%
| 2271 | 6 | 9.3.1.1.2.8 | 하나CBS -전자결제 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 100%
| 2272 | 6 | 9.3.1.1.2.8 | 하나CBS -외국환 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 100%
| 2273 | 6 | 9.3.1.1.2.9 | 하나CBS light |  |  | 0 | 2015-05-04 | 2015-05-08 |  | 5 | [6 empty] | 0%
| 2274 | 6 | 9.3.1.1.2.8 | 하나CBS light -전자결제 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 100%
| 2275 | 6 | 9.3.1.1.2.8 | 하나CBS light -외국환 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 100%
| 2276 | 6 | 9.3.1.1.2.10 | 특화서비스 |  |  | 0 | 2015-05-11 | 2015-05-15 |  | 5 | [6 empty] | 0%
| 2277 | 5 | 9.3.1.1.3 | In-House뱅킹PLUS |  |  | 0 | 2015-03-02 | 2015-06-05 | 0.2 | 70 |  |  | 0.2 |  |  |  | 0%
| 2278 | 6 | 9.3.1.1.3.1 | 업무관리 |  |  | -1 | 2015-03-02 | 2015-03-06 |  | 5 | [6 empty] | 0%
| 2279 | 6 | 9.3.1.1.3.2 | 조회¦보고서 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2280 | 6 | 9.3.1.1.3.3 | 자금관리 |  |  | -1 | 2015-03-23 | 2015-03-27 |  | 5 | [6 empty] | 0%
| 2281 | 6 | 9.3.1.1.3.4 | 지급¦이체 |  |  | -1 | 2015-03-30 | 2015-04-03 |  | 5 | [6 empty] | 0%
| 2282 | 6 | 9.3.1.1.3.5 | 지급¦이체 - 이체 |  |  | -1 | 2015-04-06 | 2015-04-10 |  | 5 | [6 empty] | 0%
| 2283 | 6 | 9.3.1.1.3.5 | 지급¦이체 - 외국환 |  |  | 0 | 2015-05-04 | 2015-05-08 |  | 5 | [6 empty] | 0%
| 2284 | 6 | 9.3.1.1.3.5 | 지급¦이체 - 공과금 |  |  | 0 | 2015-05-11 | 2015-05-15 |  | 5 | [6 empty] | 0%
| 2285 | 6 | 9.3.1.1.3.6 | 예금¦대출 |  |  | 0 | 2015-04-20 | 2015-04-24 |  | 5 | [6 empty] | 0%
| 2286 | 6 | 9.3.1.1.3.7 | 전자결제 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2287 | 6 | 9.3.1.1.3.7 | 전자결제 - 구매기업, 판매기업 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 0%
| 2288 | 6 | 9.3.1.1.3.8 | 수출입 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2289 | 6 | 9.3.1.1.3.9 | 법인카드 |  |  | -1 | 2015-04-13 | 2015-04-17 |  | 5 | [6 empty] | 0%
| 2290 | 6 | 9.3.1.1.3.10 | 시스템관리 |  |  | -1 | 2015-03-09 | 2015-03-13 |  | 5 | [6 empty] | 0%
| 2291 | 5 | 9.3.1.1.4 | GCMS PLUS |  |  | 0 | 2015-03-16 | 2015-05-22 | 0.04 | 50 |  |  | 0.04 |  |  |  | 0%
| 2292 | 6 | 9.3.1.1.4.1 | 은행계좌 |  |  | -1 | 2015-03-16 | 2015-03-20 |  | 5 | [6 empty] | 0%
| 2293 | 6 | 9.3.1.1.4.2 | 통합카드 |  |  | 0 | 2015-04-20 | 2015-04-24 |  | 5 | [6 empty] | 0%
| 2294 | 6 | 9.3.1.1.4.3 | 증권 |  |  | 0 | 2015-04-20 | 2015-04-24 |  | 5 | [6 empty] | 0%
| 2295 | 6 | 9.3.1.1.4.4 | 전자결제/어음 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 0%
| 2296 | 6 | 9.3.1.1.4.5 | 지급 |  |  | -1 | 2015-04-06 | 2015-04-10 |  | 5 | [6 empty] | 0%
| 2297 | 6 | 9.3.1.1.4.6 | 집금/배분 |  |  | 0 | 2015-05-04 | 2015-05-08 |  | 5 | [6 empty] | 0%
| 2298 | 6 | 9.3.1.1.4.7 | 전자세금계산서 |  |  | 0 | 2015-05-04 | 2015-05-08 |  | 5 | [6 empty] | 0%
| 2299 | 6 | 9.3.1.1.4.8 | 서비스관리 |  |  | 0 | 2015-04-27 | 2015-05-01 |  | 5 | [6 empty] | 0%
| 2300 | 6 | 9.3.1.1.4.9 | ERP연계관리 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 0%
| 2301 | 5 | 9.3.1.1.5 | In-House뱅킹MEGA |  |  | 0 | 2015-05-04 | 2015-05-29 | 0.01 | 20 |  |  | 0.01 |  |  |  | 0%
| 2302 | 6 | 9.3.1.1.5.1 | 통합조회 |  |  | 0 | 2015-05-04 | 2015-05-08 |  | 5 | [6 empty] | 0%
| 2303 | 6 | 9.3.1.1.5.2 | 지급관리 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 0%
| 2304 | 6 | 9.3.1.1.5.3 | 자금관리 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 0%
| 2305 | 6 | 9.3.1.1.5.4 | 법인카드 |  |  | 0 | 2015-05-11 | 2015-05-15 |  | 5 | [6 empty] | 100%
| 2306 | 6 | 9.3.1.1.5.5 | 글로벌서비스 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 100%
| 2307 | 6 | 9.3.1.1.5.6 | 서비스관리 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2308 | 6 | 9.3.1.1.5.7 | 시스템관리 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2309 | 5 | 9.3.1.1.6 | 인터넷자금관리 |  |  | 0 | 2015-04-27 | 2015-05-29 | 0.04 | 25 |  |  | 0.04 |  |  |  | 0%
| 2310 | 6 | 9.3.1.1.6.1 | 인터넷계좌통합 |  |  | 0 | 2015-04-27 | 2015-05-01 |  | 5 | [6 empty] | 0%
| 2311 | 6 | 9.3.1.1.6.2 | 집금 |  |  | 0 | 2015-05-04 | 2015-05-08 |  | 5 | [6 empty] | 0%
| 2312 | 6 | 9.3.1.1.6.3 | 배분 |  |  | 0 | 2015-05-04 | 2015-05-08 |  | 5 | [6 empty] | 0%
| 2313 | 6 | 9.3.1.1.6.4 | 법인카드관리 |  |  | 0 | 2015-05-11 | 2015-05-15 |  | 5 | [6 empty] | 0%
| 2314 | 6 | 9.3.1.1.6.5 | 서비스환경 |  |  | 0 | 2015-05-18 | 2015-05-22 |  | 5 | [6 empty] | 0%
| 2315 | 6 | 9.3.1.1.6.6 | ERP환경 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2316 | 5 | 9.3.1.1.7 | KEB Smart-Tax |  |  | 0 | 2015-05-25 | 2015-05-29 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2317 | 5 | 9.3.1.1.8 | 공통 |  |  | 0 | 2015-05-25 | 2015-05-29 | 0.02 | 5 |  |  | 0.02 |  |  |  | 0%
| 2318 | 4 | 9.3.1.2 | 배치프로그램구현 | 배치 프로그램 소스코드 |  | -1 |  |  |  | 0 | [6 empty] | 0%
| 2319 | 3 | 9.3.2 | 단위테스트 수행 |  |  | 0 | 2015-02-09 | 2015-06-12 | 1.5 | 90 |  |  | 1.5 |  |  |  | 0%
| 2320 | 4 | 9.3.2.1 | 단위테스트 수행 | 단위테스트 결과서 |  | 0 | 2015-02-09 | 2015-06-12 | 1.5 | 90 |  |  | 1.5 |  |  |  | 0%
| 2321 | 5 | 9.3.2.1.1 | BiCNET |  |  | 0 | 2015-05-25 | 2015-06-12 | 0.3 | 15 |  |  | 0.3 |  |  |  | 0%
| 2322 | 6 | 9.3.2.1.1.1 | 통합자금관리 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2323 | 6 | 9.3.2.1.1.2 | 자금수납 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2324 | 6 | 9.3.2.1.1.3 | 자금지급 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2325 | 6 | 9.3.2.1.1.4 | 법인카드 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 100%
| 2326 | 6 | 9.3.2.1.1.5 | 수출입외환 |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 100%
| 2327 | 6 | 9.3.2.1.1.6 | 부가서비스 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2328 | 6 | 9.3.2.1.1.7 | 사용자관리 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2329 | 6 | 9.3.2.1.1.8 | 특화서비스 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2330 | 5 | 9.3.2.1.2 | BiCNET light |  |  | 0 | 2015-05-25 | 2015-06-12 | 0.2 | 15 |  |  | 0.2 |  |  |  | 0%
| 2331 | 6 | 9.3.2.1.2.1 | 계좌관리 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2332 | 6 | 9.3.2.1.2.2 | 조회 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2333 | 6 | 9.3.2.1.2.3 | 집금실행 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2334 | 6 | 9.3.2.1.2.4 | 이체 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2335 | 6 | 9.3.2.1.2.5 | 법인카드 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2336 | 6 | 9.3.2.1.2.6 | 보고서 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2337 | 6 | 9.3.2.1.2.7 | 사용자관리 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2338 | 6 | 9.3.2.1.2.8 | 하나CBS |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 0%
| 2339 | 6 | 9.3.2.1.2.9 | 하나CBS light |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 0%
| 2340 | 6 | 9.3.2.1.2.10 | 특화서비스 |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 100%
| 2341 | 5 | 9.3.2.1.3 | In-House뱅킹PLUS |  |  | 0 | 2015-02-09 | 2015-06-12 | 0.45 | 90 |  |  | 0.45 |  |  |  | 0%
| 2342 | 6 | 9.3.2.1.3.1 | 업무관리 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2343 | 6 | 9.3.2.1.3.2 | 조회¦보고서 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2344 | 6 | 9.3.2.1.3.3 | 자금관리 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2345 | 6 | 9.3.2.1.3.4 | 지급¦이체 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2346 | 6 | 9.3.2.1.3.5 | 예금¦대출 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2347 | 6 | 9.3.2.1.3.6 | 전자결제 |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 0%
| 2348 | 6 | 9.3.2.1.3.7 | 수출입 |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 0%
| 2349 | 6 | 9.3.2.1.3.8 | 법인카드 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2350 | 6 | 9.3.2.1.3.9 | 시스템관리 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2351 | 5 | 9.3.2.1.4 | GCMS PLUS |  |  | 0 | 2015-05-25 | 2015-06-12 | 0.12 | 15 |  |  | 0.12 |  |  |  | 0%
| 2352 | 6 | 9.3.2.1.4.1 | 은행계좌 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2353 | 6 | 9.3.2.1.4.2 | 통합카드 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2354 | 6 | 9.3.2.1.4.3 | 증권 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2355 | 6 | 9.3.2.1.4.4 | 전자결제/어음 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2356 | 6 | 9.3.2.1.4.5 | 지급 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2357 | 6 | 9.3.2.1.4.6 | 집금/배분 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 100%
| 2358 | 6 | 9.3.2.1.4.7 | 전자세금계산서 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2359 | 6 | 9.3.2.1.4.8 | 서비스관리 |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 100%
| 2360 | 6 | 9.3.2.1.4.9 | ERP연계관리 |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 0%
| 2361 | 5 | 9.3.2.1.5 | In-House뱅킹MEGA |  |  | 0 | 2015-05-25 | 2015-06-12 | 0.22 | 15 |  |  | 0.22 |  |  |  | 100%
| 2362 | 6 | 9.3.2.1.5.1 | 통합조회 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2363 | 6 | 9.3.2.1.5.2 | 지급관리 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 100%
| 2364 | 6 | 9.3.2.1.5.3 | 법인카드 |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 100%
| 2365 | 6 | 9.3.2.1.5.4 | 글로벌서비스 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2366 | 6 | 9.3.2.1.5.5 | 서비스관리 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2367 | 5 | 9.3.2.1.6 | 인터넷자금관리 |  |  | 0 | 2015-05-25 | 2015-06-12 | 0.2 | 15 |  |  | 0.2 |  |  |  | 0%
| 2368 | 6 | 9.3.2.1.6.1 | 인터넷계좌통합 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2369 | 6 | 9.3.2.1.6.2 | 집금 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2370 | 6 | 9.3.2.1.6.3 | 배분 |  |  | 0 | 2015-06-01 | 2015-06-05 |  | 5 | [6 empty] | 0%
| 2371 | 6 | 9.3.2.1.6.4 | 법인카드관리 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2372 | 6 | 9.3.2.1.6.5 | 서비스환경 |  |  | 0 | 2015-05-25 | 2015-05-29 |  | 5 | [6 empty] | 0%
| 2373 | 6 | 9.3.2.1.6.6 | ERP환경 |  |  | 0 | 2015-06-08 | 2015-06-12 |  | 5 | [6 empty] | 0%
| 2374 | 5 | 9.3.2.1.7 | Smart-TAX |  |  | 0 | 2015-06-08 | 2015-06-12 | 0.01 | 5 |  |  | 0.01 |  |  |  | 0%
| 2375 | 1 | 10 | 전자금융 상품처리 / 콜센터 |  |  | 0 | 2015-02-09 | 2015-06-12 | 9 | 90 |  |  | 9 | 95 | 130 | 78.89% | 100%
| 2376 | 2 | 10.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 3 | 15 |  |  | 3 | 10 | 11 | 100% | 100%
| 2377 | 3 | 10.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-13 | 0.2 | 5 |  |  | 0.2 | 10 | 11 | 100% | 100%
| 2378 | 4 | 10.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-09 | 2015-02-13 | 0.2 | 5 |  |  | 0.2 | 10 | 11 | 100% | 0%
| 2379 | 3 | 10.1.2 | GAP 분석 |  |  | -1 | 2015-02-09 | 2015-02-17 | 1.3 | 7 |  |  | 1.3 | 5 | 4 | 100% | 100%
| 2380 | 4 | 10.1.2.1 | 메뉴 GAP분석(화면 GAP 분석) |  |  | -1 | 2015-02-09 | 2015-02-13 | 0.8 | 5 |  |  | 0.8 | 5 | 4 | 100% | 0%
| 2381 | 5 | 10.1.2.1.1 | KEBiNet | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-09 | 2015-02-13 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2382 | 5 | 10.1.2.1.2 | IN-HOUS | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-09 | 2015-02-13 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2383 | 5 | 10.1.2.1.3 | 기업약정관리 | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-09 | 2015-02-13 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2384 | 5 | 10.1.2.1.4 | 기업자금관리 | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-09 | 2015-02-13 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2385 | 5 | 10.1.2.1.5 | e-채널 공통 | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-09 | 2015-02-13 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2386 | 5 | 10.1.2.1.6 | e-채널 이용자관리 | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-09 | 2015-02-13 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2387 | 5 | 10.1.2.1.7 | e-채널 CBS관리 | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-09 | 2015-02-13 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2388 | 5 | 10.1.2.1.8 | 콜센타 | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-09 | 2015-02-13 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2389 | 4 | 10.1.2.2 | 테이블/속성 GAP분석 | 현행 시스템 분석서 | 상품처리개발자 | -1 | 2015-02-16 | 2015-02-17 | 0.5 | 2 |  |  | 0.5 | 2 | 1 | 100% | 0%
| 2390 | 3 | 10.1.3 | 통합요건정의 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.8 | 5 |  |  | 0.8 | 15 | 18 | 100% | 100%
| 2391 | 4 | 10.1.3.1 | 업무별 요건 분류 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.8 | 5 |  |  | 0.8 | 15 | 18 | 100% | 0%
| 2392 | 5 | 10.1.3.1.1 | KEBiNet | 요구사항추적표 요구사항정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2393 | 5 | 10.1.3.1.2 | IN-HOUS | 요구사항추적표 요구사항정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2394 | 5 | 10.1.3.1.3 | 기업약정관리 | 요구사항추적표 요구사항정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2395 | 5 | 10.1.3.1.4 | 기업자금관리 | 요구사항추적표 요구사항정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2396 | 5 | 10.1.3.1.5 | e-채널 공통 | 요구사항추적표 요구사항정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2397 | 5 | 10.1.3.1.6 | e-채널 이용자관리 | 요구사항추적표 요구사항정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2398 | 5 | 10.1.3.1.7 | e-채널 CBS관리 | 요구사항추적표 요구사항정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2399 | 5 | 10.1.3.1.8 | 콜센타 | 요구사항추적표 요구사항정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.1 | 5 |  |  | 0.1 | 15 | 18 | 100% | 0%
| 2400 | 3 | 10.1.5 | 논리모델구축 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.7 | 5 |  |  | 0.7 | 5 | 4 | 100% | 100%
| 2401 | 4 | 10.1.5.1 | 프로세스 모델링(신규분) |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.7 | 5 |  |  | 0.7 | 5 | 4 | 100% | 0%
| 2402 | 5 | 10.1.5.1.1 | KEBiNet | 프로세스정의서 인터페이스정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.0875 | 5 |  |  | 0.0875 | 15 | 18 | 100% | 0%
| 2403 | 5 | 10.1.5.1.2 | IN-HOUS | 프로세스정의서 인터페이스정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.0875 | 5 |  |  | 0.0875 | 15 | 18 | 100% | 0%
| 2404 | 5 | 10.1.5.1.3 | 기업약정관리 | 프로세스정의서 인터페이스정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.0875 | 5 |  |  | 0.0875 | 15 | 18 | 100% | 0%
| 2405 | 5 | 10.1.5.1.4 | 기업자금관리 | 프로세스정의서 인터페이스정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.0875 | 5 |  |  | 0.0875 | 15 | 18 | 100% | 0%
| 2406 | 5 | 10.1.5.1.5 | e-채널 공통 | 프로세스정의서 인터페이스정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.0875 | 5 |  |  | 0.0875 | 15 | 18 | 100% | 0%
| 2407 | 5 | 10.1.5.1.6 | e-채널 이용자관리 | 프로세스정의서 인터페이스정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.0875 | 5 |  |  | 0.0875 | 15 | 18 | 100% | 0%
| 2408 | 5 | 10.1.5.1.7 | e-채널 CBS관리 | 프로세스정의서 인터페이스정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.0875 | 5 |  |  | 0.0875 | 15 | 18 | 100% | 0%
| 2409 | 5 | 10.1.5.1.8 | 콜센타 | 프로세스정의서 인터페이스정의서 | 상품처리개발자 | -1 | 2015-02-23 | 2015-02-27 | 0.0875 | 5 |  |  | 0.0875 | 15 | 18 | 100% | 0%
| 2410 | 2 | 10.2 | 설계 |  |  | -1 | 2015-03-02 | 2015-03-13 | 3 | 10 |  |  | 3 | 9 | 10 | 100% | 100%
| 2411 | 3 | 10.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-02 | 2015-03-13 | 1.5 | 10 |  |  | 1.5 | 9 | 10 | 100% | 100%
| 2412 | 4 | 10.2.1.1 | 화면설계(신규분) | 화면목록 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.7 | 10 |  |  | 0.7 | 9 | 10 | 100% | 0%
| 2413 | 5 | 10.2.1.1.1 | KEBiNet | 화면설계서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0875 | 10 |  |  | 0.0875 | 9 | 10 | 100% | 0%
| 2414 | 5 | 10.2.1.1.2 | IN-HOUS | 화면설계서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0875 | 10 |  |  | 0.0875 | 9 | 10 | 100% | 0%
| 2415 | 5 | 10.2.1.1.3 | 기업약정관리 | 화면설계서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0875 | 10 |  |  | 0.0875 | 9 | 10 | 100% | 0%
| 2416 | 5 | 10.2.1.1.4 | 기업자금관리 | 화면설계서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0875 | 10 |  |  | 0.0875 | 9 | 10 | 100% | 0%
| 2417 | 5 | 10.2.1.1.5 | e-채널 공통 | 화면설계서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0875 | 10 |  |  | 0.0875 | 9 | 10 | 100% | 0%
| 2418 | 5 | 10.2.1.1.6 | e-채널 이용자관리 | 화면설계서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0875 | 10 |  |  | 0.0875 | 9 | 10 | 100% | 0%
| 2419 | 5 | 10.2.1.1.7 | e-채널 CBS관리 | 화면설계서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0875 | 10 |  |  | 0.0875 | 9 | 10 | 100% | 0%
| 2420 | 5 | 10.2.1.1.8 | 콜센타 | 화면설계서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0875 | 10 |  |  | 0.0875 | 9 | 10 | 100% | 0%
| 2421 | 4 | 10.2.1.2 | 프로그램 설계(신규분) | 프로그램 목록 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.8 | 5 |  |  | 0.8 | 4 | 3 | 100% | 0%
| 2422 | 5 | 10.2.1.2.1 | KEBiNet | 프로그램 사양서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.1 | 5 |  |  | 0.1 | 4 | 3 | 100% | 0%
| 2423 | 5 | 10.2.1.2.2 | IN-HOUS | 프로그램 사양서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.1 | 5 |  |  | 0.1 | 4 | 3 | 100% | 0%
| 2424 | 5 | 10.2.1.2.3 | 기업약정관리 | 프로그램 사양서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.1 | 5 |  |  | 0.1 | 4 | 3 | 100% | 0%
| 2425 | 5 | 10.2.1.2.4 | 기업자금관리 | 프로그램 사양서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.1 | 5 |  |  | 0.1 | 4 | 3 | 100% | 0%
| 2426 | 5 | 10.2.1.2.5 | e-채널 공통 | 프로그램 사양서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.1 | 5 |  |  | 0.1 | 4 | 3 | 100% | 0%
| 2427 | 5 | 10.2.1.2.6 | e-채널 이용자관리 | 프로그램 사양서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.1 | 5 |  |  | 0.1 | 4 | 3 | 100% | 0%
| 2428 | 5 | 10.2.1.2.7 | e-채널 CBS관리 | 프로그램 사양서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.1 | 5 |  |  | 0.1 | 4 | 3 | 100% | 0%
| 2429 | 5 | 10.2.1.2.8 | 콜센타 | 프로그램 사양서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.1 | 5 |  |  | 0.1 | 4 | 3 | 100% | 0%
| 2430 | 3 | 10.2.2 | 통합전문설계 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.4 | 10 |  |  | 0.4 | 9 | 10 | 100% | 100%
| 2431 | 4 | 10.2.2.1 | 전문매핑 | 전문목록 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.4 | 10 |  |  | 0.4 | 9 | 10 | 100% | 0%
| 2432 | 5 | 10.2.2.1.1 | KEBiNet | 전문매핑정의서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 9 | 10 | 100% | 0%
| 2433 | 5 | 10.2.2.1.2 | IN-HOUS | 전문매핑정의서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 9 | 10 | 100% | 0%
| 2434 | 5 | 10.2.2.1.3 | 기업약정관리 | 전문매핑정의서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 9 | 10 | 100% | 0%
| 2435 | 5 | 10.2.2.1.4 | 기업자금관리 | 전문매핑정의서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 9 | 10 | 100% | 0%
| 2436 | 5 | 10.2.2.1.5 | e-채널 공통 | 전문매핑정의서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 9 | 10 | 100% | 0%
| 2437 | 5 | 10.2.2.1.6 | e-채널 이용자관리 | 전문매핑정의서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 9 | 10 | 100% | 0%
| 2438 | 5 | 10.2.2.1.7 | e-채널 CBS관리 | 전문매핑정의서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 9 | 10 | 100% | 0%
| 2439 | 5 | 10.2.2.1.8 | 콜센타 | 전문매핑정의서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 9 | 10 | 100% | 0%
| 2440 | 3 | 10.2.3 | 배치프로세스 설계 |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.3 | 5 |  |  | 0.3 | 4 | 3 | 100% | 100%
| 2441 | 4 | 10.2.3.1 | 배치프로그램 설계(신규분) |  |  | -1 | 2015-03-09 | 2015-03-13 | 0.3 | 5 |  |  | 0.3 | 4 | 3 | 100% | 0%
| 2442 | 5 | 10.2.3.1.1 | KEBiNet | 배치프로세스 정의서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.0375 | 5 |  |  | 0.0375 | 9 | 10 | 100% | 0%
| 2443 | 5 | 10.2.3.1.2 | IN-HOUS | 배치프로세스 정의서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.0375 | 5 |  |  | 0.0375 | 9 | 10 | 100% | 0%
| 2444 | 5 | 10.2.3.1.3 | 기업약정관리 | 배치프로세스 정의서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.0375 | 5 |  |  | 0.0375 | 9 | 10 | 100% | 0%
| 2445 | 5 | 10.2.3.1.4 | 기업자금관리 | 배치프로세스 정의서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.0375 | 5 |  |  | 0.0375 | 9 | 10 | 100% | 0%
| 2446 | 5 | 10.2.3.1.5 | e-채널 공통 | 배치프로세스 정의서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.0375 | 5 |  |  | 0.0375 | 9 | 10 | 100% | 0%
| 2447 | 5 | 10.2.3.1.6 | e-채널 이용자관리 | 배치프로세스 정의서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.0375 | 5 |  |  | 0.0375 | 9 | 10 | 100% | 0%
| 2448 | 5 | 10.2.3.1.7 | e-채널 CBS관리 | 배치프로세스 정의서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.0375 | 5 |  |  | 0.0375 | 9 | 10 | 100% | 0%
| 2449 | 5 | 10.2.3.1.8 | 콜센타 | 배치프로세스 정의서 | 상품처리개발자 | -1 | 2015-03-09 | 2015-03-13 | 0.0375 | 5 |  |  | 0.0375 | 9 | 10 | 100% | 0%
| 2450 | 3 | 10.2.4 | 통합 DB 설계 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.75 | 10 |  |  | 0.75 | 9 | 10 | 100% | 100%
| 2451 | 4 | 10.2.4.1 | 양행 테이블/속성 매핑 | 테이블매핑정의서 | 상품처리개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.4 | 10 |  |  | 0.4 | 9 | 10 | 100% | 0%
| 2452 | 4 | 10.2.4.2 | 통합 데이터베이스 모델링 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.4 | 10 |  |  | 0.4 | 9 | 10 | 100% | 0%
| 2453 | 2 | 10.3 | 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 3 | 65 |  |  | 3 | 75 | 102 | 55.38% | 100%
| 2454 | 3 | 10.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 1.8 | 65 |  |  | 1.8 | 75 | 102 | 55.38% | 100%
| 2455 | 4 | 10.3.1.1 | 온라인 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 1.6 | 65 |  |  | 1.6 | 75 | 102 | 55.38% | 0%
| 2456 | 5 | 10.3.1.1.1 | KEBiNet | 온라인 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.2 | 65 |  |  | 0.2 | 65 | 88 | 55.38% | 0%
| 2457 | 5 | 10.3.1.1.2 | IN-HOUS | 온라인 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.2 | 65 |  |  | 0.2 | 65 | 88 | 55.38% | 0%
| 2458 | 5 | 10.3.1.1.3 | 기업약정관리 | 온라인 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.2 | 65 |  |  | 0.2 | 65 | 88 | 55.38% | 0%
| 2459 | 5 | 10.3.1.1.4 | 기업자금관리 | 온라인 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.2 | 65 |  |  | 0.2 | 65 | 88 | 55.38% | 0%
| 2460 | 5 | 10.3.1.1.5 | 통합로그인 | 온라인 프로그램 소스코드 | 상품처리개발자 | -1 | 2015-03-02 | 2015-04-17 | 0.1 | 35 |  |  | 0.1 | 75 | 102 | 100% | 0%
| 2461 | 5 | 10.3.1.1.6 | e-채널 공통 | 온라인 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-03-02 | 2015-06-12 | 0.2 | 75 |  |  | 0.2 | 75 | 102 | 66.67% | 0%
| 2462 | 5 | 10.3.1.1.7 | e-채널 이용자관리 | 온라인 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.2 | 65 |  |  | 0.2 | 65 | 88 | 55.38% | 0%
| 2463 | 5 | 10.3.1.1.8 | e-채널 CBS관리 | 온라인 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.2 | 65 |  |  | 0.2 | 65 | 88 | 55.38% | 0%
| 2464 | 5 | 10.3.1.1.9 | 콜센타 | 온라인 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.1 | 65 |  |  | 0.1 | 65 | 88 | 55.38% | 0%
| 2465 | 4 | 10.3.1.2 | 배치 프로그램 구현 |  |  | 0 | 2015-04-06 | 2015-06-12 | 0.2 | 50 |  |  | 0.2 | 20 | 25 | 30% | 0%
| 2466 | 5 | 10.3.1.2.1 | KEBiNet | 배치 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.025 | 50 |  |  | 0.025 | 65 | 88 | 30% | 0%
| 2467 | 5 | 10.3.1.2.2 | IN-HOUS | 배치 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.025 | 50 |  |  | 0.025 | 65 | 88 | 30% | 0%
| 2468 | 5 | 10.3.1.2.3 | 기업약정관리 | 배치 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.025 | 50 |  |  | 0.025 | 65 | 88 | 30% | 0%
| 2469 | 5 | 10.3.1.2.4 | 기업자금관리 | 배치 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.025 | 50 |  |  | 0.025 | 65 | 88 | 30% | 0%
| 2470 | 5 | 10.3.1.2.5 | e-채널 공통 | 배치 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.025 | 50 |  |  | 0.025 | 75 | 102 | 30% | 0%
| 2471 | 5 | 10.3.1.2.6 | e-채널 이용자관리 | 배치 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.025 | 50 |  |  | 0.025 | 65 | 88 | 30% | 0%
| 2472 | 5 | 10.3.1.2.7 | e-채널 CBS관리 | 배치 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.025 | 50 |  |  | 0.025 | 65 | 88 | 30% | 0%
| 2473 | 5 | 10.3.1.2.8 | 콜센타 | 배치 프로그램 소스코드 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.025 | 50 |  |  | 0.025 | 65 | 88 | 30% | 0%
| 2474 | 3 | 10.3.2 | 단위테스트수행 |  |  | 0 | 2015-04-06 | 2015-06-12 | 1.2 | 50 |  |  | 1.2 | 75 | 102 | 30% | 100%
| 2475 | 4 | 10.3.2.1 | 단위테스트수행 |  |  | 0 | 2015-04-06 | 2015-06-12 | 1.2 | 50 |  |  | 1.2 | 75 | 102 | 30% | 0%
| 2476 | 5 | 10.3.2.1.1 | KEBiNet | 단위테스트 결과서 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.15 | 50 |  |  | 0.15 | 65 | 88 | 30% | 0%
| 2477 | 5 | 10.3.2.1.2 | IN-HOUS | 단위테스트 결과서 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.15 | 50 |  |  | 0.15 | 65 | 88 | 30% | 0%
| 2478 | 5 | 10.3.2.1.3 | 기업약정관리 | 단위테스트 결과서 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.15 | 50 |  |  | 0.15 | 65 | 88 | 30% | 0%
| 2479 | 5 | 10.3.2.1.4 | 기업자금관리 | 단위테스트 결과서 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.15 | 50 |  |  | 0.15 | 65 | 88 | 30% | 0%
| 2480 | 5 | 10.3.2.1.5 | e-채널 공통 | 단위테스트 결과서 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.15 | 50 |  |  | 0.15 | 75 | 102 | 30% | 0%
| 2481 | 5 | 10.3.2.1.6 | e-채널 이용자관리 | 단위테스트 결과서 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.15 | 50 |  |  | 0.15 | 65 | 88 | 30% | 0%
| 2482 | 5 | 10.3.2.1.7 | e-채널 CBS관리 | 단위테스트 결과서 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.15 | 50 |  |  | 0.15 | 65 | 88 | 30% | 0%
| 2483 | 5 | 10.3.2.1.8 | 콜센타 | 단위테스트 결과서 | 상품처리개발자 | 0 | 2015-04-06 | 2015-06-12 | 0.15 | 50 |  |  | 0.15 | 65 | 88 | 30% | 0%
| 2484 | 1 | 11 | 개인 스마트 뱅킹 |  |  | 0 | 2015-02-09 | 2015-06-12 | 4 | 90 |  |  | 4 |  |  | 78.89% | 100%
| 2485 | 2 | 11.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-03-13 | 1.3 | 25 |  |  | 1.3 |  |  | 100% | 100%
| 2486 | 3 | 11.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.2 | 15 |  |  | 0.2 |  |  | 100% | 100%
| 2487 | 4 | 11.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 | 스마트관리 담당자 | -1 | 2015-02-09 | 2015-02-27 | 0.09 | 15 |  |  | 0.09 |  |  | 100% | 0%
| 2488 | 5 | 11.1.1.1.1 | 조회/이체 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2489 | 5 | 11.1.1.1.2 | 예금가입 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2490 | 5 | 11.1.1.1.3 | 펀드/가입 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2491 | 5 | 11.1.1.1.4 | 대출/대출신청 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2492 | 5 | 11.1.1.1.5 | 인증센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2493 | 5 | 11.1.1.1.6 | 외환 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2494 | 5 | 11.1.1.1.7 | 신용카드 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2495 | 5 | 11.1.1.1.8 | 지로/공과금 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2496 | 5 | 11.1.1.1.9 | 퇴직연금 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2497 | 5 | 11.1.1.1.10 | 부가서비스/보안센터/금융계산기 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2498 | 5 | 11.1.1.1.11 | 환경설정/기타기능 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0081818 | 15 |  |  | 0.0081818 |  |  | 100%
| 2499 | 3 | 11.1.2 | GAP 분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.26 | 15 |  |  | 0.26 |  |  | 100% | 100%
| 2500 | 4 | 11.1.2.1 | 메뉴 GAP분석 | 현행 시스템 분석서 | 스마트관리 담당자 | -1 | 2015-02-09 | 2015-02-27 | 0.156 | 15 |  |  | 0.156 |  |  | 100% | 0%
| 2501 | 5 | 11.1.2.1.1 | 조회/이체 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2502 | 5 | 11.1.2.1.2 | 예금가입 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2503 | 5 | 11.1.2.1.3 | 펀드/가입 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2504 | 5 | 11.1.2.1.4 | 대출/대출신청 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2505 | 5 | 11.1.2.1.5 | 인증센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2506 | 5 | 11.1.2.1.6 | 외환 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2507 | 5 | 11.1.2.1.7 | 신용카드 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2508 | 5 | 11.1.2.1.8 | 지로/공과금 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2509 | 5 | 11.1.2.1.9 | 퇴직연금 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2510 | 5 | 11.1.2.1.10 | 부가서비스/보안센터/금융계산기 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2511 | 5 | 11.1.2.1.11 | 환경설정/기타기능 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0036364 | 15 |  |  | 0.0036364 |  |  | 100%
| 2512 | 4 | 11.1.2.2 | 전문 GAP분석 | 현행 시스템 분석서 | 스마트뱅킹 개발자 | -1 | 2015-02-09 | 2015-02-27 | 0.104 | 15 |  |  | 0.104 |  |  | 100% | 0%
| 2513 | 5 | 11.1.2.2.1 | 조회/이체 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2514 | 5 | 11.1.2.2.2 | 예금가입 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2515 | 5 | 11.1.2.2.3 | 펀드/가입 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2516 | 5 | 11.1.2.2.4 | 대출/대출신청 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2517 | 5 | 11.1.2.2.5 | 인증센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2518 | 5 | 11.1.2.2.6 | 외환 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2519 | 5 | 11.1.2.2.7 | 신용카드 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2520 | 5 | 11.1.2.2.8 | 지로/공과금 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2521 | 5 | 11.1.2.2.9 | 퇴직연금 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2522 | 5 | 11.1.2.2.10 | 부가서비스/보안센터/금융계산기 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2523 | 5 | 11.1.2.2.11 | 환경설정/기타기능 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.0018182 | 15 |  |  | 0.0018182 |  |  | 100%
| 2524 | 3 | 11.1.3 | 통합업무확정 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.26 | 5 |  |  | 0.26 |  |  | 100% | 100%
| 2525 | 4 | 11.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 | 스마트관리 담당자 | -1 | 2015-02-23 | 2015-02-27 | 0.26 | 5 |  |  | 0.26 |  |  | 100% | 0%
| 2526 | 5 | 11.1.3.1.1 | 조회/이체 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2527 | 5 | 11.1.3.1.2 | 예금가입 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2528 | 5 | 11.1.3.1.3 | 펀드/가입 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2529 | 5 | 11.1.3.1.4 | 대출/대출신청 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2530 | 5 | 11.1.3.1.5 | 인증센터 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2531 | 5 | 11.1.3.1.6 | 외환 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2532 | 5 | 11.1.3.1.7 | 신용카드 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2533 | 5 | 11.1.3.1.8 | 지로/공과금 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2534 | 5 | 11.1.3.1.9 | 퇴직연금 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2535 | 5 | 11.1.3.1.10 | 부가서비스/보안센터/금융계산기 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2536 | 5 | 11.1.3.1.11 | 환경설정/기타기능 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0034091 | 5 |  |  | 0.0034091 |  |  | 100%
| 2537 | 3 | 11.1.4 | 통합요건정의 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.46 | 10 |  |  | 0.46 |  |  | 100% | 100%
| 2538 | 4 | 11.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 스마트뱅킹 개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0375 | 10 |  |  | 0.0375 |  |  | 100% | 0%
| 2539 | 5 | 11.1.4.1.1 | 조회/이체 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2540 | 5 | 11.1.4.1.2 | 예금가입 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2541 | 5 | 11.1.4.1.3 | 펀드/가입 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2542 | 5 | 11.1.4.1.4 | 대출/대출신청 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2543 | 5 | 11.1.4.1.5 | 인증센터 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2544 | 5 | 11.1.4.1.6 | 외환 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2545 | 5 | 11.1.4.1.7 | 신용카드 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2546 | 5 | 11.1.4.1.8 | 지로/공과금 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2547 | 5 | 11.1.4.1.9 | 퇴직연금 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2548 | 5 | 11.1.4.1.10 | 부가서비스/보안센터/금융계산기 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2549 | 5 | 11.1.4.1.11 | 환경설정/기타기능 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0034091 | 10 |  |  | 0.0034091 |  |  | 100%
| 2550 | 3 | 11.1.5 | 논리모델구축 |  |  | -1 | 2015-03-11 | 2015-03-13 | 0.13 | 3 |  |  | 0.13 |  |  | 100% | 100%
| 2551 | 4 | 11.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 | 스마트뱅킹 개발자 | -1 | 2015-03-11 | 2015-03-13 | 0.13 | 3 |  |  | 0.13 |  |  | 100% | 0%
| 2552 | 2 | 11.2 | 설계 |  |  | -1 | 2015-03-09 | 2015-03-31 | 1.3 | 17 |  |  | 1.3 |  |  | 100% | 100%
| 2553 | 3 | 11.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-09 | 2015-03-25 | 1.04 | 13 |  |  | 1.04 |  |  | 100% | 100%
| 2554 | 4 | 11.2.1.1 | 화면설계 | 화면설계서 | 스마트관리 담당자 | -1 | 2015-03-09 | 2015-03-25 | 0.728 | 13 |  |  | 0.728 |  |  | 100% | 0%
| 2555 | 5 | 11.2.1.1.1 | 조회/이체 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2556 | 5 | 11.2.1.1.2 | 예금가입 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2557 | 5 | 11.2.1.1.3 | 펀드/가입 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2558 | 5 | 11.2.1.1.4 | 대출/대출신청 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2559 | 5 | 11.2.1.1.5 | 인증센터 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2560 | 5 | 11.2.1.1.6 | 외환 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2561 | 5 | 11.2.1.1.7 | 신용카드 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2562 | 5 | 11.2.1.1.8 | 지로/공과금 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2563 | 5 | 11.2.1.1.9 | 퇴직연금 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2564 | 5 | 11.2.1.1.10 | 부가서비스/보안센터/금융계산기 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2565 | 5 | 11.2.1.1.11 | 환경설정/기타기능 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0010489 | 13 |  |  | 0.0010489 |  |  | 100%
| 2566 | 4 | 11.2.1.2 | 프로그램 설계 | 프로그램 목록 프로그램 사양서 | 스마트뱅킹 개발자 | -1 | 2015-03-16 | 2015-03-25 | 0.312 | 8 |  |  | 0.312 |  |  | 100% | 0%
| 2567 | 5 | 11.2.1.2.1 | 조회/이체 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2568 | 5 | 11.2.1.2.2 | 예금가입 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2569 | 5 | 11.2.1.2.3 | 펀드/가입 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2570 | 5 | 11.2.1.2.4 | 대출/대출신청 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2571 | 5 | 11.2.1.2.5 | 인증센터 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2572 | 5 | 11.2.1.2.6 | 외환 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2573 | 5 | 11.2.1.2.7 | 신용카드 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2574 | 5 | 11.2.1.2.8 | 지로/공과금 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2575 | 5 | 11.2.1.2.9 | 퇴직연금 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2576 | 5 | 11.2.1.2.10 | 부가서비스/보안센터/금융계산기 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2577 | 5 | 11.2.1.2.11 | 환경설정/기타기능 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0010489 | 8 |  |  | 0.0010489 |  |  | 100%
| 2578 | 3 | 11.2.2 | 통합전문설계 |  |  | -1 | 2015-03-26 | 2015-03-31 | 0.26 | 4 |  |  | 0.26 |  |  | 100% | 100%
| 2579 | 4 | 11.2.2.1 | 전문매핑 | 전문목록 | 스마트뱅킹 개발자 | -1 | 2015-03-26 | 2015-03-31 | 0.26 | 4 |  |  | 0.26 |  |  | 100% | 0%
| 2580 | 2 | 11.3 | 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 1.4 | 65 |  |  | 1.4 |  |  | 55.38% | 100%
| 2581 | 3 | 11.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.98 | 65 |  |  | 0.98 |  |  | 55.38% | 100%
| 2582 | 4 | 11.3.1.1 | 온라인 프로그램 구현 | 온라인 프로그램 소스코드 | 스마트뱅킹 개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.011538 | 65 |  |  | 0.011538 |  |  | 55.38% | 0%
| 2583 | 5 | 11.3.1.1.1 | 통합 로그인/인증센터 개발 |  |  | -1 | 2015-03-16 | 2015-03-24 | 0.0009615 | 7 |  |  | 0.0009615 |  |  | 100%
| 2584 | 5 | 11.3.1.1.2 | 다국어 처리 방식 대응 개발 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.0009615 | 5 |  |  | 0.0009615 |  |  | 100%
| 2585 | 5 | 11.3.1.1.3 | 고객센터/환경설정 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.0009615 | 5 |  |  | 0.0009615 |  |  | 100%
| 2586 | 5 | 11.3.1.1.4 | 조회 |  |  | -1 | 2015-04-01 | 2015-04-07 | 0.0009615 | 5 |  |  | 0.0009615 |  |  | 100%
| 2587 | 5 | 11.3.1.1.5 | 이체 |  |  | -1 | 2015-04-08 | 2015-04-17 | 0.0009615 | 8 |  |  | 0.0009615 |  |  | 100%
| 2588 | 5 | 11.3.1.1.6 | 예금/펀드가입/대출 |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.0009615 | 10 |  |  | 0.0009615 |  |  | 10%
| 2589 | 5 | 11.3.1.1.7 | 신용카드/지로/공과금 |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.0009615 | 10 |  |  | 0.0009615 |  |  | 10%
| 2590 | 5 | 11.3.1.1.8 | 퇴직연금 |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.0009615 | 10 |  |  | 0.0009615 |  |  | 10%
| 2591 | 5 | 11.3.1.1.9 | 부가서비스/보안센터/금융계산기 |  |  | 0 | 2015-05-04 | 2015-05-15 | 0.0009615 | 10 |  |  | 0.0009615 |  |  | 0%
| 2592 | 5 | 11.3.1.1.10 | My정보관리 |  |  | 0 | 2015-05-04 | 2015-05-15 | 0.0009615 | 10 |  |  | 0.0009615 |  |  | 0%
| 2593 | 5 | 11.3.1.1.11 | 환전클럽/송금클럽 |  |  | 0 | 2015-05-18 | 2015-05-26 | 0.0009615 | 7 |  |  | 0.0009615 |  |  | 0%
| 2594 | 5 | 11.3.1.1.12 | 외환/외화송금/매매 |  |  | 0 | 2015-05-27 | 2015-06-12 | 0.0009615 | 13 |  |  | 0.0009615 |  |  | 0%
| 2595 | 3 | 11.3.2 | 단위테스트 수행 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.42 | 65 |  |  | 0.42 |  |  | 55.38% | 100%
| 2596 | 4 | 11.3.2.1 | 단위테스트 수행 | 단위테스트 결과서 | 스마트뱅킹 개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.05 | 65 |  |  | 0.05 |  |  | 55.38% | 0%
| 2597 | 5 | 11.3.2.1.1 | 통합 로그인/인증센터 테스트 |  |  | -1 | 2015-03-16 | 2015-03-24 | 0.0041667 | 7 |  |  | 0.0041667 |  |  | 100%
| 2598 | 5 | 11.3.2.1.2 | 다국어 처리 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.0041667 | 5 |  |  | 0.0041667 |  |  | 100%
| 2599 | 5 | 11.3.2.1.3 | 고객센터/환경설정 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.0041667 | 5 |  |  | 0.0041667 |  |  | 100%
| 2600 | 5 | 11.3.2.1.4 | 조회 |  |  | -1 | 2015-04-01 | 2015-04-07 | 0.0041667 | 5 |  |  | 0.0041667 |  |  | 100%
| 2601 | 5 | 11.3.2.1.5 | 이체 |  |  | -1 | 2015-04-08 | 2015-04-17 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2602 | 5 | 11.3.2.1.6 | 예금/펀드가입/대출 |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.0041667 | 10 |  |  | 0.0041667 |  |  | 10%
| 2603 | 5 | 11.3.2.1.7 | 신용카드/지로/공과금 |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.0041667 | 10 |  |  | 0.0041667 |  |  | 10%
| 2604 | 5 | 11.3.2.1.8 | 퇴직연금 |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.0041667 | 10 |  |  | 0.0041667 |  |  | 10%
| 2605 | 5 | 11.3.2.1.9 | 부가서비스/보안센터/금융계산기 |  |  | 0 | 2015-05-04 | 2015-05-15 | 0.0041667 | 10 |  |  | 0.0041667 |  |  | 0%
| 2606 | 5 | 11.3.2.1.10 | My정보관리 |  |  | 0 | 2015-05-04 | 2015-05-15 | 0.0041667 | 10 |  |  | 0.0041667 |  |  | 0%
| 2607 | 5 | 11.3.2.1.11 | 환전클럽/송금클럽 |  |  | 0 | 2015-05-18 | 2015-05-26 | 0.0041667 | 7 |  |  | 0.0041667 |  |  | 0%
| 2608 | 5 | 11.3.2.1.12 | 외환/외화송금/매매 |  |  | 0 | 2015-05-27 | 2015-06-12 | 0.0041667 | 13 |  |  | 0.0041667 |  |  | 0%
| 2609 | 1 | 12 | 스마트 환율 |  |  | 0 | 2015-02-09 | 2015-06-12 | 4 | 90 |  |  | 4 |  |  | 78.89% | 100%
| 2610 | 2 | 12.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-03-13 | 1.3 | 25 |  |  | 1.3 |  |  | 100% | 100%
| 2611 | 3 | 12.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.2 | 15 |  |  | 0.2 |  |  | 100% | 100%
| 2612 | 4 | 12.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 | 스마트관리 담당자 | -1 | 2015-02-09 | 2015-02-27 | 0.09 | 15 |  |  | 0.09 |  |  | 100% | 0%
| 2613 | 5 | 12.1.1.1.1 | 환율조회 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.018 | 15 |  |  | 0.018 |  |  | 100%
| 2614 | 5 | 12.1.1.1.2 | 계산기 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.018 | 15 |  |  | 0.018 |  |  | 100%
| 2615 | 5 | 12.1.1.1.3 | 설정 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.018 | 15 |  |  | 0.018 |  |  | 100%
| 2616 | 5 | 12.1.1.1.4 | 위젯 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.018 | 15 |  |  | 0.018 |  |  | 100%
| 2617 | 5 | 12.1.1.1.5 | 고객센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.018 | 15 |  |  | 0.018 |  |  | 100%
| 2618 | 3 | 12.1.2 | GAP 분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.26 | 15 |  |  | 0.26 |  |  | 100% | 100%
| 2619 | 4 | 12.1.2.1 | 메뉴 GAP분석 | 현행 시스템 분석서 | 스마트관리 담당자 | -1 | 2015-02-09 | 2015-02-27 | 0.156 | 15 |  |  | 0.156 |  |  | 100% | 0%
| 2620 | 5 | 12.1.2.1.1 | 환율조회 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2621 | 5 | 12.1.2.1.2 | 계산기 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2622 | 5 | 12.1.2.1.3 | 설정 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2623 | 5 | 12.1.2.1.4 | 위젯 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2624 | 5 | 12.1.2.1.5 | 고객센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2625 | 4 | 12.1.2.2 | 전문 GAP분석 | 현행 시스템 분석서 | 스마트뱅킹 개발자 | -1 | 2015-02-09 | 2015-02-27 | 0.104 | 15 |  |  | 0.104 |  |  | 100% | 0%
| 2626 | 5 | 12.1.2.2.1 | 스마트 환율앱 전문 분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.104 | 15 |  |  | 0.104 |  |  | 100%
| 2627 | 3 | 12.1.3 | 통합업무확정 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.26 | 5 |  |  | 0.26 |  |  | 100% | 100%
| 2628 | 4 | 12.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 | 스마트관리 담당자 | -1 | 2015-02-23 | 2015-02-27 | 0.045 | 5 |  |  | 0.045 |  |  | 100% | 0%
| 2629 | 5 | 12.1.3.1.1 | 메인화면 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0075 | 5 |  |  | 0.0075 |  |  | 100%
| 2630 | 5 | 12.1.3.1.2 | 계산기 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0075 | 5 |  |  | 0.0075 |  |  | 100%
| 2631 | 5 | 12.1.3.1.3 | 사이버환전(안내,바로가기) |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0075 | 5 |  |  | 0.0075 |  |  | 100%
| 2632 | 5 | 12.1.3.1.4 | 고객센터 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0075 | 5 |  |  | 0.0075 |  |  | 100%
| 2633 | 5 | 12.1.3.1.5 | 환율 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0075 | 5 |  |  | 0.0075 |  |  | 100%
| 2634 | 5 | 12.1.3.1.6 | 환율 위젯 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.0075 | 5 |  |  | 0.0075 |  |  | 100%
| 2635 | 3 | 12.1.4 | 통합요건정의 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.46 | 10 |  |  | 0.46 |  |  | 100% | 100%
| 2636 | 4 | 12.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 스마트뱅킹 개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.09 | 10 |  |  | 0.09 |  |  | 100% | 0%
| 2637 | 5 | 12.1.4.1.1 | 메인화면 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.015 | 10 |  |  | 0.015 |  |  | 100%
| 2638 | 5 | 12.1.4.1.2 | 계산기 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.015 | 10 |  |  | 0.015 |  |  | 100%
| 2639 | 5 | 12.1.4.1.3 | 사이버환전(안내,바로가기) |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.015 | 10 |  |  | 0.015 |  |  | 100%
| 2640 | 5 | 12.1.4.1.4 | 고객센터 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.015 | 10 |  |  | 0.015 |  |  | 100%
| 2641 | 5 | 12.1.4.1.5 | 환율 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.015 | 10 |  |  | 0.015 |  |  | 100%
| 2642 | 5 | 12.1.4.1.6 | 환율 위젯 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.015 | 10 |  |  | 0.015 |  |  | 100%
| 2643 | 3 | 12.1.5 | 논리모델구축 |  |  | -1 | 2015-03-11 | 2015-03-13 | 0.13 | 3 |  |  | 0.13 |  |  | 100% | 100%
| 2644 | 4 | 12.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 | 스마트뱅킹 개발자 | -1 | 2015-03-11 | 2015-03-13 | 0.13 | 3 |  |  | 0.13 |  |  | 100% | 0%
| 2645 | 2 | 12.2 | 설계 |  |  | -1 | 2015-03-09 | 2015-03-31 | 1.3 | 17 |  |  | 1.3 |  |  | 100% | 100%
| 2646 | 3 | 12.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-09 | 2015-03-25 | 1.04 | 13 |  |  | 1.04 |  |  | 100% | 100%
| 2647 | 4 | 12.2.1.1 | 화면설계 | 화면설계서 | 스마트관리 담당자 | -1 | 2015-03-09 | 2015-03-25 | 0.728 | 13 |  |  | 0.728 |  |  | 100% | 0%
| 2648 | 5 | 12.2.1.1.1 | 메인화면 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.00625 | 13 |  |  | 0.00625 |  |  | 100%
| 2649 | 5 | 12.2.1.1.2 | 계산기 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.00625 | 13 |  |  | 0.00625 |  |  | 100%
| 2650 | 5 | 12.2.1.1.3 | 사이버환전(안내,바로가기) |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.00625 | 13 |  |  | 0.00625 |  |  | 100%
| 2651 | 5 | 12.2.1.1.4 | 고객센터 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.00625 | 13 |  |  | 0.00625 |  |  | 100%
| 2652 | 5 | 12.2.1.1.5 | 환율 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.00625 | 13 |  |  | 0.00625 |  |  | 100%
| 2653 | 5 | 12.2.1.1.6 | 환율 위젯 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.00625 | 13 |  |  | 0.00625 |  |  | 100%
| 2654 | 4 | 12.2.1.2 | 프로그램 설계 | 프로그램 목록 프로그램 사양서 | 스마트뱅킹 개발자 | -1 | 2015-03-16 | 2015-03-25 | 0.312 | 8 |  |  | 0.312 |  |  | 100% | 0%
| 2655 | 5 | 12.2.1.2.1 | Native 앱 공통 구조 개발 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2656 | 5 | 12.2.1.2.2 | PT 통신 인터페이스 개발 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2657 | 5 | 12.2.1.2.3 | 다국어 처리 방식 대응 개발 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2658 | 5 | 12.2.1.2.4 | 메인화면 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2659 | 5 | 12.2.1.2.5 | 계산기 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2660 | 5 | 12.2.1.2.6 | 사이버환전(안내,바로가기) |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2661 | 5 | 12.2.1.2.7 | 고객센터 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2662 | 5 | 12.2.1.2.8 | 환율 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2663 | 5 | 12.2.1.2.9 | 환율 위젯 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0041667 | 8 |  |  | 0.0041667 |  |  | 100%
| 2664 | 3 | 12.2.2 | 통합전문설계 |  |  | -1 | 2015-03-26 | 2015-03-31 | 0.26 | 4 |  |  | 0.26 |  |  | 100% | 100%
| 2665 | 4 | 12.2.2.1 | 전문매핑 | 전문목록 | 스마트뱅킹 개발자 | -1 | 2015-03-26 | 2015-03-31 | 0.26 | 4 |  |  | 0.26 |  |  | 100% | 0%
| 2666 | 2 | 12.3 | 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 1.4 | 65 |  |  | 1.4 |  |  | 55.38% | 100%
| 2667 | 3 | 12.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.98 | 65 |  |  | 0.98 |  |  | 55.38% | 100%
| 2668 | 4 | 12.3.1.1 | 온라인 프로그램 구현 | 온라인 프로그램 소스코드 | 스마트뱅킹 개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.8 | 65 |  |  | 0.8 |  |  | 55.38% | 0%
| 2669 | 5 | 12.3.1.1.1 | Native 앱 공통 구조 개발 |  |  | -1 | 2015-03-16 | 2015-03-27 | 0.088889 | 10 |  |  | 0.088889 |  |  | 100%
| 2670 | 5 | 12.3.1.1.2 | PT 통신 인터페이스 개발 |  |  | -1 | 2015-03-30 | 2015-04-03 | 0.088889 | 5 |  |  | 0.088889 |  |  | 100%
| 2671 | 5 | 12.3.1.1.3 | 다국어 처리 방식 대응 개발 |  |  | -1 | 2015-04-06 | 2015-04-17 | 0.088889 | 10 |  |  | 0.088889 |  |  | 100%
| 2672 | 5 | 12.3.1.1.4 | 메인화면 |  |  | 0 | 2015-04-20 | 2015-04-24 | 0.088889 | 5 |  |  | 0.088889 |  |  | 20%
| 2673 | 5 | 12.3.1.1.5 | 계산기 |  |  | 0 | 2015-04-27 | 2015-05-06 | 0.088889 | 8 |  |  | 0.088889 |  |  | 0%
| 2674 | 5 | 12.3.1.1.6 | 사이버환전(안내,바로가기) |  |  | 0 | 2015-05-07 | 2015-05-08 | 0.088889 | 2 |  |  | 0.088889 |  |  | 0%
| 2675 | 5 | 12.3.1.1.7 | 고객센터 |  |  | 0 | 2015-05-11 | 2015-05-15 | 0.088889 | 5 |  |  | 0.088889 |  |  | 0%
| 2676 | 5 | 12.3.1.1.8 | 환율 |  |  | 0 | 2015-05-18 | 2015-05-27 | 0.088889 | 8 |  |  | 0.088889 |  |  | 0%
| 2677 | 5 | 12.3.1.1.9 | 환율 위젯 |  |  | 0 | 2015-05-28 | 2015-06-12 | 0.088889 | 12 |  |  | 0.088889 |  |  | 0%
| 2678 | 3 | 12.3.2 | 단위테스트 수행 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.42 | 65 |  |  | 0.42 |  |  | 55.38% | 100%
| 2679 | 4 | 12.3.2.1 | 단위테스트 수행 | 단위테스트 결과서 | 스마트뱅킹 개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.011538 | 65 |  |  | 0.011538 |  |  | 55.38% | 0%
| 2680 | 5 | 12.3.2.1.1 | 메인화면 |  |  | 0 | 2015-04-20 | 2015-04-24 | 0.001923 | 5 |  |  | 0.001923 |  |  | 20%
| 2681 | 5 | 12.3.2.1.2 | 계산기 |  |  | 0 | 2015-04-27 | 2015-05-06 | 0.001923 | 8 |  |  | 0.001923 |  |  | 0%
| 2682 | 5 | 12.3.2.1.3 | 사이버환전(안내,바로가기) |  |  | 0 | 2015-05-07 | 2015-05-08 | 0.001923 | 2 |  |  | 0.001923 |  |  | 0%
| 2683 | 5 | 12.3.2.1.4 | 고객센터 |  |  | 0 | 2015-05-11 | 2015-05-15 | 0.001923 | 5 |  |  | 0.001923 |  |  | 0%
| 2684 | 5 | 12.3.2.1.5 | 환율 |  |  | 0 | 2015-05-18 | 2015-05-27 | 0.001923 | 8 |  |  | 0.001923 |  |  | 0%
| 2685 | 5 | 12.3.2.1.6 | 환율 위젯 |  |  | 0 | 2015-05-28 | 2015-06-12 | 0.001923 | 12 |  |  | 0.001923 |  |  | 0%
| 2686 | 1 | 13 | 스마트 웹뱅킹 |  |  | 0 | 2015-02-09 | 2015-06-12 | 4 | 90 |  |  | 4 |  |  | 78.89% | 100%
| 2687 | 2 | 13.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-03-13 | 1.3 | 25 |  |  | 1.3 |  |  | 100% | 100%
| 2688 | 3 | 13.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.02 | 15 |  |  | 0.02 |  |  | 100% | 100%
| 2689 | 4 | 13.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 | 스마트관리 담당자 | -1 | 2015-02-09 | 2015-02-27 | 0.09 | 15 |  |  | 0.09 |  |  | 100% | 0%
| 2690 | 5 | 13.1.1.1.1 | 로그인 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.01125 | 15 |  |  | 0.01125 |  |  | 100%
| 2691 | 5 | 13.1.1.1.2 | 인증서 연동(앱프리) 및 보안 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.01125 | 15 |  |  | 0.01125 |  |  | 100%
| 2692 | 5 | 13.1.1.1.3 | 간편조회 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.01125 | 15 |  |  | 0.01125 |  |  | 100%
| 2693 | 5 | 13.1.1.1.4 | 스마트금융/고객센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.01125 | 15 |  |  | 0.01125 |  |  | 100%
| 2694 | 5 | 13.1.1.1.5 | 이벤트/새소식 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.01125 | 15 |  |  | 0.01125 |  |  | 100%
| 2695 | 5 | 13.1.1.1.6 | 금융상품몰 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.01125 | 15 |  |  | 0.01125 |  |  | 100%
| 2696 | 5 | 13.1.1.1.7 | 환율 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.01125 | 15 |  |  | 0.01125 |  |  | 100%
| 2697 | 5 | 13.1.1.1.8 | 환전 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.01125 | 15 |  |  | 0.01125 |  |  | 100%
| 2698 | 3 | 13.1.2 | GAP 분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.26 | 15 |  |  | 0.26 |  |  | 100% | 100%
| 2699 | 4 | 13.1.2.1 | 메뉴 GAP분석 | 현행 시스템 분석서 | 스마트관리 담당자 | -1 | 2015-02-09 | 2015-02-27 | 0.156 | 15 |  |  | 0.156 |  |  | 100% | 0%
| 2700 | 5 | 13.1.2.1.1 | 로그인 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2701 | 5 | 13.1.2.1.2 | 인증서 연동(앱프리) 및 보안 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2702 | 5 | 13.1.2.1.3 | 간편조회 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2703 | 5 | 13.1.2.1.4 | 스마트금융/고객센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2704 | 5 | 13.1.2.1.5 | 이벤트/새소식 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2705 | 5 | 13.1.2.1.6 | 금융상품몰 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2706 | 5 | 13.1.2.1.7 | 환율 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2707 | 5 | 13.1.2.1.8 | 환전 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2708 | 4 | 13.1.2.2 | 전문 GAP분석 | 현행 시스템 분석서 | 스마트뱅킹 개발자 | -1 | 2015-02-09 | 2015-02-27 | 0.104 | 15 |  |  | 0.104 |  |  | 100% | 0%
| 2709 | 5 | 13.1.2.2.1 | 로그인 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2710 | 5 | 13.1.2.2.2 | 인증서 연동(앱프리) 및 보안 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2711 | 5 | 13.1.2.2.3 | 간편조회 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2712 | 5 | 13.1.2.2.4 | 스마트금융/고객센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2713 | 5 | 13.1.2.2.5 | 이벤트/새소식 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2714 | 5 | 13.1.2.2.6 | 금융상품몰 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2715 | 5 | 13.1.2.2.7 | 환율 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2716 | 5 | 13.1.2.2.8 | 환전 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.005625 | 15 |  |  | 0.005625 |  |  | 100%
| 2717 | 3 | 13.1.3 | 통합업무확정 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.26 | 5 |  |  | 0.26 |  |  | 100% | 100%
| 2718 | 4 | 13.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 | 스마트관리 담당자 | -1 | 2015-02-23 | 2015-02-27 | 0.9 | 5 |  |  | 0.9 |  |  | 100% | 0%
| 2719 | 5 | 13.1.3.1.1 | 로그인 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.1125 | 5 |  |  | 0.1125 |  |  | 100%
| 2720 | 5 | 13.1.3.1.2 | 인증서 연동(앱프리) 및 보안 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.1125 | 5 |  |  | 0.1125 |  |  | 100%
| 2721 | 5 | 13.1.3.1.3 | 간편조회 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.1125 | 5 |  |  | 0.1125 |  |  | 100%
| 2722 | 5 | 13.1.3.1.4 | 스마트금융/고객센터 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.1125 | 5 |  |  | 0.1125 |  |  | 100%
| 2723 | 5 | 13.1.3.1.5 | 이벤트/새소식 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.1125 | 5 |  |  | 0.1125 |  |  | 100%
| 2724 | 5 | 13.1.3.1.6 | 금융상품몰 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.1125 | 5 |  |  | 0.1125 |  |  | 100%
| 2725 | 5 | 13.1.3.1.7 | 환율 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.1125 | 5 |  |  | 0.1125 |  |  | 100%
| 2726 | 5 | 13.1.3.1.8 | 환전 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.1125 | 5 |  |  | 0.1125 |  |  | 100%
| 2727 | 3 | 13.1.4 | 통합요건정의 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.46 | 10 |  |  | 0.46 |  |  | 100% | 100%
| 2728 | 4 | 13.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 스마트뱅킹 개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0375 | 10 |  |  | 0.0375 |  |  | 100% | 0%
| 2729 | 5 | 13.1.4.1.1 | 로그인 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0046875 | 10 |  |  | 0.0046875 |  |  | 100%
| 2730 | 5 | 13.1.4.1.2 | 인증서 연동(앱프리) 및 보안 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0046875 | 10 |  |  | 0.0046875 |  |  | 100%
| 2731 | 5 | 13.1.4.1.3 | 간편조회 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0046875 | 10 |  |  | 0.0046875 |  |  | 100%
| 2732 | 5 | 13.1.4.1.4 | 스마트금융/고객센터 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0046875 | 10 |  |  | 0.0046875 |  |  | 100%
| 2733 | 5 | 13.1.4.1.5 | 이벤트/새소식 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0046875 | 10 |  |  | 0.0046875 |  |  | 100%
| 2734 | 5 | 13.1.4.1.6 | 금융상품몰 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0046875 | 10 |  |  | 0.0046875 |  |  | 100%
| 2735 | 5 | 13.1.4.1.7 | 환율 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0046875 | 10 |  |  | 0.0046875 |  |  | 100%
| 2736 | 5 | 13.1.4.1.8 | 환전 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.0046875 | 10 |  |  | 0.0046875 |  |  | 100%
| 2737 | 3 | 13.1.5 | 논리모델구축 |  |  | -1 | 2015-03-11 | 2015-03-13 | 0.13 | 3 |  |  | 0.13 |  |  | 100% | 100%
| 2738 | 4 | 13.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 | 스마트뱅킹 개발자 | -1 | 2015-03-11 | 2015-03-13 | 0.13 | 3 |  |  | 0.13 |  |  | 100% | 0%
| 2739 | 2 | 13.2 | 설계 |  |  | -1 | 2015-03-09 | 2015-03-31 | 1.3 | 17 |  |  | 1.3 |  |  | 100% | 100%
| 2740 | 3 | 13.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-09 | 2015-03-25 | 1.04 | 13 |  |  | 1.04 |  |  | 100% | 100%
| 2741 | 4 | 13.2.1.1 | 화면설계 | 화면설계서 | 스마트관리 담당자 | -1 | 2015-03-09 | 2015-03-25 | 0.728 | 13 |  |  | 0.728 |  |  | 100% | 0%
| 2742 | 5 | 13.2.1.1.1 | 로그인 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0046875 | 13 |  |  | 0.0046875 |  |  | 100%
| 2743 | 5 | 13.2.1.1.2 | 인증서 연동(앱프리) 및 보안 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0046875 | 13 |  |  | 0.0046875 |  |  | 100%
| 2744 | 5 | 13.2.1.1.3 | 간편조회 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0046875 | 13 |  |  | 0.0046875 |  |  | 100%
| 2745 | 5 | 13.2.1.1.4 | 스마트금융/고객센터 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0046875 | 13 |  |  | 0.0046875 |  |  | 100%
| 2746 | 5 | 13.2.1.1.5 | 이벤트/새소식 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0046875 | 13 |  |  | 0.0046875 |  |  | 100%
| 2747 | 5 | 13.2.1.1.6 | 금융상품몰 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0046875 | 13 |  |  | 0.0046875 |  |  | 100%
| 2748 | 5 | 13.2.1.1.7 | 환율 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0046875 | 13 |  |  | 0.0046875 |  |  | 100%
| 2749 | 5 | 13.2.1.1.8 | 환전 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0046875 | 13 |  |  | 0.0046875 |  |  | 100%
| 2750 | 4 | 13.2.1.2 | 프로그램 설계 | 프로그램 목록 프로그램 사양서 | 스마트뱅킹 개발자 | -1 | 2015-03-16 | 2015-03-25 | 0.312 | 8 |  |  | 0.312 |  |  | 100% | 0%
| 2751 | 5 | 13.2.1.2.1 | 로그인 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2752 | 5 | 13.2.1.2.2 | 인증서 연동(앱프리) 및 보안 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2753 | 5 | 13.2.1.2.3 | 간편조회 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2754 | 5 | 13.2.1.2.4 | 스마트금융/고객센터 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2755 | 5 | 13.2.1.2.5 | 이벤트/새소식 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2756 | 5 | 13.2.1.2.6 | 금융상품몰 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2757 | 5 | 13.2.1.2.7 | 환율 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2758 | 5 | 13.2.1.2.8 | 환전 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2759 | 3 | 13.2.2 | 통합전문설계 |  |  | -1 | 2015-03-26 | 2015-03-31 | 0.26 | 4 |  |  | 0.26 |  |  | 100% | 100%
| 2760 | 4 | 13.2.2.1 | 전문매핑 | 전문목록 | 스마트뱅킹 개발자 | -1 | 2015-03-26 | 2015-03-31 | 0.26 | 4 |  |  | 0.26 |  |  | 100% | 0%
| 2761 | 2 | 13.3 | 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 1.4 | 65 |  |  | 1.4 |  |  | 55.38% | 100%
| 2762 | 3 | 13.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.98 | 65 |  |  | 0.98 |  |  | 55.38% | 100%
| 2763 | 4 | 13.3.1.1 | 온라인 프로그램 구현 | 온라인 프로그램 소스코드 | 스마트뱅킹 개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.011538 | 65 |  |  | 0.011538 |  |  | 55.38% | 0%
| 2764 | 5 | 13.3.1.1.1 | 로그인 개발 |  |  | -1 | 2015-03-16 | 2015-03-24 | 0.0014422 | 7 |  |  | 0.0014422 |  |  | 100%
| 2765 | 5 | 13.3.1.1.2 | 인증서 연동(앱프리) 및 보안 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.0014422 | 5 |  |  | 0.0014422 |  |  | 100%
| 2766 | 5 | 13.3.1.1.3 | 간편조회 |  |  | -1 | 2015-03-25 | 2015-04-03 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2767 | 5 | 13.3.1.1.4 | 스마트금융/고객센터 |  |  | -1 | 2015-04-06 | 2015-04-10 | 0.0014422 | 5 |  |  | 0.0014422 |  |  | 100%
| 2768 | 5 | 13.3.1.1.5 | 이벤트/새소식 |  |  | -1 | 2015-04-13 | 2015-04-17 | 0.0014422 | 5 |  |  | 0.0014422 |  |  | 100%
| 2769 | 5 | 13.3.1.1.6 | 금융상품몰 |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.0014422 | 10 |  |  | 0.0014422 |  |  | 10%
| 2770 | 5 | 13.3.1.1.7 | 환율 |  |  | 0 | 2015-05-18 | 2015-05-27 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 0%
| 2771 | 5 | 13.3.1.1.8 | 환전 |  |  | 0 | 2015-05-28 | 2015-06-12 | 0.0014422 | 12 |  |  | 0.0014422 |  |  | 0%
| 2772 | 3 | 13.3.2 | 단위테스트 수행 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.42 | 65 |  |  | 0.42 |  |  | 55.38% | 100%
| 2773 | 4 | 13.3.2.1 | 단위테스트 수행 | 단위테스트 결과서 | 스마트뱅킹 개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.011538 | 65 |  |  | 0.011538 |  |  | 55.38% | 0%
| 2774 | 5 | 13.3.2.1.1 | 로그인 개발 |  |  | -1 | 2015-03-16 | 2015-03-24 | 0.0014422 | 7 |  |  | 0.0014422 |  |  | 100%
| 2775 | 5 | 13.3.2.1.2 | 인증서 연동(앱프리) 및 보안 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.0014422 | 5 |  |  | 0.0014422 |  |  | 100%
| 2776 | 5 | 13.3.2.1.3 | 간편조회 |  |  | -1 | 2015-03-25 | 2015-04-03 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 100%
| 2777 | 5 | 13.3.2.1.4 | 스마트금융/고객센터 |  |  | -1 | 2015-04-06 | 2015-04-10 | 0.0014422 | 5 |  |  | 0.0014422 |  |  | 100%
| 2778 | 5 | 13.3.2.1.5 | 이벤트/새소식 |  |  | -1 | 2015-04-13 | 2015-04-17 | 0.0014422 | 5 |  |  | 0.0014422 |  |  | 100%
| 2779 | 5 | 13.3.2.1.6 | 금융상품몰 |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.0014422 | 10 |  |  | 0.0014422 |  |  | 10%
| 2780 | 5 | 13.3.2.1.7 | 환율 |  |  | 0 | 2015-05-18 | 2015-05-27 | 0.0014422 | 8 |  |  | 0.0014422 |  |  | 0%
| 2781 | 5 | 13.3.2.1.8 | 환전 |  |  | 0 | 2015-05-28 | 2015-06-12 | 0.0014422 | 12 |  |  | 0.0014422 |  |  | 0%
| 2782 | 1 | 14 | 기업 스마트 뱅킹 |  |  | 0 | 2015-02-09 | 2015-06-12 | 4 | 90 |  |  | 4 |  |  | 78.89% | 100%
| 2783 | 2 | 14.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-03-13 | 1.3 | 25 |  |  | 1.3 |  |  | 100% | 100%
| 2784 | 3 | 14.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.2 | 15 |  |  | 0.2 |  |  | 100% | 100%
| 2785 | 4 | 14.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 | 스마트관리 담당자 | -1 | 2015-02-09 | 2015-02-27 | 0.09 | 15 |  |  | 0.09 |  |  | 100% | 0%
| 2786 | 5 | 14.1.1.1.1 | 로그인 및 인증센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2787 | 5 | 14.1.1.1.2 | 예금조회(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2788 | 5 | 14.1.1.1.3 | 전자결재/전자어음 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2789 | 5 | 14.1.1.1.4 | 자금이체(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2790 | 5 | 14.1.1.1.5 | 대출/카드/부가서비스 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2791 | 5 | 14.1.1.1.6 | 결재함(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2792 | 5 | 14.1.1.1.7 | 서비스관리(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2793 | 5 | 14.1.1.1.8 | 고객센터(KEBiNet 전용) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2794 | 5 | 14.1.1.1.9 | 환경설정(KEBiNet 전용) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2795 | 5 | 14.1.1.1.10 | 환율 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2796 | 3 | 14.1.2 | GAP 분석 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.26 | 15 |  |  | 0.26 |  |  | 100% | 100%
| 2797 | 4 | 14.1.2.1 | 메뉴 GAP분석 | 현행 시스템 분석서 | 스마트관리 담당자 | -1 | 2015-02-09 | 2015-02-27 | 0.156 | 15 |  |  | 0.156 |  |  | 100% | 0%
| 2798 | 5 | 14.1.2.1.1 | 로그인 및 인증센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2799 | 5 | 14.1.2.1.2 | 예금조회(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2800 | 5 | 14.1.2.1.3 | 전자결재/전자어음 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2801 | 5 | 14.1.2.1.4 | 자금이체(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2802 | 5 | 14.1.2.1.5 | 대출/카드/부가서비스 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2803 | 5 | 14.1.2.1.6 | 결재함(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2804 | 5 | 14.1.2.1.7 | 서비스관리(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2805 | 5 | 14.1.2.1.8 | 고객센터(KEBiNet 전용) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2806 | 5 | 14.1.2.1.9 | 환경설정(KEBiNet 전용) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2807 | 5 | 14.1.2.1.10 | 환율 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.004 | 15 |  |  | 0.004 |  |  | 100%
| 2808 | 4 | 14.1.2.2 | 전문 GAP분석 | 현행 시스템 분석서 | 스마트뱅킹 개발자 | -1 | 2015-02-09 | 2015-02-27 | 0.104 | 15 |  |  | 0.104 |  |  | 100% | 0%
| 2809 | 5 | 14.1.2.2.1 | 로그인 및 인증센터 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2810 | 5 | 14.1.2.2.2 | 예금조회(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2811 | 5 | 14.1.2.2.3 | 전자결재/전자어음 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2812 | 5 | 14.1.2.2.4 | 자금이체(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2813 | 5 | 14.1.2.2.5 | 대출/카드/부가서비스 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2814 | 5 | 14.1.2.2.6 | 결재함(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2815 | 5 | 14.1.2.2.7 | 서비스관리(KEBiNet 포함) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2816 | 5 | 14.1.2.2.8 | 고객센터(KEBiNet 전용) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2817 | 5 | 14.1.2.2.9 | 환경설정(KEBiNet 전용) |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2818 | 5 | 14.1.2.2.10 | 환율 |  |  | -1 | 2015-02-09 | 2015-02-27 | 0.009 | 15 |  |  | 0.009 |  |  | 100%
| 2819 | 3 | 14.1.3 | 통합업무확정 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.26 | 5 |  |  | 0.26 |  |  | 100% | 100%
| 2820 | 4 | 14.1.3.1 | 통합메뉴구조 확정 | 통합메뉴구조도 | 스마트관리 담당자 | -1 | 2015-02-23 | 2015-02-27 | 0.0375 | 5 |  |  | 0.0375 |  |  | 100% | 0%
| 2821 | 5 | 14.1.3.1.1 | 로그인 및 인증센터 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2822 | 5 | 14.1.3.1.2 | 예금조회(KEBiNet 포함) |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2823 | 5 | 14.1.3.1.3 | 전자결재/전자어음 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2824 | 5 | 14.1.3.1.4 | 자금이체(KEBiNet 포함) |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2825 | 5 | 14.1.3.1.5 | 대출/카드/부가서비스 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2826 | 5 | 14.1.3.1.6 | 결재함(KEBiNet 포함) |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2827 | 5 | 14.1.3.1.7 | 서비스관리(KEBiNet 포함) |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2828 | 5 | 14.1.3.1.8 | 고객센터(KEBiNet 전용) |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2829 | 5 | 14.1.3.1.9 | 환경설정(KEBiNet 전용) |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2830 | 5 | 14.1.3.1.10 | 환율 |  |  | -1 | 2015-02-23 | 2015-02-27 | 0.00375 | 5 |  |  | 0.00375 |  |  | 100%
| 2831 | 3 | 14.1.4 | 통합요건정의 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.46 | 10 |  |  | 0.46 |  |  | 100% | 100%
| 2832 | 4 | 14.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 스마트뱅킹 개발자 | -1 | 2015-03-02 | 2015-03-13 | 0.0375 | 10 |  |  | 0.0375 |  |  | 100% | 0%
| 2833 | 5 | 14.1.4.1.1 | 로그인 및 인증센터 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2834 | 5 | 14.1.4.1.2 | 예금조회(KEBiNet 포함) |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2835 | 5 | 14.1.4.1.3 | 전자결재/전자어음 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2836 | 5 | 14.1.4.1.4 | 자금이체(KEBiNet 포함) |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2837 | 5 | 14.1.4.1.5 | 대출/카드/부가서비스 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2838 | 5 | 14.1.4.1.6 | 결재함(KEBiNet 포함) |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2839 | 5 | 14.1.4.1.7 | 서비스관리(KEBiNet 포함) |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2840 | 5 | 14.1.4.1.8 | 고객센터(KEBiNet 전용) |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2841 | 5 | 14.1.4.1.9 | 환경설정(KEBiNet 전용) |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2842 | 5 | 14.1.4.1.10 | 환율 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.00375 | 10 |  |  | 0.00375 |  |  | 100%
| 2843 | 3 | 14.1.5 | 논리모델구축 |  |  | -1 | 2015-03-11 | 2015-03-13 | 0.13 | 3 |  |  | 0.13 |  |  | 100% | 100%
| 2844 | 4 | 14.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 | 스마트뱅킹 개발자 | -1 | 2015-03-11 | 2015-03-13 | 0.13 | 3 |  |  | 0.13 |  |  | 100% | 0%
| 2845 | 2 | 14.2 | 설계 |  |  | -1 | 2015-03-09 | 2015-03-31 | 1.3 | 17 |  |  | 1.3 |  |  | 100% | 100%
| 2846 | 3 | 14.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-09 | 2015-03-25 | 1.04 | 13 |  |  | 1.04 |  |  | 100% | 100%
| 2847 | 4 | 14.2.1.1 | 화면설계 | 화면설계서 | 스마트관리 담당자 | -1 | 2015-03-09 | 2015-03-25 | 0.728 | 13 |  |  | 0.728 |  |  | 100% | 0%
| 2848 | 5 | 14.2.1.1.1 | 로그인 및 인증센터 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2849 | 5 | 14.2.1.1.2 | 예금조회(KEBiNet 포함) |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2850 | 5 | 14.2.1.1.3 | 전자결재/전자어음 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2851 | 5 | 14.2.1.1.4 | 자금이체(KEBiNet 포함) |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2852 | 5 | 14.2.1.1.5 | 대출/카드/부가서비스 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2853 | 5 | 14.2.1.1.6 | 결재함(KEBiNet 포함) |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2854 | 5 | 14.2.1.1.7 | 서비스관리(KEBiNet 포함) |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2855 | 5 | 14.2.1.1.8 | 고객센터(KEBiNet 전용) |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2856 | 5 | 14.2.1.1.9 | 환경설정(KEBiNet 전용) |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2857 | 5 | 14.2.1.1.10 | 환율 |  |  | -1 | 2015-03-09 | 2015-03-25 | 0.0011538 | 13 |  |  | 0.0011538 |  |  | 100%
| 2858 | 4 | 14.2.1.2 | 프로그램 설계 | 프로그램 목록 프로그램 사양서 | 스마트뱅킹 개발자 | -1 | 2015-03-16 | 2015-03-25 | 0.312 | 8 |  |  | 0.312 |  |  | 100% | 0%
| 2859 | 5 | 14.2.1.2.1 | 로그인 및 인증센터 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2860 | 5 | 14.2.1.2.2 | 예금조회(KEBiNet 포함) |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2861 | 5 | 14.2.1.2.3 | 전자결재/전자어음 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2862 | 5 | 14.2.1.2.4 | 자금이체(KEBiNet 포함) |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2863 | 5 | 14.2.1.2.5 | 대출/카드/부가서비스 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2864 | 5 | 14.2.1.2.6 | 결재함(KEBiNet 포함) |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2865 | 5 | 14.2.1.2.7 | 서비스관리(KEBiNet 포함) |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2866 | 5 | 14.2.1.2.8 | 고객센터(KEBiNet 전용) |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2867 | 5 | 14.2.1.2.9 | 환경설정(KEBiNet 전용) |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2868 | 5 | 14.2.1.2.10 | 환율 |  |  | -1 | 2015-03-16 | 2015-03-25 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2869 | 3 | 14.2.2 | 통합전문설계 |  |  | -1 | 2015-03-26 | 2015-03-31 | 0.26 | 4 |  |  | 0.26 |  |  | 100% | 100%
| 2870 | 4 | 14.2.2.1 | 전문매핑 | 전문목록 | 스마트뱅킹 개발자 | -1 | 2015-03-26 | 2015-03-31 | 0.26 | 4 |  |  | 0.26 |  |  | 100% | 0%
| 2871 | 2 | 14.3 | 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 1.4 | 65 |  |  | 1.4 |  |  | 55.38% | 100%
| 2872 | 3 | 14.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.98 | 65 |  |  | 0.98 |  |  | 55.38% | 100%
| 2873 | 4 | 14.3.1.1 | 온라인 프로그램 구현 | 온라인 프로그램 소스코드 | 스마트뱅킹 개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.98 | 65 |  |  | 0.98 |  |  | 55.38% | 0%
| 2874 | 5 | 14.3.1.1.1 | 로그인/인증센터 개발 |  |  | -1 | 2015-03-16 | 2015-03-24 | 0.0011538 | 7 |  |  | 0.0011538 |  |  | 100%
| 2875 | 5 | 14.3.1.1.2 | 전자결재/전자어음 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.0011538 | 5 |  |  | 0.0011538 |  |  | 100%
| 2876 | 5 | 14.3.1.1.3 | 대출/카드/부가서비스 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.0011538 | 5 |  |  | 0.0011538 |  |  | 100%
| 2877 | 5 | 14.3.1.1.4 | 예금조회(KEBiNet 포함) |  |  | -1 | 2015-04-01 | 2015-04-07 | 0.0011538 | 5 |  |  | 0.0011538 |  |  | 100%
| 2878 | 5 | 14.3.1.1.5 | 자금이체(KEBiNet 포함) |  |  | -1 | 2015-04-08 | 2015-04-17 | 0.0011538 | 8 |  |  | 0.0011538 |  |  | 100%
| 2879 | 5 | 14.3.1.1.6 | 결재함(KEBiNet 포함) |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.0011538 | 10 |  |  | 0.0011538 |  |  | 10%
| 2880 | 5 | 14.3.1.1.7 | 서비스관리(KEBiNet 포함) |  |  | 0 | 2015-05-04 | 2015-05-14 | 0.0011538 | 9 |  |  | 0.0011538 |  |  | 0%
| 2881 | 5 | 14.3.1.1.8 | 고객센터(KEBiNet 전용) |  |  | 0 | 2015-05-15 | 2015-05-21 | 0.0011538 | 5 |  |  | 0.0011538 |  |  | 0%
| 2882 | 5 | 14.3.1.1.9 | 환경설정(KEBiNet 전용) |  |  | 0 | 2015-05-22 | 2015-05-29 | 0.0011538 | 6 |  |  | 0.0011538 |  |  | 0%
| 2883 | 5 | 14.3.1.1.10 | 환율 |  |  | 0 | 2015-06-01 | 2015-06-12 | 0.0011538 | 10 |  |  | 0.0011538 |  |  | 0%
| 2884 | 3 | 14.3.2 | 단위테스트 수행 |  |  | 0 | 2015-03-16 | 2015-06-12 | 0.42 | 65 |  |  | 0.42 |  |  | 55.38% | 100%
| 2885 | 4 | 14.3.2.1 | 단위테스트 수행 | 단위테스트 결과서 | 스마트뱅킹 개발자 | 0 | 2015-03-16 | 2015-06-12 | 0.42 | 65 |  |  | 0.42 |  |  | 55.38% | 0%
| 2886 | 5 | 14.3.2.1.1 | 로그인/인증센터 개발 |  |  | -1 | 2015-03-16 | 2015-03-24 | 0.005 | 7 |  |  | 0.005 |  |  | 100%
| 2887 | 5 | 14.3.2.1.2 | 전자결재/전자어음 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.005 | 5 |  |  | 0.005 |  |  | 100%
| 2888 | 5 | 14.3.2.1.3 | 대출/카드/부가서비스 |  |  | -1 | 2015-03-25 | 2015-03-31 | 0.005 | 5 |  |  | 0.005 |  |  | 100%
| 2889 | 5 | 14.3.2.1.4 | 예금조회(KEBiNet 포함) |  |  | -1 | 2015-04-01 | 2015-04-07 | 0.005 | 5 |  |  | 0.005 |  |  | 100%
| 2890 | 5 | 14.3.2.1.5 | 자금이체(KEBiNet 포함) |  |  | -1 | 2015-04-08 | 2015-04-17 | 0.005 | 8 |  |  | 0.005 |  |  | 100%
| 2891 | 5 | 14.3.2.1.6 | 결재함(KEBiNet 포함) |  |  | 0 | 2015-04-20 | 2015-05-01 | 0.005 | 10 |  |  | 0.005 |  |  | 10%
| 2892 | 5 | 14.3.2.1.7 | 서비스관리(KEBiNet 포함) |  |  | 0 | 2015-05-04 | 2015-05-14 | 0.005 | 9 |  |  | 0.005 |  |  | 0%
| 2893 | 5 | 14.3.2.1.8 | 고객센터(KEBiNet 전용) |  |  | 0 | 2015-05-15 | 2015-05-21 | 0.005 | 5 |  |  | 0.005 |  |  | 0%
| 2894 | 5 | 14.3.2.1.9 | 환경설정(KEBiNet 전용) |  |  | 0 | 2015-05-22 | 2015-05-29 | 0.005 | 6 |  |  | 0.005 |  |  | 0%
| 2895 | 5 | 14.3.2.1.10 | 환율 |  |  | 0 | 2015-06-01 | 2015-06-12 | 0.005 | 10 |  |  | 0.005 |  |  | 0%
| 2896 | 1 | 15 | 이행 |  |  | 0 | 2015-08-03 | 2015-11-30 |  | 86 |  |  |  | #REF! | #REF! | 0% | 100%
| 2897 | 2 | 15.1 | 이행계획 |  |  | 0 | 2015-08-03 | 2015-09-25 |  | 40 |  |  |  | -30026 | -42037 | 0% | 100%
| 2898 | 3 | 15.1.1 | 이행계획수립 | 이행계획서 |  | 0 | 2015-08-03 | 2015-09-25 |  | 40 |  |  |  | -30027 | -42038 | 0% | 0%
| 2899 | 4 | 15.1.1.1 | 이행계획수립서 작성 | 이행계획서 |  | 0 | 2015-08-03 | 2015-09-25 |  | 40 |  |  |  | -30028 | -42039 | 0% | 0%
| 2900 | 4 | 15.1.1.2 | 이행시나리오 작성 | 이행계획서 |  | 0 | 2015-08-03 | 2015-09-25 |  | 40 |  |  |  | -30029 | -42040 | 0% | 0%
| 2901 | 4 | 15.1.1.3 | 시스템구성도(web/was) 작성 | 이행계획서 |  | 0 | 2015-08-03 | 2015-09-25 |  | 40 |  |  |  | -30029 | -42040 | 0% | 0%
| 2902 | 4 | 15.1.1.4 | 종합상황실 운영방안 작성 | 이행계획서 |  | 0 | 2015-08-03 | 2015-09-25 |  | 40 |  |  |  | -30030 | -42041 | 0% | 0%
| 2903 | 3 | 15.1.2 | 이행프로그램 작성 |  |  | 0 | 2015-09-07 | 2015-09-25 | 2 | 15 |  |  | 2 | -30028 | -42039 | 0% | 100%
| 2904 | 4 | 15.1.2.1 | 이행프로그램 목록정리 | 이행프로그램 목록 |  | 0 | 2015-09-07 | 2015-09-25 |  | 15 |  |  |  | #REF! | #REF! | 0% | 0%
| 2905 | 4 | 15.1.2.2 | Web Server 이행목록 정리 | 이행프로그램 목록 |  | 0 | 2015-09-07 | 2015-09-25 |  | 15 |  |  |  | #REF! | #REF! | 0% | 0%
| 2906 | 4 | 15.1.2.3 | WAS Server 이행목록 정리 | 이행프로그램 목록 |  | 0 | 2015-09-07 | 2015-09-25 |  | 15 |  |  |  | #REF! | #REF! | 0% | 0%
| 2907 | 4 | 15.1.2.4 | 프레임워크 이행목록 정리 | 이행프로그램 목록 |  | 0 | 2015-09-07 | 2015-09-25 |  | 15 |  |  |  | #REF! | #REF! | 0% | 0%
| 2908 | 4 | 15.1.2.5 | 설정파일 이행목록 정리 | 이행프로그램 목록 |  | 0 | 2015-09-07 | 2015-09-25 |  | 15 |  |  |  | #REF! | #REF! | 0% | 0%
| 2909 | 4 | 15.1.2.6 | 3rd Party 솔루션 설치목록 정리 | 이행프로그램 목록 |  | 0 | 2015-09-07 | 2015-09-25 |  | 15 |  |  |  | #REF! | #REF! | 0% | 0%
| 2910 | 4 | 15.1.2.7 | 방화벽 요청 목록 정리 | 이행프로그램 목록 |  | 0 | 2015-09-07 | 2015-09-25 |  | 15 |  |  |  | #REF! | #REF! | 0% | 0%
| 2911 | 4 | 15.1.2.8 | DB 이행목록 정리 | 이행프로그램 목록 |  | 0 | 2015-09-07 | 2015-09-25 |  | 15 |  |  |  | #REF! | #REF! | 0% | 0%
| 2912 | 4 | 15.1.2.9 | 체크리스트 작성 | 이행프로그램 목록 |  | 0 | 2015-08-03 | 2015-09-25 |  | 40 |  |  |  | -30030 | -42041 | 0% | 0%
| 2913 | 3 | 15.1.3 | 이행리허설 |  |  | 0 | 2015-09-14 | 2015-09-25 |  | 10 |  |  |  | -30026 | -42037 | 0% | 100%
| 2914 | 4 | 15.1.3.1 | 이행계획수립 | 이행계획서 |  | 0 | 2015-09-14 | 2015-09-25 |  | 10 |  |  |  | -30027 | -42038 | 0% | 0%
| 2915 | 3 | 15.1.4 | 컨버전 및 릴리즈 |  |  | 0 | 2015-09-21 | 2015-10-02 |  | 10 |  |  |  | -30028 | -42039 | 0% | 100%
| 2916 | 4 | 15.1.4.1 | 인수테스트결과 | 인수테스트 결과서 |  | 0 | 2015-09-21 | 2015-10-02 |  | 10 |  |  |  | #REF! | #REF! | 0% | 0%
| 2917 | 3 | 15.1.5 | 시스템이행 |  |  | 0 | 2015-09-21 | 2015-10-16 |  | 20 |  |  |  | #REF! | #REF! | 0% | 100%
| 2918 | 4 | 15.1.5.1 | 사전이행 | 최종 이행목록 |  | 0 | 2015-09-21 | 2015-09-08 |  | -10 |  |  |  | #REF! | #REF! | 0% | 0%
| 2919 | 4 | 15.1.5.2 | 시스템(web/was) 구성 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2920 | 4 | 15.1.5.3 | 방화벽 작업 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2921 | 4 | 15.1.5.4 | 3rd Pary 솔루션 설치 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2922 | 4 | 15.1.5.5 | DB 사전이행 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2923 | 4 | 15.1.5.6 | 본이행 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2924 | 4 | 15.1.5.7 | 시스템(web/was) 구성 점검 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2925 | 4 | 15.1.5.8 | DB이행 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2926 | 4 | 15.1.5.9 | 방화벽 점검 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2927 | 4 | 15.1.5.10 | 3rd Pary 솔루션 점검 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2928 | 4 | 15.1.5.11 | 프로그램 이행 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2929 | 4 | 15.1.5.12 | 설정파일 점검 및 변경 | 최종 이행목록 |  | 0 | 2015-09-08 | 2015-09-12 |  | 4 |  |  |  | #REF! | #REF! | 0% | 0%
| 2930 | 3 | 15.1.6 | 시스템 사용자교육 |  |  | 0 | 2015-10-26 | 2015-11-20 |  | 20 |  |  |  | #REF! | #REF! | 0% | 100%
| 2931 | 4 | 15.1.6.1 | 사용자 매뉴얼 작성 | 사용자 매뉴얼 |  | 0 | 2015-10-26 | 2015-11-20 |  | 20 |  |  |  | #REF! | #REF! | 0% | 0%
| 2932 | 4 | 15.1.6.2 | 운영자 매뉴얼 작성 | 운영자 매뉴얼 |  | 0 | 2015-11-02 | 2015-11-20 |  | 15 |  |  |  | #REF! | #REF! | 0% | 0%
| 2933 | 1 | 16 | 공통 |  |  | 0 | 2015-02-09 | 2015-06-12 | 5 | 90 |  |  | 5 | 0 | 0 | 78.89%
| 2934 | 2 | 16.1 | 분석 |  |  | -1 | 2015-02-09 | 2015-03-06 | 1.6 | 20 |  |  | 1.6 | 0 | 0 | 100%
| 2935 | 3 | 16.1.1 | 현황분석 |  |  | -1 | 2015-02-09 | 2015-03-06 | 0.5 | 20 |  |  | 0.5 | 0 | 0 | 100%
| 2936 | 4 | 16.1.1.1 | 양행시스템분석 | 현행 시스템 분석서 | 채널공통팀 | -1 | 2015-02-09 | 2015-03-06 | 0.5 | 20 |  |  | 0.5 | 0 | 0 | 100%
| 2937 | 3 | 16.1.2 | GAP 분석 |  |  | -1 | 2015-02-09 | 2015-03-06 | 0.4 | 20 |  |  | 0.4 | 0 | 0 | 100%
| 2938 | 4 | 16.1.2.1 | 전문 GAP분석 | 현행 시스템 분석서 | 채널공통팀 | -1 | 2015-02-09 | 2015-03-06 | 0.2 | 20 |  |  | 0.2 | 0 | 0 | 100%
| 2939 | 4 | 16.1.2.2 | 테이블/속성 GAP분석 | 현행 시스템 분석서 | 채널공통팀 | -1 | 2015-02-09 | 2015-03-06 | 0.2 | 20 |  |  | 0.2 | 0 | 0 | 100%
| 2940 | 3 | 16.1.4 | 통합요건정의 |  |  | -1 | 2015-02-09 | 2015-03-06 | 0.3 | 20 |  |  | 0.3 | 0 | 0 | 100%
| 2941 | 4 | 16.1.4.1 | 업무별 요건 분류 | 요구사항정의서 요구사항추적표 | 채널공통팀 | -1 | 2015-02-09 | 2015-03-06 | 0.3 | 20 |  |  | 0.3 | 0 | 0 | 100%
| 2942 | 3 | 16.1.5 | 논리모델구축 |  |  | -1 | 2015-02-23 | 2015-03-06 | 0.3 | 10 |  |  | 0.3 | 0 | 0 | 100%
| 2943 | 4 | 16.1.5.1 | 프로세스 모델링 | 인터페이스 정의서 | 채널공통팀 | -1 | 2015-02-23 | 2015-03-06 | 0.3 | 10 |  |  | 0.3 | 0 | 0 | 100%
| 2944 | 3 | 16.1.6 | 1차 AS-IS 소스 취약점 점검 |  |  | -1 | 2015-02-09 | 2015-03-06 | 0.05 | 20 |  |  | 0.05 | 0 | 0 | 100%
| 2945 | 4 | 16.1.6.1 | 취약점 분석 |  | 채널공통팀 | -1 | 2015-02-09 | 2015-02-27 | 0.025 | 15 |  |  | 0.025 | 0 | 0 | 100%
| 2946 | 4 | 16.1.6.2 | 취약점 조치 및 가이드 문서 반영 | 개발가이드 문서 | 채널공통팀 | -1 | 2015-02-23 | 2015-03-06 | 0.025 | 10 |  |  | 0.025 | 0 | 0 | 100%
| 2947 | 3 | 16.1.7 | 파일럿 |  |  | -1 | 2015-02-16 | 2015-03-06 | 0.05 | 15 |  |  | 0.05 | 0 | 0 | 100%
| 2948 | 4 | 16.1.7.1 | 파일럿 개발 |  | 채널공통팀 | -1 | 2015-02-16 | 2015-03-06 | 0.025 | 15 |  |  | 0.025 | 0 | 0 | 100%
| 2949 | 4 | 16.1.7.2 | 파일럿 개발 및 가이드 문서 작성 | 개발가이드 문서 | 채널공통팀 | -1 | 2015-02-23 | 2015-03-06 | 0.025 | 10 |  |  | 0.025 | 0 | 0 | 100%
| 2950 | 2 | 16.2 | 설계 |  |  | -1 | 2015-03-02 | 2015-03-06 | 1.7 | 5 |  |  | 1.7 | 0 | 0 | 100%
| 2951 | 3 | 16.2.1 | 통합온라인 프로세스 설계 |  |  | -1 | 2015-03-02 | 2015-03-06 | 0.4 | 5 |  |  | 0.4 | 0 | 0 | 100%
| 2952 | 4 | 16.2.1.1 | 화면설계 | 화면설계서 | 채널공통팀 | -1 | 2015-03-02 | 2015-03-20 | 0.1 | 15 |  |  | 0.1 | 0 | 0 | 100%
| 2953 | 4 | 16.2.1.2 | 프로그램 설계 | 프로그램 목록 프로그램 사양서 | 채널공통팀 | -1 | 2015-03-02 | 2015-03-20 | 0.3 | 15 |  |  | 0.3 | 0 | 0 | 100%
| 2954 | 3 | 16.2.2 | 통합전문설계 |  |  | -1 | 2015-03-02 | 2015-03-20 | 0.5 | 15 |  |  | 0.5 | 0 | 0 | 100%
| 2955 | 4 | 16.2.2.1 | 전문매핑 | 전문목록 전문매핑정의서 | 채널공통팀 | -1 | 2015-03-02 | 2015-03-20 | 0.5 | 15 |  |  | 0.5 | 0 | 0 | 100%
| 2956 | 3 | 16.2.3 | 배치프로세스 설계 |  |  | -1 | 2015-03-02 | 2015-03-20 | 0.4 | 15 |  |  | 0.4 | 0 | 0 | 100%
| 2957 | 4 | 16.2.3.1 | 배치프로그램 설계 | 배치프로세스 정의서 | 채널공통팀 | -1 | 2015-03-02 | 2015-03-20 | 0.4 | 15 |  |  | 0.4 | 0 | 0 | 100%
| 2958 | 3 | 16.2.4 | 통합 DB 설계 |  |  | -1 | 2015-03-16 | 2015-03-27 | 0.3 | 10 |  |  | 0.3 | 0 | 0 | 100%
| 2959 | 4 | 16.2.4.1 | 양행 테이블/속성 매핑 | 논리 ERD 물리 ERD 테이블목록 테이블매핑정의서 | 채널공통팀 | -1 | 2015-03-16 | 2015-03-27 | 0.15 | 10 |  |  | 0.15 | 0 | 0 | 100%
| 2960 | 4 | 16.2.4.2 | 통합 데이터베이스 모델링 |  |  | -1 | 2015-03-16 | 2015-03-27 | 0.15 | 10 |  |  | 0.15 | 0 | 0 | 100%
| 2961 | 3 | 16.2.6 | 에러메세지 처리방안 리뷰 |  |  | -1 | 2015-03-30 | 2015-04-03 | 0.05 | 5 |  |  | 0.05 | 0 | 0 | 100%
| 2962 | 3 | 16.2.7 | 변경전문 대응 처리방안 리뷰 |  |  | -1 | 2015-03-30 | 2015-04-03 | 0.05 | 5 |  |  | 0.05 | 0 | 0 | 100%
| 2963 | 2 | 16.3 | 구현 |  |  | 0 | 2015-03-02 | 2015-06-12 | 1.7 | 75 |  |  | 1.7 | 0 | 0 | 66.67%
| 2964 | 3 | 16.3.1 | 프로그램 구현 |  |  | 0 | 2015-03-02 | 2015-06-12 | 1.6 | 75 |  |  | 1.6 | 0 | 0 | 66.67%
| 2965 | 4 | 16.3.1.1 | 온라인 프로그램 구현 |  | 채널공통팀 | 0 | 2015-03-02 | 2015-06-12 | 0.6 | 75 |  |  | 0.6 | 0 | 0 | 66.67%
| 2966 | 5 | 16.3.1.1.1 | 온라인 프로그램 구현 | 온라인 프로그램 소스코드 | 채널공통팀 | 0 | 2015-03-30 | 2015-06-12 | 0.5 | 55 |  |  | 0.5 | 0 | 0 | 40%
| 2967 | 5 | 16.3.1.1.2 | 로그인/인증 | 로그인/인증 프로그램 소스코드 | 채널공통팀 | -1 | 2015-03-30 | 2015-04-10 | 0.1 | 10 |  |  | 0.1 | 0 | 0 | 100%
| 2968 | 4 | 16.3.1.2 | 배치 프로그램 구현 |  | 채널공통팀 | 0 | 2015-03-02 | 2015-06-12 | 0.2 | 75 |  |  | 0.2 | 0 | 0 | 66.67%
| 2969 | 5 | 16.3.1.2.1 | 배치 프로그램 구현 | 배치 프로그램 소스코드 | 채널공통팀 | 0 | 2015-03-02 | 2015-06-12 | 0.2 | 75 |  |  | 0.2 | 0 | 0 | 66.67%
| 2970 | 4 | 16.3.1.3 | SSO 프로그램 구현 |  | 채널공통팀 | 0 | 2015-04-06 | 2015-06-12 | 0.15 | 50 |  |  | 0.15 | 0 | 0 | 30%
| 2971 | 5 | 16.3.1.3.1 | SSO 설계 |  | 채널공통팀 | -1 | 2015-04-06 | 2015-04-17 | 0.05 | 10 |  |  | 0.05 | 0 | 0 | 100%
| 2972 | 5 | 16.3.1.3.2 | SSO 프로그램 구현 | SSO 프로그램 소스코드 | 채널공통팀 | 0 | 2015-04-20 | 2015-05-29 | 0.07 | 30 |  |  | 0.07 | 0 | 0 | 3.333%
| 2973 | 5 | 16.3.1.3.3 | SSO 단위 테스트 |  | 채널공통팀 | 0 | 2015-06-01 | 2015-06-12 | 0.03 | 10 |  |  | 0.03 | 0 | 0 | 0%
| 2974 | 4 | 16.3.1.4 | 메뉴관리 프로그램 구현 | 메뉴관리 프로그램 소스코드 | 채널공통팀 | 0 | 2015-03-02 | 2015-06-12 | 0.3 | 75 |  |  | 0.3 | 0 | 0 | 66.67%
| 2975 | 5 | 16.3.1.4.1 | 현 시스템 메뉴 분석 |  | 채널공통팀 | -1 | 2015-03-02 | 2015-03-13 | 0.08 | 10 |  |  | 0.08 | 0 | 0 | 100%
| 2976 | 5 | 16.3.1.4.2 | 메뉴관리 설계 | 테이블목록, ERD | 채널공통팀 | -1 | 2015-03-16 | 2015-04-03 | 0.07 | 15 |  |  | 0.07 | 0 | 0 | 100%
| 2977 | 5 | 16.3.1.4.3 | 메뉴관리 프로그램 구현 | 메뉴관리 프로그램 소스코드 | 채널공통팀 | 0 | 2015-04-06 | 2015-05-30 | 0.1 | 40 |  |  | 0.1 | 0 | 0 | 37.5%
| 2978 | 5 | 16.3.1.4.4 | 메뉴관리 단위테스트 |  | 채널공통팀 | 0 | 2015-06-01 | 2015-06-12 | 0.05 | 10 |  |  | 0.05 | 0 | 0 | 0%
| 2979 | 4 | 16.3.1.5 | 대응답 시스템 구축 |  | 채널공통팀 | -1 | 2015-02-09 | 2015-03-20 | 0.1 | 30 |  |  | 0.1 | 0 | 0 | 100%
| 2980 | 4 | 16.3.1.6 | 다국어 시스템 구축 |  | 채널공통팀 | -1 | 2015-02-09 | 2015-04-03 | 0.1 | 40 |  |  | 0.1 | 0 | 0 | 100%
| 2981 | 4 | 16.3.1.7 | 전문 맵퍼 |  | 채널공통팀 | 0 | 2015-02-09 | 2015-05-22 | 0.15 | 75 |  |  | 0.15 | 0 | 0 | 94.67%
| 2982 | 5 | 16.3.1.7.1 | 전문 맵퍼 프로그램 구현 | 전문 맵퍼 프로그램 소스 | 채널공통팀 | -1 | 2015-02-09 | 2015-03-13 | 0.06 | 25 |  |  | 0.06 | 0 | 0 | 100%
| 2983 | 5 | 16.3.1.7.2 | 전문 맵퍼 DB 설계 | 테이블목록, ERD | 채널공통팀 | -1 | 2015-03-16 | 2015-03-27 | 0.04 | 10 |  |  | 0.04 | 0 | 0 | 100%
| 2984 | 5 | 16.3.1.7.3 | 전문 맵퍼 관리자화면 구현 | 전문 맵퍼 프로그램 소스 | 채널공통팀 | 0 | 2015-03-30 | 2015-05-08 | 0.04 | 30 |  |  | 0.04 | 0 | 0 | 73.33%
| 2985 | 5 | 16.3.1.7.4 | 전문 맵퍼 단위 테스트 |  | 채널공통팀 | 0 | 2015-05-11 | 2015-05-22 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0%
| 2986 | 3 | 16.3.2 | 2차 개발 소스 보안취약점 점검 |  |  | 0 | 2015-04-13 | 2015-04-24 | 0.05 | 10 |  |  | 0.05 | 0 | 0 | 80%
| 2987 | 4 | 16.3.2.1 | 취약점 분석 |  | 채널공통팀 | -1 | 2015-04-13 | 2015-04-17 | 0.025 | 5 |  |  | 0.025 | 0 | 0 | 100%
| 2988 | 4 | 16.3.2.2 | 취약점 조치 및 가이드 문서 반영 | 개발가이드 문서 | 채널공통팀 | 0 | 2015-04-20 | 2015-04-24 | 0.025 | 5 |  |  | 0.025 | 0 | 0 | 20%
| 2989 | 3 | 16.3.3 | 3차 개발 소스 보안취약점 점검 |  |  | 0 | 2015-05-18 | 2015-05-29 | 0.05 | 10 |  |  | 0.05 | 0 | 0 | 0%
| 2990 | 4 | 16.3.3.1 | 취약점 분석 |  | 채널공통팀 | 0 | 2015-05-18 | 2015-05-22 | 0.025 | 5 |  |  | 0.025 | 0 | 0 | 0%
| 2991 | 4 | 16.3.3.2 | 취약점 조치 및 가이드 문서 반영 | 개발가이드 문서 | 채널공통팀 | 0 | 2015-05-26 | 2015-05-29 | 0.025 | 4 |  |  | 0.025 | 0 | 0 | 0%
| 2992 | 1 | 17 | 디자인/기획 |  |  | 0 | 2015-02-09 | 2015-11-06 | 4 |  |  |  | 4 |  |  | #DIV/0! | 100%
| 2993 | 2 | 17.1 | 분석 |  | 퓨즈와이어 | -1 | 2015-02-09 | 2015-02-27 | 0.07 |  |  |  | 0.07 |  |  |  | 100%
| 2994 | 3 | 17.1.1 | 컨셉도출 |  | 퓨즈와이어 | -1 | 2015-02-09 | 2015-02-13 | 0.04 |  |  |  | 0.04 |  |  |  | 100%
| 2995 | 4 | 17.1.1.1 | 사이트 현황 분석 및 사이트 분석 |  | 기획, 디자인, 퍼블리셔 | -1 | 2015-02-09 | 2015-02-13 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 2996 | 4 | 17.1.1.2 | 컨셉도출 및 디자인 방향 설정 |  | 디자인 | -1 | 2015-02-09 | 2015-02-13 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 2997 | 3 | 17.1.2 | 컨텐츠 수급 및 요구사항 정의 |  | 퓨즈와이어 | -1 | 2015-02-02 | 2015-02-27 | 0.03 |  |  |  | 0.03 |  |  |  | 100%
| 2998 | 4 | 12.1.2.1 | 내부문서수급(기존산출물, 양식, 기타) |  | 기획, 디자인, 퍼블리셔 | -1 | 2015-02-09 | 2015-02-17 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 2999 | 4 | 12.1.2.2 | 현업 요구사항 분석 |  | 기획, 디자인, 퍼블리셔 | -1 | 2015-02-09 | 2015-02-27 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3000 | 2 | 17.2 | 설계 |  | 퓨즈와이어 | 0 | 2015-02-09 | 2015-06-12 | 1.22 |  |  |  | 1.22 |  |  |  | 100%
| 3001 | 3 | 17.2.1 | 정보구조(IA)수립 |  | 퓨즈와이어 | -1 | 2015-02-09 | 2015-02-27 | 0.15 |  |  |  | 0.15 |  |  |  | 100%
| 3002 | 4 | 17.2.1.1 | 메뉴 구조 수립 |  | 기획자 | -1 | 2015-02-09 | 2015-02-13 | 0.05 |  |  |  | 0.05 |  |  |  | 0%
| 3003 | 4 | 17.2.1.2 | 통합 메뉴 IA 수립 및 확정 | 통합메뉴구조도 (IA) | 기획자 | -1 | 2015-02-16 | 2015-02-27 | 0.1 |  |  |  | 0.1 |  |  |  | 0%
| 3004 | 3 | 17.2.2 | 화면설계 |  | 퓨즈와이어 | 0 | 2015-02-09 | 2015-06-12 | 1.07 |  |  |  | 1.07 |  |  |  | 100%
| 3005 | 4 | 17.2.2.1 | 시안용 화면설계 (다국어뱅킹, 외환포탈, 글로벌맞춤뱅킹) |  | 기획자 | -1 | 2015-02-09 | 2015-02-17 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3006 | 4 | 17.2.2.2 | 화면설계 양식 작성 |  | 기획자 | -1 | 2015-02-09 | 2015-02-13 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3007 | 4 | 17.2.2.3 | 화면설계 (프로토타입 Leading) 작업 |  | 기획자 | -1 | 2015-02-09 | 2015-02-27 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3008 | 4 | 17.2.2.4 | 화면설계 (개인뱅킹) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.17 |  |  |  | 0.17 |  |  |  | 0%
| 3009 | 5 | 17.2.2.4.1 | MyHana |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3010 | 5 | 17.2.2.4.2 | 부가서비스 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3011 | 5 | 17.2.2.4.3 | 보험/공제 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3012 | 5 | 17.2.2.4.4 | 예금신탁 |  | 기획자 | -1 | 2015-03-09 | 2015-03-27 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3013 | 5 | 17.2.2.4.5 | 대출 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3014 | 5 | 17.2.2.4.6 | 펀드 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3015 | 5 | 17.2.2.4.7 | 이체 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3016 | 5 | 17.2.2.4.8 | 조회 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3017 | 5 | 17.2.2.4.9 | 카드 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3018 | 5 | 17.2.2.4.10 | 공과금 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3019 | 5 | 17.2.2.4.11 | 기업결제 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3020 | 5 | 17.2.2.4.12 | 외환 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3021 | 5 | 17.2.2.4.13 | 공인인증센터 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3022 | 5 | 17.2.2.4.14 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3023 | 4 | 17.2.2.5 | 화면설계 (오픈뱅킹) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.16 |  |  |  | 0.16 |  |  |  | 0%
| 3024 | 5 | 17.2.2.5.1 | MyHana |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3025 | 5 | 17.2.2.5.2 | 부가서비스 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3026 | 5 | 17.2.2.5.3 | 보험/공제 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3027 | 5 | 17.2.2.5.4 | 예금신탁 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3028 | 5 | 17.2.2.5.5 | 대출 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3029 | 5 | 17.2.2.5.6 | 펀드 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3030 | 5 | 17.2.2.5.7 | 이체 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3031 | 5 | 17.2.2.5.8 | 조회 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3032 | 5 | 17.2.2.5.9 | 카드 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3033 | 5 | 17.2.2.5.10 | 공과금 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3034 | 5 | 17.2.2.5.11 | 외환 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3035 | 5 | 17.2.2.5.12 | 공인인증센터 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3036 | 5 | 17.2.2.5.13 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3037 | 4 | 17.2.2.6 | 화면설계 (다국어뱅킹) |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.21 |  |  |  | 0.21 |  |  |  | 0%
| 3038 | 5 | 17.2.2.6.1 | 조회 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3039 | 5 | 17.2.2.6.2 | 이체 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3040 | 5 | 17.2.2.6.3 | 예금/해지 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3041 | 5 | 17.2.2.6.4 | 지로/공과금 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3042 | 5 | 17.2.2.6.5 | 공인인증썬터 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3043 | 5 | 17.2.2.6.6 | 송금/외화이체 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3044 | 5 | 17.2.2.6.7 | 외환매입매도 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3045 | 5 | 17.2.2.6.8 | 환율 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3046 | 5 | 17.2.2.6.9 | 대출 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3047 | 5 | 17.2.2.6.10 | 고객정보관리 / 한도관리 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3048 | 5 | 17.2.2.6.11 | 메인페이지 / 상품안내 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3049 | 5 | 17.2.2.6.12 | 퇴직연금 조회 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3050 | 5 | 17.2.2.6.13 | 공인인증센터 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3051 | 5 | 17.2.2.6.14 | 사고신고 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3052 | 5 | 17.2.2.6.15 | 내정보관리 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3053 | 5 | 17.2.2.6.16 | 보안센터 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3054 | 5 | 17.2.2.6.17 | 상품,서비스 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3055 | 5 | 17.2.2.6.18 | 유용한정보 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3056 | 5 | 17.2.2.6.19 | 고객센터 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3057 | 5 | 17.2.2.6.20 | 이용안내 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3058 | 5 | 17.2.2.6.21 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3059 | 4 | 17.2.2.7 | 화면설계 (외환포탈) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.09 |  |  |  | 0.09 |  |  |  | 0%
| 3060 | 5 | 17.2.2.7.1 | 환율(36) |  | 기획자 | -1 | 2015-02-23 | 2015-03-27 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3061 | 5 | 17.2.2.7.2 | 환전(61) |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3062 | 5 | 17.2.2.7.3 | 외화송금(55) |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3063 | 5 | 17.2.2.7.4 | FX딜링(194) |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3064 | 5 | 17.2.2.7.5 | 외화예금(53) |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3065 | 5 | 17.2.2.7.6 | FX우대서비스(11) |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3066 | 5 | 17.2.2.7.7 | 글로벌뱅킹(15) |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3067 | 5 | 17.2.2.7.8 | 기타(35) |  | 기획자 | -1 | 2015-03-09 | 2015-03-27 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3068 | 5 | 17.2.2.7.9 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3069 | 4 | 17.2.2.8 | 화면설계 (기업뱅킹) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.15 |  |  |  | 0.15 |  |  |  | 0%
| 3070 | 5 | 17.2.2.8.1 | 조회 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3071 | 5 | 17.2.2.8.2 | 이체 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3072 | 5 | 17.2.2.8.3 | 전자결제 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3073 | 5 | 17.2.2.8.4 | 수출입외환(외국환) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3074 | 5 | 17.2.2.8.5 | 대출 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3075 | 5 | 17.2.2.8.6 | 공과금 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3076 | 5 | 17.2.2.8.7 | 신규해지 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3077 | 5 | 17.2.2.8.8 | 통합자금관리 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3078 | 5 | 17.2.2.8.9 | 부가서비스 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3079 | 5 | 17.2.2.8.10 | 결재함 |  | 기획자 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3080 | 5 | 17.2.2.8.11 | 공인인증센터 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3081 | 5 | 17.2.2.8.12 | HanaCBS이용안내 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3082 | 5 | 17.2.2.8.13 | HanaCBS보안센터 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3083 | 5 | 17.2.2.8.14 | 사용자관리 |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3084 | 5 | 17.2.2.8.15 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3085 | 4 | 17.2.2.9 | 화면설계 (글로벌맞춤뱅킹) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.14 |  |  |  | 0.14 |  |  |  | 0%
| 3086 | 5 | 17.2.2.9.1 | 로그인 |  | 기획자 | -1 | 2015-02-23 | 2015-03-06 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3087 | 5 | 17.2.2.9.2 | 관리자서비스 |  | 기획자 | -1 | 2015-02-23 | 2015-03-27 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3088 | 5 | 17.2.2.9.3 | 조회보고서 |  | 기획자 | -1 | 2015-02-23 | 2015-03-27 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3089 | 5 | 17.2.2.9.4 | 지급 |  | 기획자 | -1 | 2015-02-23 | 2015-03-27 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3090 | 5 | 17.2.2.9.5 | 예금/대출 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3091 | 5 | 17.2.2.9.6 | 전자결제 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3092 | 5 | 17.2.2.9.7 | 외환/수출입 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3093 | 5 | 17.2.2.9.8 | 카드/부가서비스 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3094 | 5 | 17.2.2.9.9 | 자금관리 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3095 | 5 | 17.2.2.9.10 | 결재함/거래함 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3096 | 5 | 17.2.2.9.11 | 수납정보관리(KEBiSBs) |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3097 | 5 | 17.2.2.9.12 | 고시/수납관리 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3098 | 5 | 17.2.2.9.13 | 정산/대사관리 |  | 기획자 | 0 | 2015-03-30 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3099 | 5 | 17.2.2.9.14 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 기획자 | 0 | 2015-02-23 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3100 | 4 | 17.2.2.10 | 화면설계 수정 및 보완, 지원 |  | 기획자 | 0 | 2015-04-23 | 2015-06-12 | 0.1 |  |  |  | 0.1 |  |  |  | 0%
| 3101 | 2 | 17.3 | 구현 |  | 퓨즈와이어 | 0 | 2015-02-09 | 2015-06-12 | 8.71 |  |  |  | 8.71 |  |  |  | 100%
| 3102 | 3 | 17.3.1 | 디자인 구현 |  | 퓨즈와이어 | 0 | 2015-02-09 | 2015-06-12 | 1.36 |  |  |  | 1.36 |  |  |  | 100%
| 3103 | 4 | 17.3.1.1 | 웹스타일 가이드 제작 (신규사이트만 해당) |  | 디자이너 | 0 | 2015-02-09 | 2015-06-12 | 0.04 |  |  |  | 0.04 |  |  |  | 0%
| 3104 | 4 | 17.3.1.2 | 웹스타일 Leading 가이드 교육 |  | 디자이너 | -1 | 2015-02-16 | 2015-02-17 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3105 | 4 | 17.3.1.3 | 메인화면 디자인 시안 |  | 디자이너 | -1 | 2015-02-23 | 2015-03-20 | 0.1 |  |  |  | 0.1 |  |  |  | 0%
| 3106 | 4 | 17.3.1.4 | 디자인 가이드 제작 (신규사이트만 해당) |  | 디자이너 | 0 | 2015-02-16 | 2015-06-12 | 0.05 |  |  |  | 0.05 |  |  |  | 0%
| 3107 | 4 | 17.3.1.5 | 화면디자인 (개인뱅킹) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.17 |  |  |  | 0.17 |  |  |  | 0%
| 3108 | 5 | 17.3.1.5.1 | MyHana |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3109 | 5 | 17.3.1.5.2 | 부가서비스 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3110 | 5 | 17.3.1.5.3 | 보험/공제 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3111 | 5 | 17.3.1.5.4 | 예금신탁 |  | 디자이너 | -1 | 2015-03-16 | 2015-04-03 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3112 | 5 | 17.3.1.5.5 | 대출 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3113 | 5 | 17.3.1.5.6 | 펀드 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3114 | 5 | 17.3.1.5.7 | 이체 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3115 | 5 | 17.3.1.5.8 | 조회 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3116 | 5 | 17.3.1.5.9 | 카드 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3117 | 5 | 17.3.1.5.10 | 공과금 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3118 | 5 | 17.3.1.5.11 | 기업결제 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3119 | 5 | 17.3.1.5.12 | 외환 |  | 디자이너 | -1 | 2015-03-02 | 2015-04-03 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3120 | 5 | 17.3.1.5.13 | 공인인증센터 |  | 디자이너 | -1 | 2015-03-16 | 2015-04-03 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3121 | 5 | 17.3.1.5.14 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3122 | 4 | 17.3.1.6 | 화면디자인 (오픈뱅킹) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.16 |  |  |  | 0.16 |  |  |  | 0%
| 3123 | 5 | 17.3.1.6.1 | MyHana |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3124 | 5 | 17.3.1.6.2 | 부가서비스 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3125 | 5 | 17.3.1.6.3 | 보험/공제 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3126 | 5 | 17.3.1.6.4 | 예금신탁 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3127 | 5 | 17.3.1.6.5 | 대출 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3128 | 5 | 17.3.1.6.6 | 펀드 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3129 | 5 | 17.3.1.6.7 | 이체 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3130 | 5 | 17.3.1.6.8 | 조회 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3131 | 5 | 17.3.1.6.9 | 카드 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3132 | 5 | 17.3.1.6.10 | 공과금 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3133 | 5 | 17.3.1.6.11 | 외환 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3134 | 5 | 17.3.1.6.12 | 공인인증센터 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3135 | 5 | 17.3.1.6.13 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3136 | 4 | 17.3.1.7 | 화면디자인 (다국어뱅킹) |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.21 |  |  |  | 0.21 |  |  |  | 0%
| 3137 | 5 | 17.3.1.7.1 | 조회 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3138 | 5 | 17.3.1.7.1 | 이체 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3139 | 5 | 17.3.1.7.1 | 예금/해지 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3140 | 5 | 17.3.1.7.1 | 지로/공과금 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3141 | 5 | 17.3.1.7.1 | 공인인증썬터 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3142 | 5 | 17.3.1.7.1 | 송금/외화이체 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3143 | 5 | 17.3.1.7.1 | 외환매입매도 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3144 | 5 | 17.3.1.7.1 | 환율 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3145 | 5 | 17.3.1.7.1 | 대출 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3146 | 5 | 17.3.1.7.1 | 고객정보관리 / 한도관리 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3147 | 5 | 17.3.1.7.1 | 메인페이지 / 상품안내 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3148 | 5 | 17.3.1.7.1 | 퇴직연금 조회 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3149 | 5 | 17.3.1.7.1 | 공인인증센터 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3150 | 5 | 17.3.1.7.1 | 사고신고 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3151 | 5 | 17.3.1.7.1 | 내정보관리 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3152 | 5 | 17.3.1.7.1 | 보안센터 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3153 | 5 | 17.3.1.7.1 | 상품,서비스 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3154 | 5 | 17.3.1.7.1 | 유용한정보 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3155 | 5 | 17.3.1.7.1 | 고객센터 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3156 | 5 | 17.3.1.7.1 | 이용안내 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3157 | 5 | 17.3.1.7.1 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3158 | 4 | 17.3.1.8 | 화면디자인 (외환포탈) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.13 |  |  |  | 0.13 |  |  |  | 0%
| 3159 | 5 | 17.3.1.8.1 | 환율(36) |  | 디자이너 | -1 | 2015-03-02 | 2015-04-03 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3160 | 5 | 17.3.1.8.2 | 환전(61) |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3161 | 5 | 17.3.1.8.3 | 외화송금(55) |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3162 | 5 | 17.3.1.8.4 | FX딜링(194) |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3163 | 5 | 17.3.1.8.5 | 외화예금(53) |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3164 | 5 | 17.3.1.8.6 | FX우대서비스(11) |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3165 | 5 | 17.3.1.8.7 | 글로벌뱅킹(15) |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3166 | 5 | 17.3.1.8.8 | 기타(35) |  | 디자이너 | -1 | 2015-03-16 | 2015-04-03 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3167 | 5 | 17.3.1.8.9 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.04 |  |  |  | 0.04 |  |  |  | 0%
| 3168 | 4 | 17.3.1.9 | 화면디자인 (기업맹킹) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.15 |  |  |  | 0.15 |  |  |  | 0%
| 3169 | 5 | 17.3.1.9.1 | 조회 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3170 | 5 | 17.3.1.9.2 | 이체 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3171 | 5 | 17.3.1.9.3 | 전자결제 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3172 | 5 | 17.3.1.9.4 | 수출입외환(외국환) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3173 | 5 | 17.3.1.9.5 | 대출 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3174 | 5 | 17.3.1.9.6 | 공과금 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3175 | 5 | 17.3.1.9.7 | 신규해지 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3176 | 5 | 17.3.1.9.8 | 통합자금관리 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3177 | 5 | 17.3.1.9.9 | 부가서비스 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3178 | 5 | 17.3.1.9.10 | 결재함 |  | 디자이너 | 0 | 2015-03-16 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3179 | 5 | 17.3.1.9.11 | 공인인증센터 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3180 | 5 | 17.3.1.9.12 | HanaCBS이용안내 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3181 | 5 | 17.3.1.9.13 | HanaCBS보안센터 |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3182 | 5 | 17.3.1.9.14 | 사용자관리 |  | 디자이너 | 0 | 2015-03-02 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3183 | 5 | 17.3.1.9.15 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3184 | 4 | 17.3.1.10 | 화면디자인 (글로벌맞춤뱅킹) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.14 |  |  |  | 0.14 |  |  |  | 0%
| 3185 | 5 | 17.2.2.9.1 | 로그인 |  | 디자이너 | -1 | 2015-03-02 | 2015-03-13 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3186 | 5 | 17.2.2.9.2 | 관리자서비스 |  | 디자이너 | -1 | 2015-03-02 | 2015-04-03 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3187 | 5 | 17.2.2.9.3 | 조회보고서 |  | 디자이너 | -1 | 2015-03-02 | 2015-04-03 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3188 | 5 | 17.2.2.9.4 | 지급 |  | 디자이너 | -1 | 2015-03-02 | 2015-04-03 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3189 | 5 | 17.2.2.9.5 | 예금/대출 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3190 | 5 | 17.2.2.9.6 | 전자결제 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3191 | 5 | 17.2.2.9.7 | 외환/수출입 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3192 | 5 | 17.2.2.9.8 | 카드/부가서비스 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3193 | 5 | 17.2.2.9.9 | 자금관리 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3194 | 5 | 17.2.2.9.10 | 결재함/거래함 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3195 | 5 | 17.2.2.9.11 | 수납정보관리(KEBiSBs) |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3196 | 5 | 17.2.2.9.12 | 고시/수납관리 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3197 | 5 | 17.2.2.9.13 | 정산/대사관리 |  | 디자이너 | 0 | 2015-04-06 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3198 | 5 | 17.3.1.10.14 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3199 | 4 | 17.3.1.11 | 화면디자인 (스마트뱅킹) |  | 디자이너 | 0 | 2015-03-02 | 2015-05-07 | 0.1 |  |  |  | 0.1 |  |  |  | 0%
| 3200 | 4 | 17.3.1.12 | 화면디자인 수정 및 보완(퍼블/개발대응) |  | 디자이너 | 0 | 2015-05-08 | 2015-06-12 | 0.05 |  |  |  | 0.05 |  |  |  | 0%
| 3201 | 4 | 17.3.1.13 | 웹스타일, 디자인 가이드 수정 및 보완 |  | 디자이너 | 0 | 2015-05-08 | 2015-06-12 | 0.05 |  |  |  | 0.05 |  |  |  | 0%
| 3202 | 3 | 17.3.2 | 퍼블리싱 구현 |  | 퓨즈와이어 | 0 | 2015-02-23 | 2015-06-12 | 7.27 |  |  |  | 7.27 |  |  |  | 100%
| 3203 | 4 | 17.3.2.1 | 웹접근성 및 퍼블리싱 전파 교육 |  | 퍼블리셔 | -1 | 2015-03-02 | 2015-03-02 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3204 | 4 | 17.3.2.2 | HTML 퍼블리싱 (개인뱅킹) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.17 |  |  |  | 0.17 |  |  |  | 0%
| 3205 | 5 | 17.3.2.2.1 | MyHana |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3206 | 5 | 17.3.2.2.2 | 부가서비스 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3207 | 5 | 17.3.2.2.3 | 보험/공제 |  | 퍼블리셔 | 0 | 2015-03-23 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3208 | 5 | 17.3.2.2.4 | 예금신탁 |  | 퍼블리셔 | -1 | 2015-03-23 | 2015-04-10 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3209 | 5 | 17.3.2.2.5 | 대출 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3210 | 5 | 17.3.2.2.6 | 펀드 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3211 | 5 | 17.3.2.2.7 | 이체 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3212 | 5 | 17.3.2.2.8 | 조회 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3213 | 5 | 17.3.2.2.9 | 카드 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3214 | 5 | 17.3.2.2.10 | 공과금 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3215 | 5 | 17.3.2.2.11 | 기업결제 |  | 퍼블리셔 | 0 | 2015-03-23 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3216 | 5 | 17.3.2.2.12 | 외환 |  | 퍼블리셔 | -1 | 2015-03-09 | 2015-04-10 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3217 | 5 | 17.3.2.2.13 | 공인인증센터 |  | 퍼블리셔 | 0 | 2015-03-23 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3218 | 5 | 17.3.2.2.14 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3219 | 4 | 17.3.2.3 | HTML 퍼블리싱 (오픈뱅킹) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.16 |  |  |  | 0.16 |  |  |  | 0%
| 3220 | 5 | 17.3.2.3.1 | MyHana |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3221 | 5 | 17.3.2.3.2 | 부가서비스 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3222 | 5 | 17.3.2.3.3 | 보험/공제 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3223 | 5 | 17.3.2.3.4 | 예금신탁 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3224 | 5 | 17.3.2.3.5 | 대출 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3225 | 5 | 17.3.2.3.6 | 펀드 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3226 | 5 | 17.3.2.3.7 | 이체 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3227 | 5 | 17.3.2.3.8 | 조회 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3228 | 5 | 17.3.2.3.9 | 카드 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3229 | 5 | 17.3.2.3.10 | 공과금 |  | 퍼블리셔 | 0 | 2015-03-23 | 2015-05-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3230 | 5 | 17.3.2.3.11 | 외환 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3231 | 5 | 17.3.2.3.12 | 공인인증센터 |  | 퍼블리셔 | 0 | 2015-03-23 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3232 | 5 | 17.3.2.3.13 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3233 | 4 | 17.3.2.4 | HTML 퍼블리싱 (다국어뱅킹) |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.1 |  |  |  | 0.1 |  |  |  | 0%
| 3234 | 5 | 17.3.2.4.1 | 인터넷뱅킹 |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3235 | 5 | 17.3.2.4.2 | 공인인증센터 |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3236 | 5 | 17.3.2.4.3 | 사고신고 |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3237 | 5 | 17.3.2.4.4 | 내정보관리 |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3238 | 5 | 17.3.2.4.5 | 보안센터 |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3239 | 5 | 17.3.2.4.6 | 상품,서비스 |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3240 | 5 | 17.3.2.4.7 | 유용한정보 |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3241 | 5 | 17.3.2.4.8 | 고객센터 |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3242 | 5 | 17.3.2.4.9 | 이용안내 |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3243 | 5 | 17.3.2.4.10 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3244 | 4 | 17.3.2.5 | HTML 퍼블리싱 (외환포탈) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.13 |  |  |  | 0.13 |  |  |  | 0%
| 3245 | 5 | 17.3.2.5.1 | 환율(36) |  | 퍼블리셔 | -1 | 2015-03-09 | 2015-04-10 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3246 | 5 | 17.3.2.5.2 | 환전(61) |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3247 | 5 | 17.3.2.5.3 | 외화송금(55) |  | 퍼블리셔 | 0 | 2015-03-23 | 2015-05-22 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3248 | 5 | 17.3.2.5.4 | FX딜링(194) |  | 퍼블리셔 | 0 | 2015-03-23 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3249 | 5 | 17.3.2.5.5 | 외화예금(53) |  | 퍼블리셔 | 0 | 2015-03-23 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3250 | 5 | 17.3.2.5.6 | FX우대서비스(11) |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3251 | 5 | 17.3.2.5.7 | 글로벌뱅킹(15) |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3252 | 5 | 17.3.2.5.8 | 기타(35) |  | 퍼블리셔 | -1 | 2015-03-23 | 2015-04-10 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3253 | 5 | 17.3.2.5.9 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.04 |  |  |  | 0.04 |  |  |  | 0%
| 3254 | 4 | 17.3.2.6 | HTML 퍼블리싱 (기업맹킹) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.15 |  |  |  | 0.15 |  |  |  | 0%
| 3255 | 5 | 17.3.2.6.1 | 조회 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3256 | 5 | 17.3.2.6.2 | 이체 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3257 | 5 | 17.3.2.6.3 | 전자결제 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3258 | 5 | 17.3.2.6.4 | 수출입외환(외국환) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3259 | 5 | 17.3.2.6.5 | 대출 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3260 | 5 | 17.3.2.6.6 | 공과금 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3261 | 5 | 17.3.2.6.7 | 신규해지 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3262 | 5 | 17.3.2.6.8 | 통합자금관리 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3263 | 5 | 17.3.2.6.9 | 부가서비스 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3264 | 5 | 17.3.2.6.10 | 결재함 |  | 퍼블리셔 | 0 | 2015-03-23 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3265 | 5 | 17.3.2.6.11 | 공인인증센터 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3266 | 5 | 17.3.2.6.12 | HanaCBS이용안내 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3267 | 5 | 17.3.2.6.13 | HanaCBS보안센터 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3268 | 5 | 17.3.2.6.14 | 사용자관리 |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3269 | 5 | 17.3.2.6.15 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-04-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3270 | 4 | 17.3.2.7 | HTML 퍼블리싱 (글로벌맞춤뱅킹) |  | 퍼블리셔 | 0 | 2015-03-09 | 2015-05-22 | 0.14 |  |  |  | 0.14 |  |  |  | 0%
| 3271 | 5 | 17.2.2.9.1 | 로그인 |  | 퍼블리셔 | -1 | 2015-03-09 | 2015-03-20 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3272 | 5 | 17.2.2.9.2 | 관리자서비스 |  | 퍼블리셔 | -1 | 2015-03-09 | 2015-04-10 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3273 | 5 | 17.2.2.9.3 | 조회보고서 |  | 퍼블리셔 | -1 | 2015-03-09 | 2015-04-10 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3274 | 5 | 17.2.2.9.4 | 지급 |  | 퍼블리셔 | -1 | 2015-03-09 | 2015-04-10 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3275 | 5 | 17.2.2.9.5 | 예금/대출 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3276 | 5 | 17.2.2.9.6 | 전자결제 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3277 | 5 | 17.2.2.9.7 | 외환/수출입 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3278 | 5 | 17.2.2.9.8 | 카드/부가서비스 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3279 | 5 | 17.2.2.9.9 | 자금관리 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3280 | 5 | 17.2.2.9.10 | 결재함/거래함 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3281 | 5 | 17.2.2.9.11 | 수납정보관리(KEBiSBs) |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3282 | 5 | 17.2.2.9.12 | 고시/수납관리 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3283 | 5 | 17.2.2.9.13 | 정산/대사관리 |  | 퍼블리셔 | 0 | 2015-04-13 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3284 | 5 | 17.3.2.7.14 | 기타 및 공통 (메인, 푸터, 메뉴) |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.01 |  |  |  | 0.01 |  |  |  | 0%
| 3285 | 4 | 17.3.2.8 | HTML 퍼블리싱 (스마트뱅킹) |  | 퍼블리셔 | 0 | 2015-03-02 | 2015-05-22 | 0.1 |  |  |  | 0.1 |  |  |  | 0%
| 3286 | 4 | 17.3.2.9 | 공통관리자 (3월 2주, 4월 말) |  | 퍼블리셔 | 0 | 2015-02-23 | 2015-04-30 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3287 | 4 | 17.3.2.10 | HTML 퍼블리싱 수정 및 보완 |  | 퍼블리셔 | 0 | 2015-05-26 | 2015-06-12 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3288 | 4 | 17.3.2.11 | 웹접근성 테스트 후 수정 (1차) |  | 퍼블리셔(오픈뱅킹) | 0 | 2015-05-26 | 2015-05-28 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3289 | 4 | 17.3.2.12 | 웹접근성 테스트 후 수정 (2차) |  | 퍼블리셔(오픈뱅킹) | 0 | 2015-07-01 | 2015-07-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3290 | 4 | 17.3.2.13 | 웹접근성 테스트 후 수정 (3차) |  | 퍼블리셔(오픈뱅킹) | 0 | 2015-09-01 | 2015-09-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3291 | 4 | 17.3.2.14 | 웹접근성 테스트 후 수정 (4차) |  | 퍼블리셔(오픈뱅킹) | 0 | 2015-10-12 | 2015-10-16 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3292 | 3 | 17.3.3 | 웹접근성 컨설팅 |  | 웹접근성컨설턴트 | -1 | 2015-02-16 | 2015-02-17 | 0.02 |  |  |  | 0.02 |  |  |  | 100%
| 3293 | 4 | 17.3.3.1 | 웹접근성 교육 및 가이드 작성 |  | 컨설턴트(오픈뱅킹) | -1 | 2015-02-23 | 2015-02-24 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3294 | 2 | 17.4 | 통합테스트 |  |  | 0 | 2015-05-11 | 2015-10-16 | 0.2 |  |  |  | 0.2 |  |  |  | 100%
| 3295 | 3 | 17.4.1 | 테스트 결과 기획/디자인/퍼블리싱 수정 보완 진행 |  | 기획/디자인/퍼블 | 0 | 2015-06-15 | 2015-10-12 | 0.12 |  |  |  | 0.12 |  |  |  | 100%
| 3296 | 3 | 17.4.2 | 오픈뱅킹 웹접근성 점검 및 진단 |  | 웹접근성컨설턴트 | 0 | 2015-05-11 | 2015-10-16 | 0.08 |  |  |  | 0.08 |  |  |  | 100%
| 3297 | 4 | 17.4.2.1 | 웹접근성 테스트 (1차) |  | 컨설턴트(오픈뱅킹) | 0 | 2015-05-11 | 2015-05-15 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3298 | 4 | 17.4.2.2 | 웹접근성 테스트 (2차) |  | 컨설턴트(오픈뱅킹) | 0 | 2015-07-01 | 2015-07-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3299 | 4 | 17.4.2.3 | 웹접근성 테스트 (3차) |  | 컨설턴트(오픈뱅킹) | 0 | 2015-09-01 | 2015-09-07 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3300 | 4 | 17.4.2.4 | 웹접근성 테스트 (4차) |  | 컨설턴트(오픈뱅킹) | 0 | 2015-10-12 | 2015-10-16 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3301 | 2 | 17.5 | 매뉴얼 |  |  | 0 | 2015-10-19 | 2015-11-06 | 0.02 |  |  |  | 0.02 |  |  |  | 100%
| 3302 | 3 | 17.5.1 | 사용자메뉴얼 (신규/변경분) | 사용자메뉴얼 | 기획/디자인/퍼블 | 0 | 2015-10-19 | 2015-11-06 | 0.02 |  |  |  | 0.02 |  |  |  | 100%
| 3303 | 2 | 17.6 | 인증 |  |  | 0 | 2015-10-19 | 2015-11-06 | 0.02 |  |  |  | 0.02 |  |  |  | 100%
| 3304 | 3 | 17.6.1 | 웹접근성 인증 |  | 기획/디자인/퍼블 | 0 | 2015-10-19 | 2015-11-06 | 0.02 |  |  |  | 0.02 |  |  |  | 100%
| 3305 | 4 | 17.6.1.1 | 웹접근성 인증 신청 |  | 웹케시(오픈뱅킹) | 0 | 2015-10-19 | 2015-10-20 | 0 |  |  |  | 0 |  |  |  | 0%
| 3306 | 4 | 17.6.1.2 | 웹접근성 인증 심사 |  | 웹케시(오픈뱅킹) | 0 | 2015-10-21 | 2015-10-27 | 0 |  |  |  | 0 |  |  |  | 0%
| 3307 | 4 | 17.6.1.3 | 웹접근성 인증 심사 대응 |  | 기획, 디자인, 퍼블 대응 | 0 | 2015-10-28 | 2015-10-30 | 0.02 |  |  |  | 0.02 |  |  |  | 0%
| 3308 | 4 | 17.6.1.4 | 웹접근성 인증 완료 |  | 웹케시(오픈뱅킹) | 0 | 2015-11-02 | 2015-11-06 | 0 |  |  |  | 0 |  |  |  | 0%
| 3309 | 1 | 18 | 아키텍처 |  |  | 0 | 2015-02-09 | 2015-10-31 | 4 | 190 |  |  | 4 | 0 | 0 |  | 0%
| 3310 | 2 | 18.1 | 어플리케이션 |  |  | 0 | 2015-02-09 | 2015-10-31 | 4 | 190 |  |  | 4 | 0 | 0 |  | 0%
| 3311 | 3 | 18.1.1 | 양행 아키텍처 현황 분석 및 베이스라인 수립 |  |  | -1 | 2015-02-09 | 2015-02-27 | 4 | 15 |  |  | 4 | 0 | 0 |  | 0%
| 3312 | 4 | 18.1.1.1 | 현행 아키텍처 현황 분석을 위한 필요사항 정리 |  |  | -1 | 2015-02-09 | 2015-02-20 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3313 | 4 | 18.1.1.2 | 하나은행 전자금융 전체 아키텍처 분석 | 현행 아키텍처 분석서 |  | -1 | 2015-02-09 | 2015-02-20 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3314 | 5 | 18.1.1.2.1 | 현행 아키텍처 구성 분석 |  |  | -1 | 2015-02-09 | 2015-02-20 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3315 | 5 | 18.1.1.2.2 | 현행 아키텍처 분석서 작성 |  |  | -1 | 2015-02-09 | 2015-02-20 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3316 | 4 | 18.1.1.3 | 외환은행 외환포탈/글로벌 맞춤뱅킹 아키텍처 | 현행 아키텍처 분석서 |  | -1 | 2015-02-09 | 2015-02-20 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3317 | 5 | 18.1.1.3.1 | 현행 아키텍처 구성 분석 |  |  | -1 | 2015-02-09 | 2015-02-20 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3318 | 5 | 18.1.1.3.2 | 현행 아키텍처 분석서 작성 |  |  | -1 | 2015-02-09 | 2015-02-20 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3319 | 4 | 18.1.1.4 | 현행 아키텍처 베이스라인 수립 | 현행 아키텍처 정의서, 현행 정책정의서 |  | -1 | 2015-02-09 | 2015-02-20 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3320 | 5 | 18.1.1.4.1 | 현행 아키텍처 베이스라인 수립 |  |  | -1 | 2015-02-09 | 2015-02-20 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3321 | 5 | 18.1.1.4.2 | 현행 아키텍처 베이스라인 검토 및 보완 |  |  | -1 | 2015-02-23 | 2015-02-27 | 4 | 5 |  |  | 4 | 0 | 0 |  | 0%
| 3322 | 3 | 18.1.2 | GAP 분석 |  |  | -1 | 2015-02-23 | 2015-03-13 | 4 | 15 |  |  | 4 | 0 | 0 |  | 0%
| 3323 | 4 | 18.1.2.1 | 비기능요구사항정의 | 요구사항정의서 |  | -1 | 2015-02-23 | 2015-03-06 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3324 | 4 | 18.1.2.2 | 양행 어플리케이션 아키텍처 GAP분석 | GAP 분석서 |  | -1 | 2015-02-23 | 2015-03-06 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3325 | 5 | 18.1.2.2.1 | 요구사항접수분 아키텍처 GAP 분석 |  |  | -1 | 2015-02-23 | 2015-03-06 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3326 | 5 | 18.1.2.2.2 | 주요 정책 요소별 GAP 분석 |  |  | -1 | 2015-02-23 | 2015-03-06 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3327 | 4 | 18.1.2.3 | 양행 어플리케이션 아키텍처 GAP분석 검토 및 보완 |  |  | -1 | 2015-03-09 | 2015-03-13 | 4 | 5 |  |  | 4 | 0 | 0 |  | 0%
| 3328 | 3 | 18.1.3 | 통합 어플리케이션 아키텍처 수립 |  |  | -1 | 0 | 2015-04-10 | 4 | 25 |  |  | 4 | 0 | 0 |  | 0%
| 3329 | 4 | 18.1.3.1 | 아키텍처 GAP반영 및 통합 | 통합 아키텍처 정의서, 통합 정책정의서 |  | -1 | 2015-03-09 | 2015-04-03 | 4 | 20 |  |  | 4 | 0 | 0 |  | 0%
| 3330 | 5 | 18.1.3.1.1 | 요구사항접수분 아키텍처 GAP 반영 |  |  | -1 | 2015-03-09 | 2015-04-03 | 4 | 20 |  |  | 4 | 0 | 0 |  | 0%
| 3331 | 5 | 18.1.3.1.2 | 주요 정책 요소별 GAP 반영 및 통합 |  |  | -1 | 2015-03-09 | 2015-04-03 | 4 | 20 |  |  | 4 | 0 | 0 |  | 0%
| 3332 | 4 | 18.1.3.2 | 통합 어플리케이션 아키텍처 검토 및 보완 |  |  | -1 | 2015-04-06 | 2015-04-10 | 4 | 5 |  |  | 4
| 3333 | 3 | 18.1.4 | 채널공통파트와 협업 |  |  | 0 | 2015-02-23 | 2015-10-31 | 4 | 180 |  |  | 4 | 0 | 0 |  | 0%
| 3334 | 4 | 18.1.4.1 | 신규개발방식에 대한 전략분석 및 파일럿 가이드 지원 |  |  | -1 | 2015-02-23 | 2015-03-06 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3335 | 4 | 18.1.4.2 | 채널공통 어플리케이션 아키텍처 지원 |  |  | 0 | 2015-02-23 | 2015-10-31 | 4 | 180 |  |  | 4 | 0 | 0 |  | 0%
| 3336 | 3 | 18.1.5 | 전행 운영지원팀 어플리케이션 파트와 협업 |  |  | 0 | 2015-03-06 | 2015-10-31 | 4 | 171 |  |  | 4 | 0 | 0 |  | 0%
| 3337 | 4 | 18.1.5.1 | 상품처리전자금융 신규개발에 대한 아키텍처 지원 |  |  | 0 | 2015-03-06 | 2015-10-31 | 4 | 171 |  |  | 4 | 0 | 0 |  | 0%
| 3338 | 4 | 18.1.5.2 | 전행 어플리케이션 아키텍처 지원 |  |  | 0 | 2015-03-06 | 2015-10-31 | 4 | 171 |  |  | 4 | 0 | 0 |  | 0%
| 3339 | 3 | 18.1.6 | 어플리케이션 표준점검 및 가이드 |  |  | 0 | 2015-04-06 | 2015-06-12 | 4 | 50 |  |  | 4 | 0 | 0 |  | 0%
| 3340 | 4 | 18.1.6.1 | 어플리케이션 표준점검 및 가이드 1차 |  |  | 0 | 2015-04-06 | 2015-04-30 | 4 | 19 |  |  | 4 | 0 | 0 |  | 0%
| 3341 | 4 | 18.1.6.2 | 어플리케이션 표준점검 및 가이드 2차 |  |  | 0 | 2015-05-04 | 2015-05-29 | 4 | 20 |  |  | 4 | 0 | 0 |  | 0%
| 3342 | 4 | 18.1.6.3 | 아키텍처 변화관리 | 통합 아키텍처정의서(정제) |  | 0 | 2015-06-01 | 2015-06-12 | 4 | 10 |  |  | 4
| 3343 | 3 | 18.1.7 | 테스트 |  |  | 0 | 2015-06-15 | 2015-09-30 | 4 | 78 |  |  | 4 | 0 | 0 |  | 0%
| 3344 | 4 | 18.1.7.1 | 통합 테스트 지원 |  |  | 0 | 2015-06-15 | 2015-09-30 | 4 | 78 |  |  | 4
| 3345 | 4 | 18.1.7.2 | 성능튜닝 지원 |  |  | 0 | 2015-06-16 | 2015-09-30 | 4 | 77 |  |  | 4 | 0 | 0 |  | 0%
| 3346 | 4 | 18.1.7.3 | 이행테스트 지원 |  |  | 0 | 2015-06-16 | 2015-09-30 | 4 | 77 |  |  | 4
| 3347 | 3 | 18.1.8 | 이행계획 |  |  | 0 | 2015-06-01 | 2015-08-28 | 4 | 65 |  |  | 4 | 0 | 0 |  | 0%
| 3348 | 4 | 18.1.8.1 | AS-IS시스템 변경관리 방안 절차 수립 및 지원 |  |  | 0 | 2015-06-01 | 2015-08-28 | 4 | 65 |  |  | 4 | 0 | 0 |  | 0%
| 3349 | 4 | 18.1.8.2 | 이행계획지원 | 이행체크리스트 |  | 0 | 2015-08-17 | 2015-08-28 | 4 | 10 |  |  | 4 | 0 | 0 |  | 0%
| 3350 | 3 | 18.1.9 | Day-3 통합 아키텍처 청사진 수립 |  |  | 0 | 2015-10-05 | 2015-10-30 | 4 | 20 |  |  | 4 | 0 | 0 |  | 0%
| 3351 | 4 | 18.1.9.1 | 차후 개선과제 도출 |  |  | 0 | 2015-10-05 | 2015-10-30 | 4 | 20 |  |  | 4 | 0 | 0 |  | 0%
| 3352 | 4 | 18.1.9.2 | 개선방안 도출 및 보고서 작성 |  |  | 0 | 2015-10-05 | 2015-10-30 | 4 | 20 |  |  | 4 | 0 | 0 |  | 0%
| 3353 | 3 | 18.1.10 | 안정화 |  |  | 0 | 2015-10-19 | 2015-10-30 | 4 | 10 |  |  | 4
| 3354 | 2 | 18.2 | 데이터 |  |  | 0 | 2015-02-09 | 2015-09-30 | 4 | 168 |  |  | 4 | 0 | 0 |  | 100%
| 3355 | 3 | 18.2.1 | 양행 현행 시스템 분석 |  |  | -1 | 2015-02-09 | 2015-02-17 | 4 | 7 |  |  | 4 | 0 | 0 |  | 200%
| 3356 | 4 | 18.2.1.1 | 양행 시스템 현황 분석 |  |  | -1 | 2015-02-09 | 2015-02-13 | 4 | 5 |  |  | 4 | 0 | 0 |  | 300%
| 3357 | 4 | 18.2.1.2 | 양행 데이터 GAP 분석 |  |  | -1 | 2015-02-16 | 2015-02-17 | 4 | 2 |  |  | 4 | 0 | 0 |  | 400%
| 3358 | 3 | 18.2.2 | 통합 요건 정의 |  |  | -1 | 2015-02-23 | 2015-02-25 | 4 | 3 |  |  | 4 | 0 | 0 |  | 500%
| 3359 | 3 | 18.2.3 | 논리모델 설계 |  |  | -1 | 2015-02-26 | 2015-03-13 | 4 | 12 |  |  | 4 | 0 | 0 |  | 600%
| 3360 | 4 | 18.2.3.1 | 자료사전 작성 | 자료사전 | 분석/설계자1 | -1 | 2015-02-26 | 2015-03-05 | 4 | 6 |  |  | 4 | 0 | 0 |  | 700%
| 3361 | 4 | 18.2.3.2 | 논리모델 작성 | 논리 데이터 모델 | 분석/설계자1 | -1 | 2015-03-06 | 2015-03-13 | 4 | 6 |  |  | 4 | 0 | 0 |  | 800%
| 3362 | 4 | 18.2.3.3 | 엔티티정의서 작성 | 엔티티정의서 | 분석/설계자1 | -1 | 2015-03-13 | 2015-03-13 | 4 | 1 |  |  | 4 | 0 | 0 |  | 900%
| 3363 | 1 | 19 | 테스트 관리 |  | 테스트 총괄 | 0 | 2015-02-09 | 2015-09-30 | 5 | 168 |  |  | 5 | 0 | 0 | 42.26% | #REF!
| 3364 | 2 | 19.1 | 테스트 환경 분석 | 테스트 계획서 | 테스트 총괄 | -1 | 2015-02-09 | 2015-02-27 | 0.1 | 15 |  |  | 0.1 | 0 | 0 | 100% | #REF!
| 3365 | 3 | 19.1.1 | 업무별 요건 분류(신규, 유지 등) |  | 테스트 총괄 | -1 | 2015-02-09 | 2015-02-10 | 0.1 | 2 |  |  | 0.1 | 0 | 0 | 100% | 20%
| 3366 | 4 | 19.1.1.1 | 요건 분석 |  |  | -1 | 2015-02-09 | 2015-02-10 | 0.02 | 2 |  |  | 0.02 | 0 | 0 | 100% | #REF!
| 3367 | 5 | 19.1.1.1.1 | 유지 메뉴 요건 분석 |  | 테스트 총괄 | -1 | 2015-02-09 | 2015-02-10 | 0.01 | 2 |  |  | 0.01 | 0 | 0 | 100% | 20%
| 3368 | 5 | 19.1.1.1.2 | 변경/신규 메뉴 요건 분석 |  | 테스트 총괄 | -1 | 2015-02-09 | 2015-02-10 | 0.01 | 2 |  |  | 0.01 | 0 | 0 | 100% | #REF!
| 3369 | 4 | 19.1.1.2 | 테스트 대상 메뉴 분류 / 확정 |  | 테스트 총괄 | -1 | 2015-02-11 | 2015-02-11 | 0.02 | 1 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 3370 | 4 | 19.1.1.3 | 시나리오 작성 가이드 작성 |  | 테스트 총괄 | -1 | 2015-02-12 | 2015-02-27 | 0.06 | 12 |  |  | 0.06 | 0 | 0 | 100% | 0%
| 3371 | 5 | 19.1.1.3.1 | 유지메뉴 중 샘플 시나리오 작성 |  | 테스트 총괄 | -1 | 2015-02-12 | 2015-02-16 | 0.02 | 3 |  |  | 0.02 | 0 | 0 | 100% | 0%
| 3372 | 5 | 19.1.1.3.2 | 샘플 시나리오 검토 |  | 테스트 총괄 | -1 | 2015-02-17 | 2015-02-17 | 0.01 | 1 |  |  | 0.01 | 0 | 0 | 100% | 0%
| 3373 | 5 | 19.1.1.3.3 | 샘플 시나리오를 활용한 가이드 작성 |  | 테스트 총괄 | -1 | 2015-02-23 | 2015-02-27 | 0.03 | 5 |  |  | 0.03 | 0 | 0 | 100% | 0%
| 3374 | 2 | 19.2 | 통합 테스트 시나리오 작성 | 통합테스트 시나리오 | 테스트 리드 | 0 | 2015-03-02 | 2015-06-12 | 2 | 75 |  |  | 2 | 0 | 0 | 66.67% | 0%
| 3375 | 3 | 19.2.1 | 유지 메뉴 시나리오 작성 |  | 테스트 리드 | -1 | 2015-03-02 | 2015-04-10 | 0.7 | 30 |  |  | 0.7 | 0 | 0 | 100% | 0%
| 3376 | 4 | 19.2.1.1 | 개인부분 유지메뉴 시나리오 작성 |  | 테스트 리드 | -1 | 2015-03-02 | 2015-03-27 | 0.3 | 20 |  |  | 0.3 | 0 | 0 | 100% | 0%
| 3377 | 5 | 19.2.1.1.1 | 개인뱅킹 |  |  | -1 | 2015-03-02 | 2015-03-27 | 0.1 | 20 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 3378 | 5 | 19.2.1.1.2 | 오픈뱅킹 |  |  | -1 | 2015-03-02 | 2015-03-27 | 0.1 | 20 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 3379 | 5 | 19.2.1.1.3 | 다국어뱅킹 |  |  | -1 | 2015-03-02 | 2015-03-13 | 0.05 | 10 |  |  | 0.05 | 0 | 0 | 100% | 0%
| 3380 | 5 | 19.2.1.1.4 | 외환포털 |  |  | -1 | 2015-03-16 | 2015-03-27 | 0.05 | 10 |  |  | 0.05 | 0 | 0 | 100% | 0%
| 3381 | 4 | 19.2.1.2 | 기업/CMS부분 유지메뉴 시나리오 작성 |  | 테스트 리드 | -1 | 2015-03-02 | 2015-04-10 | 0.3 | 30 |  |  | 0.3 | 0 | 0 | 100% | 0%
| 3382 | 5 | 19.2.1.2.1 | 기업뱅킹 |  |  | -1 | 2015-03-02 | 2015-03-27 | 0.2 | 20 |  |  | 0.2 | 0 | 0 | 100% | 0%
| 3383 | 5 | 19.2.1.2.2 | CMS |  |  | -1 | 2015-03-30 | 2015-04-10 | 0.1 | 10 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 3384 | 4 | 19.2.1.3 | 상품처리/콜센터 유지메뉴 시나리오 작성 |  | 테스트 리드 | -1 | 2015-03-30 | 2015-04-10 | 0.1 | 10 |  |  | 0.1 | 0 | 0 | 100% | 0%
| 3385 | 5 | 19.2.1.3.1 | 상품처리 |  |  | -1 | 2015-03-30 | 2015-04-10 | 0.05 | 10 |  |  | 0.05 |  |  | 100%
| 3386 | 5 | 19.2.1.3.2 | 콜센터 상담 지원 |  |  | -1 | 2015-03-30 | 2015-04-10 | 0.05 | 10 |  |  | 0.05 |  |  | 100%
| 3387 | 3 | 19.2.2 | 변경/신규 메뉴 시나리오 작성 |  | 테스트 리드 | 0 | 2015-04-13 | 2015-05-22 | 1 | 30 |  |  | 1 | 0 | 0 | 26.67% | 0%
| 3388 | 4 | 19.2.2.1 | 개인부분 변경/신규 메뉴 |  | 테스트 리드 | 0 | 2015-04-13 | 2015-05-08 | 0.4 | 20 |  |  | 0.4 | 0 | 0 | 40% | 0%
| 3389 | 5 | 19.2.2.1.1 | 개인뱅킹 |  |  | 0 | 2015-04-13 | 2015-05-08 | 0.15 | 20 |  |  | 0.15 |  |  | 40%
| 3390 | 5 | 19.2.2.1.2 | 오픈뱅킹 |  |  | 0 | 2015-04-13 | 2015-05-08 | 0.15 | 20 |  |  | 0.15 |  |  | 40%
| 3391 | 5 | 19.2.2.1.3 | 다국어뱅킹 |  |  | 0 | 2015-04-13 | 2015-04-24 | 0.05 | 10 |  |  | 0.05 |  |  | 80%
| 3392 | 5 | 19.2.2.1.4 | 외환포털 |  |  | 0 | 2015-04-27 | 2015-05-08 | 0.05 | 10 |  |  | 0.05 |  |  | 0%
| 3393 | 4 | 19.2.2.2 | 기업/CMS부분 변경/신규 메뉴 |  | 테스트 리드 | 0 | 2015-04-13 | 2015-05-22 | 0.4 | 30 |  |  | 0.4 | 0 | 0 | 26.67% | 0%
| 3394 | 5 | 19.2.2.2.1 | 기업뱅킹 |  |  | 0 | 2015-04-13 | 2015-05-08 | 0.25 | 20 |  |  | 0.25 |  |  | 40%
| 3395 | 5 | 19.2.2.2.2 | CMS |  |  | 0 | 2015-05-11 | 2015-05-22 | 0.15 | 10 |  |  | 0.15 |  |  | 0%
| 3396 | 4 | 19.2.2.3 | 상품처리/기타부분 변경/신규 메뉴 |  | 테스트 리드 | 0 | 2015-05-11 | 2015-05-22 | 0.2 | 10 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3397 | 5 | 19.2.2.3.1 | 상품처리 |  |  | 0 | 2015-05-11 | 2015-05-22 | 0.1 | 10 |  |  | 0.1 |  |  | 0%
| 3398 | 5 | 19.2.2.3.2 | 콜센터 상담 지원 |  |  | 0 | 2015-05-11 | 2015-05-22 | 0.1 | 10 |  |  | 0.1 |  |  | 0%
| 3399 | 3 | 19.2.3 | 시나리오 검토 |  |  | 0 | 2015-05-26 | 2015-06-12 | 0.3 | 14 |  |  | 0.3 | 0 | 0 | 0% | 0%
| 3400 | 4 | 19.2.3.1 | 테스트 리드팀 내부 교차 검토 |  |  | 0 | 2015-05-26 | 2015-05-29 | 0.1 | 4 |  |  | 0.1 | 0 | 0 | 0% | 0%
| 3401 | 4 | 19.2.3.2 | 개발자와의 교차 검토 |  |  | 0 | 2015-06-01 | 2015-06-12 | 0.2 | 10 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3402 | 2 | 19.3 | 단위 테스트 지원 |  | 테스트 전담반 | 0 | 2015-05-26 | 2015-06-12 | 0.1 | 14 |  |  | 0.1 | 0 | 0 | 0% | 0%
| 3403 | 3 | 19.3.1 | 단위 테스트 케이스 검토 |  | 테스트 전담반 | 0 | 2015-05-26 | 2015-05-29 | 0.07 | 4 |  |  | 0.07 | 0 | 0 | 0% | 0%
| 3404 | 4 | 19.3.1.1 | 개인부분 검토 |  | 테스트 전담반 | 0 | 2015-05-26 | 2015-05-29 | 0.02 | 4 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3405 | 4 | 19.3.1.2 | 기업/I-vostro/CMS부분 검토 |  | 테스트 전담반 | 0 | 2015-05-26 | 2015-05-29 | 0.02 | 4 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3406 | 4 | 19.3.1.3 | 스마트부분 검토 |  | 테스트 전담반 | 0 | 2015-05-26 | 2015-05-29 | 0.02 | 4 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3407 | 4 | 19.3.1.3 | 상품처리/기타부분 검토 |  | 테스트 전담반 | 0 | 2015-05-26 | 2015-05-29 | 0.01 | 4 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3408 | 3 | 19.3.2 | 단위 테스트 수행 지원 |  | 테스트 전담반 | 0 | 2015-06-01 | 2015-06-12 | 0.03 | 10 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 3409 | 4 | 19.3.2.1 | 개인부분 수행 지원 |  | 테스트 전담반 | 0 | 2015-06-01 | 2015-06-12 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3410 | 4 | 19.3.2.2 | 기업/I-vostro/CMS부분 수행 지원 |  | 테스트 전담반 | 0 | 2015-06-01 | 2015-06-12 | 0.01 | 10 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3411 | 4 | 19.3.2.3 | 스마트부분 수행 지원 |  | 테스트 전담반 | 0 | 2015-06-01 | 2015-06-12 | 0.005 | 10 |  |  | 0.005 | 0 | 0 | 0% | 0%
| 3412 | 4 | 19.3.2.4 | 상품처리/기타부분 수행 지원 |  | 테스트 전담반 | 0 | 2015-06-01 | 2015-06-12 | 0.005 | 10 |  |  | 0.005 | 0 | 0 | 0% | 0%
| 3413 | 2 | 19.4 | 통합테스트 1차 | 통합테스트 결과서(1차) | 테스트 전담반 | 0 | 2015-06-15 | 2015-07-17 | 0.5 | 25 |  |  | 0.5 | 0 | 0 | 0% | 0%
| 3414 | 3 | 19.4.1 | 통합테스트 수행 |  | 테스트 전담반 | 0 | 2015-06-15 | 2015-07-10 | 0.2 | 20 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3415 | 3 | 19.4.2 | 결함 수정 |  | 테스트 전담반 | 0 | 2015-06-16 | 2015-07-15 | 0.2 | 22 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3416 | 3 | 19.4.3 | 조치 결과 재테스트 |  | 테스트 전담반 | 0 | 2015-06-17 | 2015-07-16 | 0.08 | 22 |  |  | 0.08 | 0 | 0 | 0% | 0%
| 3417 | 3 | 19.4.4 | 통합테스트 수행 결과서 작성 |  | 테스트 전담반 | 0 | 2015-07-13 | 2015-07-17 | 0.02 | 5 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3418 | 2 | 19.5 | 영업점 테스트 1차(통합TFT팀) |  | 테스트 전담반 & 통합 TFT팀 | 0 | 2015-07-18 | 2015-07-18 | 0.05 | 0 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 3419 | 3 | 19.5.1 | 영업점 테스트 수행 |  | 테스트 전담반 & 통합 TFT팀 | 0 | 2015-07-18 | 2015-07-18 | 0.04 | 0 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 3420 | 3 | 19.5.2 | 영업점 테스트 수행 결과서 작성 |  | 테스트 전담반 & 통합 TFT팀 | 0 | 2015-07-18 | 2015-07-18 | 0.01 | 0 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3421 | 2 | 19.6 | 통합테스트 2차 | 통합테스트 결과서(2차) | 테스트 전담반 | 0 | 2015-07-20 | 2015-08-07 | 0.5 | 15 |  |  | 0.5 | 0 | 0 | 0% | 0%
| 3422 | 3 | 19.6.1 | 통합테스트 수행 |  | 테스트 전담반 | 0 | 2015-07-20 | 2015-07-31 | 0.2 | 10 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3423 | 3 | 19.6.2 | 결함 수정 |  | 테스트 전담반 | 0 | 2015-07-21 | 2015-08-05 | 0.2 | 12 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3424 | 3 | 19.6.3 | 조치 결과 재테스트 |  | 테스트 전담반 | 0 | 2015-07-22 | 2015-08-06 | 0.08 | 12 |  |  | 0.08 | 0 | 0 | 0% | 0%
| 3425 | 3 | 19.6.4 | 통합테스트 수행 결과서 작성 |  | 테스트 전담반 | 0 | 2015-08-03 | 2015-08-07 | 0.02 | 5 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3426 | 2 | 19.7 | 영업점 테스트 2차(전산팀) |  | 테스트 전담반 & 전산팀 | 0 | 2015-08-08 | 2015-08-08 | 0.05 | 0 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 3427 | 3 | 19.7.1 | 영업점 테스트 수행 |  | 테스트 전담반 & 전산팀 | 0 | 2015-08-08 | 2015-08-08 | 0.04 | 0 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 3428 | 3 | 19.7.2 | 영업점 테스트 수행 결과서 작성 |  | 테스트 전담반 & 전산팀 | 0 | 2015-08-08 | 2015-08-08 | 0.01 | 0 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3429 | 2 | 19.8 | 통합테스트 3차 | 통합테스트 결과서(3차) | 테스트 전담반 | 0 | 2015-08-10 | 2015-09-04 | 0.5 | 20 |  |  | 0.5 | 0 | 0 | 0% | 0%
| 3430 | 3 | 19.8.1 | 통합테스트 수행 |  | 테스트 전담반 | 0 | 2015-08-10 | 2015-08-28 | 0.2 | 15 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3431 | 3 | 19.8.2 | 결함 수정 |  | 테스트 전담반 | 0 | 2015-08-11 | 2015-09-02 | 0.2 | 17 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3432 | 3 | 19.8.3 | 조치 결과 재테스트 |  | 테스트 전담반 | 0 | 2015-08-12 | 2015-09-03 | 0.08 | 17 |  |  | 0.08 | 0 | 0 | 0% | 0%
| 3433 | 3 | 19.8.4 | 통합테스트 수행 결과서 작성 |  | 테스트 전담반 | 0 | 2015-08-31 | 2015-09-04 | 0.02 | 5 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3434 | 2 | 19.9 | 알파테스트 | 알파테스트 결과서 | 알파테스트 수행팀 | 0 | 2015-08-10 | 2015-09-04 | 0.2 | 20 |  |  | 0.2 | 0 | 0 | 0% | #REF!
| 3435 | 3 | 19.8.1 | 알파테스트 수행 |  | 알파테스트 수행팀 | 0 | 2015-08-10 | 2015-08-28 | 0.08 | 15 |  |  | 0.08 | 0 | 0 | 0% | 0%
| 3436 | 3 | 19.8.2 | 결함 수정 |  | 알파테스트 수행팀 | 0 | 2015-08-11 | 2015-09-02 | 0.08 | 17 |  |  | 0.08 | 0 | 0 | 0% | 0%
| 3437 | 3 | 19.8.3 | 조치 결과 재테스트 |  | 알파테스트 수행팀 | 0 | 2015-08-12 | 2015-09-03 | 0.03 | 17 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 3438 | 3 | 19.8.4 | 알파테스트 수행 결과서 작성 |  | 알파테스트 수행팀 | 0 | 2015-08-31 | 2015-09-04 | 0.01 | 5 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3439 | 2 | 19.10 | 영업점 테스트 3차(본부) |  | 테스트 전담반 & 본부 | 0 | 2015-09-05 | 2015-09-05 | 0.05 | 0 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 3440 | 3 | 19.10.1 | 영업점 테스트 수행 |  | 테스트 전담반 & 본부 | 0 | 2015-09-05 | 2015-09-05 | 0.04 | 0 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 3441 | 3 | 19.10.2 | 영업점 테스트 수행 결과서 작성 |  | 테스트 전담반 & 본부 | 0 | 2015-09-05 | 2015-09-05 | 0.01 | 0 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3442 | 2 | 19.11 | 통합테스트 4차 | 통합테스트 결과서(4차) | 테스트 전담반 | 0 | 2015-09-07 | 2015-09-25 | 0.5 | 15 |  |  | 0.5 | 0 | 0 | 0% | 0%
| 3443 | 3 | 19.11.1 | 통합테스트 수행 |  | 테스트 전담반 | 0 | 2015-09-07 | 2015-09-18 | 0.2 | 10 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3444 | 3 | 19.11.2 | 결함 수정 |  | 테스트 전담반 | 0 | 2015-09-08 | 2015-09-23 | 0.2 | 12 |  |  | 0.2 | 0 | 0 | 0% | 0%
| 3445 | 3 | 19.11.3 | 조치 결과 재테스트 |  | 테스트 전담반 | 0 | 2015-09-09 | 2015-09-24 | 0.08 | 12 |  |  | 0.08 | 0 | 0 | 0% | 0%
| 3446 | 3 | 19.11.4 | 통합테스트 수행 결과서 작성 |  | 테스트 전담반 | 0 | 2015-09-21 | 2015-09-25 | 0.02 | 5 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3447 | 2 | 19.10 | 영업점 테스트 4차(영업점) |  | 테스트 전담반 & 영업점 | 0 | 2015-09-20 | 2015-09-20 | 0.05 | 0 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 3448 | 3 | 19.10.1 | 영업점 테스트 수행 |  | 테스트 전담반 & 영업점 | 0 | 2015-09-20 | 2015-09-20 | 0.04 | 0 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 3449 | 3 | 19.10.2 | 영업점 테스트 수행 결과서 작성 |  | 테스트 전담반 & 영업점 | 0 | 2015-09-20 | 2015-09-20 | 0.01 | 0 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3450 | 2 | 19.11 | 성능테스트 |  | 테스트 리드 & 테스트 전담반 | 0 | 2015-06-15 | 2015-09-30 | 0.4 | 78 |  |  | 0.4 | 0 | 0 | 0% | 0%
| 3451 | 3 | 19.11.1 | 성능 테스트 분석 |  | 성능테스트 수행팀 | 0 | 2015-06-15 | 2015-07-28 | 0.05 | 32 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 3452 | 4 | 19.11.1.1 | 성능 테스트 계획서 작성 | 성능 테스트 계획서 | 성능테스트 수행팀 | 0 | 2015-06-15 | 2015-06-19 | 0.03 | 5 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 3453 | 4 | 19.11.1.2 | 대상 업무 인터뷰 |  | 성능테스트 수행팀 | 0 | 2015-07-01 | 2015-07-08 | 0.02 | 6 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3454 | 3 | 19.11.2 | 성능 테스트 설계 |  | 성능테스트 수행팀 | 0 | 2015-06-22 | 2015-07-16 | 0.05 | 19 |  |  | 0.05 | 0 | 0 | 0% | 0%
| 3455 | 4 | 19.11.2.1 | WorkLoadModel 수립(대상 업무 확정 포함) | 성능테스트 상세 설계서 | 성능테스트 수행팀 | 0 | 2015-06-22 | 2015-06-26 | 0.02 | 5 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3456 | 4 | 19.11.2.2 | 시스템 모니터링 항목 확정 |  | 성능테스트 수행팀 | 0 | 2015-07-09 | 2015-07-09 | 0.02 | 1 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3457 | 4 | 19.11.2.3 | 기술적용성검토(암호화모듈) |  | 성능테스트 수행팀 | 0 | 2015-07-10 | 2015-07-16 | 0.01 | 5 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3458 | 3 | 19.11.3 | 성능테스트구현 |  | 성능테스트 수행팀 | 0 | 2015-07-15 | 2015-08-14 | 0.1 | 23 |  |  | 0.1 | 0 | 0 | 0% | 0%
| 3459 | 4 | 19.11.3.1 | 성능 테스트 환경 셋업 |  | 성능테스트 수행팀 | 0 | 2015-07-15 | 2015-07-17 | 0.01 | 3 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3460 | 4 | 19.11.3.2 | 부하 발생 환경 셋업 |  | 성능테스트 수행팀 | 0 | 2015-07-17 | 2015-07-17 | 0.02 | 1 |  |  | 0.02 | 0 | 0 | 0% | 0%
| 3461 | 4 | 19.11.3.3 | 테스트 데이터 생성/관리 |  | 성능테스트 수행팀 | 0 | 2015-07-20 | 2015-07-24 | 0.03 | 5 |  |  | 0.03 | 0 | 0 | 0% | 0%
| 3462 | 4 | 19.11.3.4 | Script구현 |  | 성능테스트 수행팀 | 0 | 2015-07-20 | 2015-08-14 | 0.04 | 20 |  |  | 0.04 | 0 | 0 | 0% | 0%
| 3463 | 3 | 19.11.4 | 성능 테스트 실행 |  | 성능테스트 수행팀 | 0 | 2015-07-27 | 2015-09-30 | 0.15 | 48 |  |  | 0.15 | 0 | 0 | 0% | 0%
| 3464 | 4 | 19.11.4.1 | 단위 성능 테스트 - 개인 뱅킹 |  | 성능테스트 수행팀 | 0 | 2015-07-27 | 2015-08-21 | 0.01 | 20 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3465 | 4 | 19.11.4.2 | 단위 성능 테스트 - 기업 뱅킹 |  | 성능테스트 수행팀 | 0 | 2015-07-27 | 2015-08-21 | 0.01 | 20 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3466 | 4 | 19.11.4.3 | 단위 성능 테스트 - 글로벌 맞춤뱅킹 |  | 성능테스트 수행팀 | 0 | 2015-07-27 | 2015-08-21 | 0.01 | 20 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3467 | 4 | 19.11.4.4 | 단위 성능 테스트 - CMS |  | 성능테스트 수행팀 | 0 | 2015-07-27 | 2015-08-21 | 0.01 | 20 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3468 | 4 | 19.11.4.5 | 단위 성능 테스트 - 스마트뱅킹 |  | 성능테스트 수행팀 | 0 | 2015-07-27 | 2015-08-21 | 0.01 | 20 |  |  | 0.01 | 0 | 0 | 0% | 0%
| 3469 | 4 | 19.11.4.6 | 통합 성능 테스트 |  | 성능테스트 수행팀 | 0 | 2015-08-24 | 2015-09-04 | 0.025 | 10 |  |  | 0.025 | 0 | 0 | 0% | 0%
| 3470 | 4 | 19.11.4.7 | 임계 성능 테스트 |  | 성능테스트 수행팀 | 0 | 2015-09-07 | 2015-09-11 | 0.025 | 5 |  |  | 0.025 | 0 | 0 | 0% | 0%
| 3471 | 4 | 19.11.4.8 | 통합 연동 성능 테스트 |  | 성능테스트 수행팀 | 0 | 2015-09-14 | 2015-09-18 | 0.025 | 5 |  |  | 0.025 | 0 | 0 | 0% | 0%
| 3472 | 4 | 19.11.4.9 | 안정성 테스트 |  | 성능테스트 수행팀 | 0 | 2015-09-18 | 2015-09-23 | 0.025 | 4 |  |  | 0.025 | 0 | 0 | 0% | 0%
| 3473 | 3 | 19.11.5 | 성능 테스트 결과 분석 및 보고 | 성능 테스트 결과 보고서 | 성능테스트 수행팀 | 0 | 2015-09-24 | 2015-09-30 | 0.05 | 5 |  |  | 0.05 | 0 | 0 | 0% | 0%
Formulas:
계획 일정 = MINA([계획 일정, row below]:I135)
계획 일정 = MINA([계획 일정, row below])
완료 = MAXA([완료, row below]:J135)
완료 = MAX([완료, row below]:J382)
기간 = NETWORKDAYS([계획 일정],[완료],0)
기간 = NETWORKDAYS([실제 일정],[완료],0)

## Chart (hidden)
- |  | 계획 | 계획 | 완료 | 완료
- | 주 | TASK | 누적TASK | TASK | 누적TASK | 남은TASK | 미완료
- | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 32 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 33 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 34 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 35 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 37 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 38 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 40 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 41 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 42 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 43 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 44 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 46 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 47 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 49 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 51 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 53 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | SUM | #REF! |  | #REF!
-
- |  | 계획 |  | 완료
- | 주 | TASK | 누적TASK | TASK | 누적TASK | 남은TASK | 미완료
- | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 32 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 33 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 34 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 35 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 37 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 38 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 40 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 41 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 42 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 43 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 44 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 46 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 47 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 49 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 51 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 53 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | SUM | #REF! |  | #REF!
-
- | 0 | 계획 |  | 완료 |  | 0 | 0
- | 주 | TASK | 누적TASK | TASK | 누적TASK | 남은TASK | 미완료
- | 1 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 2 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 3 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 4 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 5 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 6 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 7 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 8 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 9 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 10 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 11 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 12 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 13 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 14 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 15 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 16 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 17 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 18 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 19 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 20 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 21 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 22 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 23 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 24 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 25 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 26 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 27 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 28 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 29 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 30 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 31 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 32 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 33 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 34 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 35 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 36 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 37 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 38 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 39 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 40 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 41 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 42 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 43 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 44 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 45 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 46 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 47 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 48 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 49 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 50 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 51 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 52 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 53 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | 54 | #REF! | #REF! | #REF! | #REF! | #REF! | #REF!
- | SUM | #REF! | 0 | #REF! | 0 | 0 | 0
-
차트 내용 분석 (대충^^)
46주차에 4건의 TASK가 계획됨
46주차에 2건의 TASK가 완료됨
차트 내용 분석 (대충^^)
46주차 부터 48주차 까지 총 9건의 TASK가 계획됨
계획 대비 46주차 부터 49주차 까지 각각 TASK가 2,1,2,2 건씩 완료됨
46주차에 4건의 TASK가 계획되었으나 2건 만의 TASK가 완료되었으며,
49주차 현재 완료되지 못한 TASK가 2건이 남아 있음
차트 내용 분석 (대충^^)
본 프로젝트에서 계획된 총 TASK는 9건
완료된 총 TASK는 7건
완료되지 못한 TASK는 총 2건

## Manual (hidden)
프로젝트의 시작일
캘린더에 파란 세로 선으로 자동 표현됨
TODAY 함수
오늘 날짜가 캘린더에 붉은 세로선으로 자동 표현됨
프로젝트의 종료일
캘린더에 붉은 세로 선으로 자동 표현됨
사용자의 지정 휴일
예: 연차,휴가,예비군,공가.... 등등
[표지]Sheet의 A2의 값을 참조함
"Level" 1~9 숫자에 따라서 "조건부서식" 적용
"데이터유형성 검사" 기능 적용
목록: "등록,수정,삭제,추가"
"진행상태"에 따라서 "아이콘" 표시
목록: 완료, 진행중, 미완료
=IF(ISBLANK($S14)=FALSE,1,IF($M14<=$D$6,-1,0))
D6인 오늘날짜와 "계획일정"의 "완료일", "실제일정"의 "완료일"을 비교하여 상태를
아이콘으로 표현함
Level1에 해당하는 "행"은 수식이 적용되어 있음
캘린더에 "실제인정"에 따른 "진행율" 표시를 위해 필요한 항목
"계획총기간", "진척일"은 열 숨김표시로 사용해도 상관없음
"실제진척율"의 %에 따라서 캘린더에 진행율이 표현됨 (조건부 서식)
Level1 제외한 "실제진척율"은 직접입력
[Chart]Sheet에서 주 단위로 Count 하여 차트로 표현
[Chart]Sheet에서 주 단위로 Count 하여 차트로 표현
1년치 캘린더, 월 단위로 그룹핑
캘린더 시작일 직접입력
1년치 캘린더, 월 단위로 그룹핑
해당요일의 "Week"표혐
프로젝트 시작일
Start Date D4
프로젝트 종료일
End Date D8
TOday D6
계획일정 조건부서식
실제일정 조건부서식
실제일정 완료일 조건부서식
[Chart]SHeet의 데이터는 1년치 "Week"를 차트로 표현해놨음.
[REV0]Sheet에서 임의의 캘린더(열)을 삭제할 경우 차트에 표현되지 않음.
캘린더의 "열"을 조정할 경우 차트의 "가로축" 값도 조정해줘야 함
차트는 복잡하지 않고, 심플하게 만들었으며 차트 개수도 최소화 했음

## 테스트 (hidden)
하나/외환은행 전자금융 통합 프로젝트 WBS (Work Breakdown Structure)
Start Date ▶ |  | 2015-02-02 | 6th
Today ▶ |  | 2015-04-21 | 17th
End Date ▶ |  | 2015-11-30 | 49th
PROJECT | [8 empty] | 계획 일정 |  |  |  |  | 실제 일정 |  |  |  |  | 진척표시
ID | TASK | [6 empty] | 진행상태
| Level | Code of Account | Title | Comment | Doc | State |  |  | 시작 | 완료 |  | - M/D | 기간 | 시작 | 완료 |  | - M/D | 기간 | 계획 총기간 | 진척일 | 실제 진척율
[6 empty] | List | Date |  |  | 월-일 | 주 |  | Day |  | 월-일 | 주 |  | Day
1 | 1 | 2 | 개인인터넷 뱅킹 | TASK 1 |  | 등록 | 2014-09-05 | #REF! |  | #REF! | #REF! |  | #REF! | #REF! |  | 0 |  | #REF! | #REF! | #REF! | 100%
2 | 2 | 1.1 | 분석 | TASK 2 |  | 등록 | - | 1 | 2015-02-02 | 2015-02-27 | 9 |  | 20 | 2015-11-06 | 2015-11-08 | 46 |  | 1 | 2 | 2015-11-08 | 100%
3 | 3 | 1.1.1 | 현황분석 | TASK 3 |  | 등록 | - | -1 |  | 2015-03-01 | 10 |  | 30045 | 2015-02-02 |  | 0 |  | -30026 | -42037 | 0 | 100%
4 | 4 | 1.1.1.1 | 양행시스템분석 | TASK 4 | 현행 시스템 분석서 | 등록 | - | -1 |  | 2015-03-03 | 10 |  | 30047 | 2015-02-03 |  | 0 |  | -30027 | -42038 | 2015-02-02 | 0%
5 | 3 | 1.1.2 | GAP 분석 | TASK 3 |  | 등록 | - | -1 |  | 2015-03-05 | 10 |  | 30049 | 2015-02-04 |  | 0 |  | -30028 | -42039 | 0 | 100%
6 | 4 | 1.1.1.1 | 메뉴 GAP분석 | TASK 4 | 현행 시스템 분석서 | 등록 | - | -1 |  | 2015-03-07 | 10 |  | 30050 | 2015-02-05 |  | 0 |  | -30029 | -42040 | 2015-02-04 | 0%
7 | 4 | 1.1.1.2 | 전문 GAP분석 | TASK 4 | 현행 시스템 분석서 | 등록 | - | -1 |  | 2015-03-09 | 11 |  | 30051 | 2015-02-06 |  | 0 |  | -30030 | -42041 | 2015-02-05 | 0%
8 | 4 | 1.1.1.3 | 테이블/속성 GAP분석 | TASK 4 | 현행 시스템 분석서 | 등록 | - | -1 |  | 2015-03-11 | 11 |  | 30053 | 2015-02-07 |  | 0 |  | -30030 | -42042 | 2015-02-06 | 0%
9 | 3 | 1.1.3 | 통합업무확정 | TASK 3 |  | 등록 | - | -1 |  | 2015-03-13 | 11 |  | 30055 | 2015-02-08 |  | 0 |  | -30030 | -42043 | 0 | 100%
10 | 4 | 1.1.1.1 | 통합메뉴구조 확정 | TASK 4 | 통합메뉴구조도 | 등록 | - | -1 |  | 2015-03-15 | 12 |  | 30055 | 2015-02-09 |  | 0 |  | -30031 | -42044 | 2015-02-08 | 0%
11 | 3 | 1.1.4 | 통합요건정의 | TASK 3 |  | 등록 | - | -1 |  | 2015-03-17 | 12 |  | 30057 | 2015-02-10 |  | 0 |  | -30032 | -42045 | 0 | 100%
12 | 4 | 1.1.1.1 | 업무별 요건 분류 | TASK 4 | 요구사항정의서 요구사항추적표 | 등록 | - | -1 |  | 2015-03-19 | 12 |  | 30059 | 2015-02-11 |  | 0 |  | -30033 | -42046 | 2015-02-10 | 0%
13 | 3 | 1.1.5 | 논리모델구축 | TASK 3 |  | 등록 | - | -1 |  | 2015-03-21 | 12 |  | 30060 | 2015-02-12 |  | 0 |  | -30034 | -42047 | 0 | 100%
14 | 4 | 1.1.1.1 | 프로세스 모델링 | TASK 4 | 인터페이스 정의서 | 등록 | - | -1 |  | 2015-03-23 | 13 |  | 30061 | 2015-02-13 |  | 0 |  | -30035 | -42048 | 2015-02-12 | 0%
15 | 2 | 2.1 | 설계 | TASK 2 |  | 등록 | - | 1 | 2015-02-18 | 2015-03-18 | 12 |  | 21 | 2015-11-06 | 2015-11-08 | 46 |  | 1 | 2 | 2015-11-08 | 100%
16 | 3 | 2.1.1 | 통합온라인 프로세스 설계 | TASK 3 |  | 등록 | - | -1 |  | 2015-03-20 | 12 |  | 30060 | 2015-02-02 |  | 0 |  | -30026 | -42037 | 0 | 100%
17 | 4 | 2.1.1.1 | 화면설계 | 변경분 | 화면설계서 | 등록 | - | -1 |  | 2015-03-22 | 13 |  | 30060 | 2015-02-03 |  | 0 |  | -30027 | -42038 | 2015-02-02 | 0%
18 | 4 | 2.1.1.2 | 프로그램 설계 | TASK 4 | 프로그램 목록 프로그램 사양서 | 등록 | - | -1 |  | 2015-03-24 | 13 |  | 30062 | 2015-02-04 |  | 0 |  | -30028 | -42039 | 2015-02-03 | 0%
19 | 3 | 2.1.2 | 통합전문설계 | TASK 3 |  | 등록 | - | -1 |  | 2015-03-24 | 13 |  | 30062 | 2015-02-04 |  | 0 |  | -30028 | -42039 | 0 | 100%
20 | 4 | 2.1.2.1 | 전문매핑 | TASK 4 | 전문목록 전문매핑정의서 | 등록 | - | -1 |  | 2015-03-26 | 13 |  | 30064 | 2015-02-05 |  | 0 |  | -30029 | -42040 | 2015-02-04 | 0%
21 | 3 | 2.1.3 | 배치프로세스 설계 | TASK 3 |  | 등록 | - | -1 |  | 2015-03-28 | 13 |  | 30065 | 2015-02-06 |  | 0 |  | -30030 | -42041 | 0 | 100%
22 | 4 | 2.1.3.1 | 배치프로그램 설계 | TASK 4 | 배치프로세스 정의서 | 등록 | - | -1 |  | 2015-03-30 | 14 |  | 30066 | 2015-02-07 |  | 0 |  | -30030 | -42042 | 2015-02-06 | 0%
23 | 3 | 2.1.4 | 테스트 설계 | TASK 3 |  | 등록 | - | -1 |  | 2015-04-01 | 14 |  | 30068 | 2015-02-08 |  | 0 |  | -30030 | -42043 | 0 | 100%
24 | 4 | 2.1.4.1 | 단위테스트 시나리오 작성 | TASK 4 | 단위테스트 시나리오 | 등록 | - | -1 |  | 2015-04-03 | 14 |  | 30070 | 2015-02-09 |  | 0 |  | -30031 | -42044 | 2015-02-08 | 0%
25 | 2 | 3.1 | 구현 | TASK 2 |  | 등록 | - | 1 | 2015-03-02 | 2015-06-16 | 25 |  | 77 | 2015-11-06 | 2015-11-08 | 46 |  | 1 | 2 | 2015-11-08 | 100%
26 | 3 | 3.1.1 | 프로그램 구현 | TASK 3 |  | 등록 | - | 0 |  | 2015-06-18 | 25 |  | 30124 | 2015-02-02 |  | 0 |  | -30026 | -42037 | 0 | 100%
27 | 4 | 3.1.1.1 | 온라인 프로그램 구현 | TASK 4 | 온라인 프로그램 소스코드 | 등록 | - | 0 |  | 2015-06-20 | 25 |  | 30125 | 2015-02-03 |  | 0 |  | -30027 | -42038 | 2015-02-02 | 0%
28 | 4 | 3.1.1.2 | 배치 프로그램 구현 | TASK 4 | 배치 프로그램 소스코드 | 등록 | - | 0 |  | 2015-06-22 | 26 |  | 30126 | 2015-02-04 |  | 0 |  | -30028 | -42039 | 2015-02-03 | 0%
29 | 3 | 2.1.2 | 단위테스트 수행 | TASK 3 |  | 등록 | - | 0 |  | 2015-06-22 | 26 |  | 30126 | 2015-02-04 |  | 0 |  | -30028 | -42039 | 0 | 100%
30 | 4 | 2.1.2.1 | 단위테스트 수행 | TASK 4 | 단위테스트 결과서 | 등록 | - | 0 |  | 2015-06-24 | 26 |  | 30128 | 2015-02-05 |  | 0 |  | -30029 | -42040 | 2015-02-04 | 0%
31 | 2 | 4.1 | 테스트 | TASK 2 |  | 등록 | - | 1 | 2015-06-17 | 2015-10-07 | 41 |  | 81 | 2015-11-06 | 2015-11-08 | 46 |  | 1 | 2 | 2015-11-08 | 100%
32 | 3 | 4.1.1 | 통합테스트 | TASK 3 |  | 등록 | - | 0 |  | 2015-10-09 | 41 |  | 30205 | 2015-02-02 |  | 0 |  | -30026 | -42037 | 0 | 100%
33 | 4 | 4.1.1.1 | 통합테스트 1차 | TASK 4 |  | 등록 | - | 0 |  | 2015-10-11 | 42 |  | 30205 | 2015-02-03 |  | 0 |  | -30027 | -42038 | 2015-02-02 | 0%
33 | 4 | 4.1.1.2 | 통합테스트 2차 | TASK 4 |  | 등록 | - | 0 |  | 2015-10-11 | 42 |  | 30205 | 2015-02-03 |  | 0 |  | -30027 | -42038 | 2015-02-02 | 0%
33 | 4 | 4.1.1.3 | 통합테스트 3차 | TASK 4 |  | 등록 | - | 0 |  | 2015-10-11 | 42 |  | 30205 | 2015-02-03 |  | 0 |  | -30027 | -42038 | 2015-02-02 | 0%
34 | 4 | 4.1.1.4 | 통합테스트 4차 | TASK 4 |  | 등록 | - | 0 |  | 2015-10-13 | 42 |  | 30207 | 2015-02-04 |  | 0 |  | -30028 | -42039 | 2015-02-03 | 0%
35 | 3 | 4.1.1 | 시스템 테스트 | TASK 3 |  | 등록 | - | 0 |  | 2015-10-15 | 42 |  | 30209 | 2015-02-02 |  | 0 |  | -30026 | -42037 | 0 | 100%
35 | 4 | 4.1.1.1 | 시스템 테스트 계획수립 | TASK 4 |  | 등록 | - | 0 |  | 2015-10-15 | 42 |  | 30209 | 2015-02-05 |  | 0 |  | -30029 | -42040 | 2015-02-04 | 0%
36 | 4 | 4.1.1.2 | 성능테스트 1차 | TASK 4 |  | 등록 | - | 0 |  | 2015-10-17 | 42 |  | 30210 | 2015-02-03 |  | 0 |  | -30027 | -42038 | 2015-02-02 | 0%
36 | 4 | 4.1.1.3 | 성능테스트 2차 | TASK 4 |  | 등록 | - | 0 |  | 2015-10-17 | 42 |  | 30210 | 2015-02-03 |  | 0 |  | -30027 | -42038 | 2015-02-02 | 0%
36 | 4 | 4.1.1.4 | 성능테스트 3차 | TASK 4 |  | 등록 | - | 0 |  | 2015-10-17 | 42 |  | 30210 | 2015-02-03 |  | 0 |  | -30027 | -42038 | 2015-02-02 | 0%
35 | 3 | 2.1.2 | 인수테스트 | TASK 3 |  | 등록 | - | 0 |  | 2015-10-13 | 42 |  | 30207 | 2015-02-04 |  | 0 |  | -30028 | -42039 | 0 | 100%
36 | 4 | 2.1.2.1 | 인수테스트 수행 | TASK 4 |  | 등록 | - | 0 |  | 2015-10-15 | 42 |  | 30209 | 2015-02-05 |  | 0 |  | -30029 | -42040 | 2015-02-04 | 0%
END LINE |  |  |  | - | - | - | - | - | - | - | - | - | - | - | - | - | - | -
Formulas:
주 = WEEKNUM([완료])
기간 = NETWORKDAYS([계획 일정],[완료],0)-N14
기간 = NETWORKDAYS([실제 일정],[완료],0)-S14
완료 = [완료, row above]+2
실제 일정 = [실제 일정, row above]+1
진척일 = IF([실제 진척율]=0,[실제 일정]-1,[실제 일정]+(INT([진척표시]*[실제 진척율])))

## 범례 (hidden)
PJT구분 | Level 0 | 가 | Level 3 | 가 | Level 6 | 가 | Level 9 | 지정휴일 | 지정휴일
가 | Level 1 | 가 | Level 4 | 가 | Level 7 |  | 기간
가 | Level 2 | 가 | Level 5 | 가 | Level 8 |  | 완료일